## Export
ID | WorklistID | EquipmentNo | Loc | SubLoc1 | SubLoc2 | EqptType | Discipline | Work Category | Job Category | Request | Worklist Reference 1 | Phase | TaskNo | Task | TaskNote | Dur (Hrs) | Weightage | Group | WCSCode | ActivityCode | SubTasklistCode | SubTasklistType | Total SubTask | For BoxUp | PlanStart | PlanFinish | BL1Start | BL1Finish | BL2Start | BL2Finish | ForecastStart | ForecastEnd | Approved Date | Reference 1 | Reference 2 | Reference 3 | Reference 4
EC55BC0F-01DA-49E5-6073-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 10 | Isolate affecting panel |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 14:00 | [6 empty] | 2026-07-27 01:33 | CPP.E4000
B72832B0-F9E9-40FD-6070-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 20 | Proof dead check if possible before any job execute. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-27 01:33 | CPP.E4010
7CBA2B04-8659-476C-6075-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 30 | Open the panel and rack out the VCB |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-26 09:00 | [6 empty] | 2026-07-27 01:33 | CPP.E4020
82D2D64D-71CD-42B3-6074-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 40 | Do proper cleaning by take out all of the unnecessary remnant |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 11:30 | [6 empty] | 2026-07-27 01:33 | CPP.E4030
FBBCE9AA-909A-4309-6072-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 50 | Remove and dismantle all of the defect components |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 17:00 | [6 empty] | 2026-07-27 01:33 | CPP.E4040
A06B4085-25A8-4AB0-6071-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 60 | Remove all the termination control cables/ thermostat |  | 2.5 | 5 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 09:00 | 2026-07-27 12:00 | [6 empty] | 2026-07-27 01:33 | CPP.E4050
6641B838-C887-4644-606D-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 70 | Tagging the cable if necessary for reference later. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-27 15:00 | [6 empty] | 2026-07-27 01:33 | CPP.E4060
759AD800-76A9-4DE1-6076-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 80 | Install affected components e.g. thermostat,heater, switches, Aux Relay, Bushing/ Arrester, and bushing |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-28 11:30 | [6 empty] | 2026-07-27 01:33 | CPP.E4070
C3F705CA-32A6-4391-606F-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 90 | Wired back the control wiring as per the cable tagging |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 11:30 | 2026-07-28 14:30 | [6 empty] | 2026-07-27 01:33 | CPP.E4080
A3145DF2-5F43-4A6E-606E-08DEEB3BEAFA | TA00190 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | Schneider | Execution | 100 | Housekeeping |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 17:00 | [6 empty] | 2026-07-27 01:33 | CPP.E4090
6B3F353F-C096-4319-6063-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 10 | Isolation of circuit and verify on site |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 14:00 | [6 empty] | 2026-07-27 01:33 | CPP.E2000
7952233A-DD13-437A-6069-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 20 | Functional check on space heater |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 16:30 | [6 empty] | 2026-07-27 01:33 | CPP.E2010
207DA210-9F0D-45D3-606B-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 30 | Functional test on interlock (electrical and mechanical) and Automatic Transfer Switch (ATS) |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 16:30 | 2026-07-26 13:30 | [6 empty] | 2026-07-27 01:33 | CPP.E2020
CE0CC976-F2C5-4A39-6065-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 40 | Functional test on interlock within panel and inter-trip between upstream & downstream |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-27 09:30 | [6 empty] | 2026-07-27 01:33 | CPP.E2030
AF21EC87-16BF-4BC7-606C-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 50 | Physical Inspection on busbar compartment, dropper bars and cable compartments of HV Switchgear/LV MCC |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 10:00 | 2026-07-27 15:00 | [6 empty] | 2026-07-27 01:33 | CPP.E2040
F7825F84-CB07-4862-6066-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 60 | Cleaning for panel, auxiliary and insulation resistance test on main conductor |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-28 11:30 | [6 empty] | 2026-07-27 01:33 | CPP.E2050
8E4E8B5F-866B-437B-6064-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 70 | Contact resistance test and torque check for busbar, dropper bars |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 11:30 | 2026-07-28 13:30 | [6 empty] | 2026-07-27 01:33 | CPP.E2060
4D34FF11-FACE-44E0-6067-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 80 | Online partial discharge measurement (for HV switchgear) |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 13:30 | 2026-07-28 14:30 | [6 empty] | 2026-07-27 01:33 | CPP.E2070
AFF6E89C-B31C-4ED0-6068-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 90 | Reinstate equipment after maintenance |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 16:00 | [6 empty] | 2026-07-27 01:33 | CPP.E2080
03DC02B3-EFC8-47FD-606A-08DEEB3BEAFA | TA00189 | SG-7500 | Bokor | BOCPP-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 100 | Normalise circuit |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 16:00 | 2026-07-28 17:00 | [6 empty] | 2026-07-27 01:33 | CPP.E2090
1B640D7F-CC6E-4C40-F1D4-08DEE9C18370 | TA00188 | STARTUP SEQUENCE LAILA | Laila | LADR-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 10 | Line up Laila Tie-In (HP Mode) at BEDP-A to Baronia |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 08:30 | [6 empty] | 2026-07-25 09:53 | LDA.O2000
C9ABB5AB-627F-4EF5-F1D3-08DEE9C18370 | TA00188 | STARTUP SEQUENCE LAILA | Laila | LADR-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 20 | De-isolate UPS Isolator |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 08:30 | [6 empty] | 2026-07-25 09:53 | LDA.O2010
0191D40C-B30D-472D-F1D5-08DEE9C18370 | TA00188 | STARTUP SEQUENCE LAILA | Laila | LADR-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 30 | Run SDG |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 08:30 | [6 empty] | 2026-07-25 09:53 | LDA.O2020
CDFAC153-FC4D-414D-F1D2-08DEE9C18370 | TA00188 | STARTUP SEQUENCE LAILA | Laila | LADR-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 40 | Energize station |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 08:30 | [6 empty] | 2026-07-25 09:53 | LDA.O2030
A662BFFA-7040-4E6F-F1D6-08DEE9C18370 | TA00188 | STARTUP SEQUENCE LAILA | Laila | LADR-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 50 | Open up LA-102/104 with HP Mode |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-04 08:30 | 2026-08-04 09:00 | [6 empty] | 2026-07-25 09:53 | LDA.O2040
60267CA8-3E5B-4C1F-F1D0-08DEE9C18370 | TA00187 | STARTUP SEQUENCE BAKAU | Bakau | BKP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 10 | Line up valves |  | 1 | 10 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | KPA.O2000
B034EF27-871D-4A88-F1D1-08DEE9C18370 | TA00187 | STARTUP SEQUENCE BAKAU | Bakau | BKP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 20 | Open N2 to ABV and ready to receive |  | 1 | 10 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 16:00 | [6 empty] | 2026-07-25 09:53 | KPA.O2010
6991C687-5883-4C96-F1C9-08DEE9C18370 | TA00186 | STARTUP SEQUENCE BETTY | Betty | BEDP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 10 | Run EDG and IAC |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 13:00 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.O2000
5803037F-E3FB-410B-F1CA-08DEE9C18370 | TA00186 | STARTUP SEQUENCE BETTY | Betty | BEDP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 20 | Ensure adjustable choke is at lowest bean size |  | 0.25 | 2.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 13:45 | [6 empty] | 2026-07-25 09:53 | BPA.O2010
FA93EA00-DB6D-4218-F1CF-08DEE9C18370 | TA00186 | STARTUP SEQUENCE BETTY | Betty | BEDP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 30 | Perform N2 Purging |  | 1 | 10 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 13:45 | 2026-07-31 14:45 | [6 empty] | 2026-07-25 09:53 | BPA.O2020
34EA20C2-348E-4910-F1CB-08DEE9C18370 | TA00186 | STARTUP SEQUENCE BETTY | Betty | BEDP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 40 | Ensure Bakau is ready to receive Crude from Betty |  | 0.25 | 2.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 14:45 | 2026-07-31 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.O2030
430CF742-34A0-44D3-F1CC-08DEE9C18370 | TA00186 | STARTUP SEQUENCE BETTY | Betty | BEDP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 50 | Open up 1 HHP well for fuel gas & gaslift |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 15:00 | 2026-07-31 15:30 | [6 empty] | 2026-07-25 09:53 | BPA.O2040
50F91A57-66CB-41B2-F1CE-08DEE9C18370 | TA00186 | STARTUP SEQUENCE BETTY | Betty | BEDP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 60 | Slowly open up HP and LP wells |  | 1 | 10 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 15:30 | 2026-07-31 16:30 | [6 empty] | 2026-07-25 09:53 | BPA.O2050
7B523BDD-6C68-4617-F1CD-08DEE9C18370 | TA00186 | STARTUP SEQUENCE BETTY | Betty | BEDP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 70 | Run COTP to manage level V-300 |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-31 16:30 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.O2060
0B840E3C-906D-494C-F1C3-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 10 | Line up Baronia to bokor via BOP-A V500 for fuel gas and gaslift |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 13:00 | 2026-08-07 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.O2000
3AE59EBB-AF36-4732-F1C8-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 20 | Flow all Betty LP & HP wells |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 13:15 | 2026-08-07 13:45 | [6 empty] | 2026-07-25 09:53 | CPP.O2010
CC94543D-FFB0-4AF0-F1C5-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 30 | Ensure EDG and utilities running |  | 1 | 15 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 13:30 | 2026-08-07 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.O2020
B05AA0B5-9E1E-437D-F1BE-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 40 | Line up ABV for BOCPP |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 13:45 | 2026-08-07 14:15 | [6 empty] | 2026-07-25 09:53 | CPP.O2030
A8489632-0E04-4B34-F1C6-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 50 | Request HP Gas from Baronia for fuel gas and gaslift & gas injection |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 14:00 | 2026-08-07 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.O2040
AAAD7AF5-3E49-4B46-F1C7-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 60 | Start GTG-7510 & 7520 on Gas Mode and energize power to jacket |  | 1 | 15 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 14:15 | 2026-08-07 15:45 | [6 empty] | 2026-07-25 09:53 | CPP.O2050
938347E1-376A-4291-F1BB-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 70 | Line up ABV for BODP-B/C/D/E/F |  | 1 | 15 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 14:30 | 2026-08-07 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.O2060
204DD306-C0DA-4F59-F1B9-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 80 | Ensure adjustable choke is at lowest bean size |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 14:45 | 2026-08-07 15:45 | [6 empty] | 2026-07-25 09:53 | CPP.O2070
E0CB1526-E478-4AC3-F1C4-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 90 | Reset and energize station at BODP-A |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 15:45 | 2026-08-07 16:15 | [6 empty] | 2026-07-25 09:53 | CPP.O2080
4EA24557-8358-4870-F1C2-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 100 | Gradually open well at BODP-A |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 16:00 | 2026-08-07 16:30 | [6 empty] | 2026-07-25 09:53 | CPP.O2090
A614C024-A667-4872-F1C0-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 110 | Start GLC-A |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 16:30 | 2026-08-07 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.O2100
F998AA44-C3DF-435F-F1BA-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 120 | Reset and energize station at BODP-B |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 17:00 | 2026-08-07 17:30 | [6 empty] | 2026-07-25 09:53 | CPP.O2110
75EFAA36-4F85-4934-F1BC-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 130 | Gradually open well at BODP-B |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 17:15 | 2026-08-07 17:45 | [6 empty] | 2026-07-25 09:53 | CPP.O2120
4B200BC7-44DE-4842-F1C1-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 140 | Monitor V-1010 level |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-07 17:30 | 2026-08-07 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.O2130
7ABE96FD-7376-4FAE-F1BD-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 150 | Start COTP, P-1310A |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-08 08:00 | 2026-08-08 08:30 | [6 empty] | 2026-07-25 09:53 | CPP.O2140
B6815C10-5FED-401B-F1BF-08DEE9C18370 | TA00185 | STARTUP SEQUENCE BOKOR | Bokor | BOCPP-A |  | Start-up | Operation/Process | Maintenance | PPM | Prelim | Operation | Start Up | 160 | Continue open up well |  | 0.5 | 7.5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-08-08 08:00 | 2026-08-08 08:30 | [6 empty] | 2026-07-25 09:53 | CPP.O2150
95B754F8-337C-4B23-F1B8-08DEE9C18370 | TA00184 | BK-ABV9004A | Bakau | BKP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BK-ABV9004A |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 12:00 | [6 empty] | 2026-07-25 09:53 | BKA.RE1040
991D5156-4550-4FF5-F1B7-08DEE9C18370 | TA00183 | BK-ABV9006A | Bakau | BKP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BK-ABV9006A |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 11:30 | [6 empty] | 2026-07-25 09:53 | BKA.RE1030
D900B1A9-4434-4D1D-F1B6-08DEE9C18370 | TA00182 | BK-ABV9100 | Bakau | BKP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BK-ABV9100 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 10:30 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | BKA.RE1020
F9163BE0-AA01-4B67-F1B5-08DEE9C18370 | TA00181 | BK-ABV9101 | Bakau | BKP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BK-ABV9101 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 09:30 | 2026-07-26 10:00 | [6 empty] | 2026-07-25 09:53 | BKA.RE1010
E3BA2864-A540-46AC-F1B4-08DEE9C18370 | TA00180 | BK-ABV9200 | Bakau | BKP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BK-ABV9200 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 09:30 | [6 empty] | 2026-07-25 09:53 | BKA.RE1000
A725C78C-A179-4C01-F1AC-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 10 | Disconnect incoming & outgoing tubing from TLCP |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1000
2A55327B-7C7A-43DF-F1A3-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 20 | Unbolt panel base from grating/platform structure |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1010
788C27BF-86E1-4912-F1AF-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 30 | Transfer out TLCP from existing location |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1020
181F7264-26BE-4FA2-F1B1-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 40 | Disconnect incoming and outgoing tubing for sounder panel |  | 2 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1030
3412A3D0-B595-413C-F1AE-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 50 | Unbolt panel base from grating/platform structure |  | 2 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1040
0F7A9DAF-2C16-4F9D-F1A9-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 60 | Transfer out sounder panel from existing location |  | 2 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1050
C86258D4-0933-428A-F1AD-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 70 | Transfer new TLCP from laydown area to work location |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 14:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1055
34A2202A-8DE8-4A80-F1AB-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 80 | Bolting panel to grating/panel structure |  | 3 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 14:00 | 2026-07-26 17:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1060
C60BBE78-115B-4167-F1B2-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 90 | Tie-in tubing to new TLCP panel |  | 4 | 16 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 08:30 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1070
8A1F8CD2-5CB3-4DA6-F1B0-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 100 | Tie-in modified N2 tubing (from N2 rack to TLCP) |  | 4 | 16 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1075
2CBF6766-0F99-419F-F1A4-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 110 | Installation of new field intruments (10 units) |  | 15 | 45 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1080
3B0ABA28-6559-49E2-F1A8-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 120 | Disconnect incoming and outgoing tubings for Buffer Tank |  | 1 | 7 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1090
86141270-1A18-4E4D-F1AA-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 130 | Unbolt panel base from grating/platform structure |  | 1 | 7 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 11:00 | 2026-07-28 12:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1100
F51DEFA1-B520-4F5F-F1A7-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 140 | Relocate Buffer Tank from existing to new location |  | 2 | 14 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 13:00 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | BKA.I1110
E7F5114C-2672-4362-F1A5-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 150 | Tie-in Buffer Tank |  | 2 | 14 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 15:30 | 2026-07-28 17:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1120
8C967781-C9CE-4B34-F1B3-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 160 | Panel pressurization and leak check (using N2) |  | 7 | 49 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 17:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1130
7D2119AD-ED3A-48F1-F1A6-08DEE9C18370 | TA00179 | TLCP Panel | Bakau | BKP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 170 | Simulating signal loss/functional check |  | 8.5 | 59.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 08:30 | 2026-07-31 10:30 | [6 empty] | 2026-07-25 09:53 | BKA.I1140
E22FC758-57CB-418D-F19F-08DEE9C18370 | TA00178 | BKPA 200-P-09002-11430 - WRAPPING (TASK 28) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 10 | (BKP-A) 200-P-09002-11430: PERFORM SURFACE PREP (VI-05) |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 09:00 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | KPA.C1200
671F9274-8AC1-4D98-F19E-08DEE9C18370 | TA00178 | BKPA 200-P-09002-11430 - WRAPPING (TASK 28) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 20 | (BKP-A) 200-P-09002-11430: MCI INSPECTION (VI-05) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 09:30 | 2026-07-28 09:45 | [6 empty] | 2026-07-25 09:53 | KPA.C1210
89081B7D-83B4-4950-F1A0-08DEE9C18370 | TA00178 | BKPA 200-P-09002-11430 - WRAPPING (TASK 28) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 30 | (BKP-A) 200-P-09002-11430: APPLY MRC (VI-05) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 09:45 | 2026-07-28 10:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1220
83BD0F44-732E-47A7-F1A2-08DEE9C18370 | TA00178 | BKPA 200-P-09002-11430 - WRAPPING (TASK 28) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 40 | (BKP-A) 200-P-09002-11430: CURING (VI-05) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1230
C6B51D2A-EBF5-4EE1-F19D-08DEE9C18370 | TA00178 | BKPA 200-P-09002-11430 - WRAPPING (TASK 28) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 50 | (BKP-A) 200-P-09002-11430: APPLY WRAPPING (VI-05) |  | 1.5 | 3 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 11:00 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | KPA.C1240
CB166F50-12B7-4824-F1A1-08DEE9C18370 | TA00178 | BKPA 200-P-09002-11430 - WRAPPING (TASK 28) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 60 | (BKP-A) 200-P-09002-11430: PERFORM HARDNESS TEST (VI-05) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 16:45 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1250
AFED5DA8-42FE-4948-F198-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BKP-A) 300-PL-13301-61432: ISOLATE LINEWORK |  | 4 | 28 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | KPA.C1000
3A452F2C-5309-4570-F195-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BKP-A) 300-PL-13301-61432: Lifting and pre-lay of spool |  | 5 | 35 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 15:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1005
C63F1F8E-F713-482B-F194-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BKP-A) 300-PL-13301-61432: UNBOLT AND REMOVE CORRODE SPOOL |  | 7 | 49 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 15:30 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1010
8DCD7A1A-ABF0-48C3-F199-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BKP-A) 300-PL-13301-61432: INSTALL AND BOLT UP NEW SPOOL; VI-04 TO VI-06 (14-12") |  | 7 | 49 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1020
B542250F-167B-49F4-F19C-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BKP-A) 300-PL-13301-61432: REPLACE GASKET AND STUDBOLT & NUTS; VI-02 (2 ea Flange 1") |  | 4 | 28 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 15:30 | 2026-07-29 11:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1030
D0458330-D39D-48DE-F19B-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BKP-A) 300-PL-13301-61432: PERFORM BOLT TORQUING (BFJI - 4 NOS) - 2 joints HTW |  | 8 | 56 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 11:00 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1040
5A5A9E14-FF02-409A-F197-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BKP-A) 300-PL-13301-61432: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 14 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1050
3644614B-0DB8-4187-F19A-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 80 | (BKP-A) 300-PL-13301-61432: INSTALL NEOPRENE |  | 2 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-30 17:30 | [6 empty] | 2026-07-25 09:53 | KPA.C1100
6D768F03-2A89-4D10-F196-08DEE9C18370 | TA00177 | 300-PL-13301-61432 - PIPING REPLACEMENT (TASK 24) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 90 | (BKP-A) 300-PL-13301-61432: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 14 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 08:30 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | KPA.C1110
3720E4AB-76F5-4445-F193-08DEE9C18370 | TA00176 | LA-UZV004 | Laila | LADR-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for LA-UZV004 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.RE1020
706B852A-85F2-479F-F192-08DEE9C18370 | TA00175 | LA-UZV001B | Laila | LADR-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for LA-UZV001B |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 13:30 | 2026-07-25 14:00 | [6 empty] | 2026-07-25 09:53 | LDA.RE1010
C9EE03A1-1263-4058-F191-08DEE9C18370 | TA00174 | LA-UZV001A | Laila | LADR-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for LA-UZV001A |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.RE1000
4D0DBD06-80C5-48FD-F18D-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 10 | Perform System Backup (at Bokor) |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 10:00 | [6 empty] | 2026-07-25 09:53 | LDA.I1100
B280039A-869D-4435-F18A-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 20 | Run DeltaV Diagnostics Check (at Bokor) |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1110
FFB84F79-BC22-4DEE-F18C-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 30 | Install DeltaV workstation hotfixes to all DeltaV workstations (1 laptop only at Bokor) |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 11:30 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1120
863928FF-2BB7-4495-F18F-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 40 | Install Microsoft Security Updates sofware to all DeltaV (1 laptop only at Bokor) |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | LDA.I1130
954F6524-0CA4-4697-F190-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 50 | Updated antivirus definitions on all DeltaV workstations (1 laptop only at Bokor) |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 09:00 | 2026-08-01 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1140
5E9D4C2F-C5D6-4A99-F18B-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 60 | Perform Flashing and Upgrade on DeltaV Controller (4 ea) and IO Cards (at Laila) |  | 7 | 7 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 11:30 | 2026-08-02 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1150
D921654F-FA46-4D88-F189-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 70 | Perform cabinet check on hardware conditions (at Laila) |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 13:30 | 2026-08-02 16:00 | [6 empty] | 2026-07-25 09:53 | LDA.I1160
BDA158C5-33EA-4525-F18E-08DEE9C18370 | TA00173 | Emerson DeltaV IPS/ FGS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 80 | Gather the latest DeltaV System Registration/ Perform System Backup (at Bokor) |  | 3.5 | 3.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 16:00 | 2026-08-03 12:00 | [6 empty] | 2026-07-25 09:53 | LDA.I1170
10D33C07-E7C7-4F96-F180-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 10 | Hardware Physical Inspection |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 10:00 | [6 empty] | 2026-07-25 09:53 | LDA.I.1000
2356DCD8-A25B-41E5-F184-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 20 | System/ Database/ Software Backup |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.I.1010
514D0155-32CB-4F9E-F182-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 30 | Check current station "DEV_MONITOR" |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.I.1020
6474FB3B-5B82-47EB-F183-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 40 | EWS1&2 - Verify system alarms, station host relationship, comm., system manager counter, network status, fieldbus status |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | LDA.I.1030
99C1EF2F-0E36-482A-F188-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 50 | Perform Quickfix installation |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 09:00 | 2026-08-01 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1000
F2078579-807B-4A37-F186-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 60 | Perform Antivirus Updates |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 11:30 | 2026-08-01 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1010
655321FB-4289-4C81-F185-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 70 | Perform Windows Patching |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 14:30 | 2026-08-02 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1020
97FA4159-7479-426C-F181-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 80 | Perform Database & Graphic Backup |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 11:30 | 2026-08-02 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1030
E6792FE3-07A9-420E-F187-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 90 | Perform FCP and FBM firmware update |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 14:30 | 2026-08-02 17:00 | [6 empty] | 2026-07-25 09:53 | LDA.I1040
83284216-59B5-4739-F17F-08DEE9C18370 | TA00172 | Foxboro DCS | Laila | LADR-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 100 | Perform Workstation Backup |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 09:00 | 2026-08-03 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.I1050
D4F7686D-9169-447B-F179-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 10 | Isolate the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1200
708F0E59-F967-4789-F177-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 20 | Check condition of CT/VT |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 11:00 | 2026-07-28 12:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1210
4CAB4FA2-89EB-4450-F17B-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 30 | Record protection relay settings |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 13:00 | 2026-07-28 14:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1220
79503D26-1CE3-49E5-F178-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 40 | Test equipment setup with wiring connection |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 14:00 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1230
236224A3-1085-4452-F17E-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 50 | Perform primary / secondary injection test |  | 3 | 6 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 15:30 | 2026-07-29 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1240
842B8677-0553-4181-F17A-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 60 | Record measurement |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 11:30 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1250
E45133F3-91FB-45DB-F17C-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 70 | Reset protection relay |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1260
2089AF67-50AF-46DB-F17D-08DEE9C18370 | TA00171 | SR-100E1 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 80 | Normalize ACB/VCB & housekeeping |  | 1.5 | 3 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 14:30 | 2026-07-29 16:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1270
4E3CB247-F67F-42AD-F175-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 10 | Isolate the ACB/VCB |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 09:30 | 2026-07-26 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1000
5B91F6F9-3376-4999-F176-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 20 | Check condition of CT/VT |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1010
303C7C64-E26B-4C81-F173-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 30 | Record protection relay settings |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-26 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1020
B33DA7EC-AB9D-442F-F16F-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 40 | Test equipment setup with wiring connection |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 14:30 | 2026-07-26 16:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1030
A44AEE65-DAB0-4E62-F172-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 50 | Perform primary / secondary injection test |  | 3 | 6 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 16:00 | 2026-07-27 12:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1040
E41DFE54-E066-42D0-F170-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 60 | Record measurement |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1050
226C975A-45A4-45C8-F171-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 70 | Reset protection relay |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | LDA.E1060
BAD25C06-CB4A-4D3D-F174-08DEE9C18370 | TA00170 | MTG G-7700 | Laila | LADR-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 80 | Normalize ACB/VCB & housekeeping |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-27 16:30 | [6 empty] | 2026-07-25 09:53 | LDA.E1070
8D37472F-67DE-4EF7-F16D-08DEE9C18370 | TA00169 | 010-RV-009 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 15:30 | 2026-07-31 15:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1760
8B54E8AA-DB4A-42E9-F16C-08DEE9C18370 | TA00169 | 010-RV-009 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 15:45 | 2026-07-31 16:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1770
31771EF3-3EE8-448F-F16E-08DEE9C18370 | TA00169 | 010-RV-009 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 11:30 | 2026-08-01 12:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1780
55E023E6-C696-46DF-F16A-08DEE9C18370 | TA00169 | 010-RV-009 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 14:30 | 2026-08-02 15:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1790
58EE102E-B8E5-416A-F16B-08DEE9C18370 | TA00169 | 010-RV-009 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 15:30 | 2026-08-02 16:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1800
44DC27B1-0387-496D-F166-08DEE9C18370 | TA00168 | 010-RV-008 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 14:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1710
88A60ACC-754A-464C-F165-08DEE9C18370 | TA00168 | 010-RV-008 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 14:45 | 2026-07-31 15:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1720
4370E496-A81A-4121-F168-08DEE9C18370 | TA00168 | 010-RV-008 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 11:15 | 2026-08-01 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1730
A912250A-E2AF-4AF3-F169-08DEE9C18370 | TA00168 | 010-RV-008 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 13:30 | 2026-08-02 13:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1740
D94B0EDA-1145-40F4-F167-08DEE9C18370 | TA00168 | 010-RV-008 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 14:00 | 2026-08-02 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1750
0CBE2A75-6E1E-4C55-F161-08DEE9C18370 | TA00167 | 010-RV-007 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 14:00 | 2026-07-31 14:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1660
6B678BBF-9892-4900-F162-08DEE9C18370 | TA00167 | 010-RV-007 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 14:15 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1670
D562D2D1-4D71-497B-F160-08DEE9C18370 | TA00167 | 010-RV-007 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 11:00 | 2026-08-01 11:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1680
6BE0892C-0B9B-4BD8-F163-08DEE9C18370 | TA00167 | 010-RV-007 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 11:45 | 2026-08-02 12:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1690
E080F4BE-FCCA-4E50-F164-08DEE9C18370 | TA00167 | 010-RV-007 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 13:00 | 2026-08-02 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1700
3DAA78E9-685D-471F-F15C-08DEE9C18370 | TA00166 | 010-RV-006 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 13:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1610
E2E68434-1363-4574-F15F-08DEE9C18370 | TA00166 | 010-RV-006 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 13:45 | 2026-07-31 14:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1620
0184780A-F3C9-4E9D-F15E-08DEE9C18370 | TA00166 | 010-RV-006 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 10:45 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1630
2205C1E7-3730-489C-F15B-08DEE9C18370 | TA00166 | 010-RV-006 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 11:00 | 2026-08-02 11:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1640
EA28701D-051C-4530-F15D-08DEE9C18370 | TA00166 | 010-RV-006 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 11:15 | 2026-08-02 11:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1650
9D01A9A3-56E3-4FFA-F159-08DEE9C18370 | TA00165 | 010-RV-005 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 13:00 | 2026-07-31 13:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1560
105E98D5-1C3A-4D04-F157-08DEE9C18370 | TA00165 | 010-RV-005 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 13:15 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1570
44B11B53-4398-4C64-F15A-08DEE9C18370 | TA00165 | 010-RV-005 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 10:30 | 2026-08-01 10:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1580
978D1348-452F-4562-F158-08DEE9C18370 | TA00165 | 010-RV-005 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 10:15 | 2026-08-02 10:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1590
4302CC0C-7EA6-4330-F156-08DEE9C18370 | TA00165 | 010-RV-005 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 10:30 | 2026-08-02 11:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1600
18E37583-8782-48A7-F153-08DEE9C18370 | TA00164 | 010-RV-004 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 11:30 | 2026-07-31 11:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1510
76D78AAC-C2FB-46BA-F154-08DEE9C18370 | TA00164 | 010-RV-004 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 11:45 | 2026-07-31 12:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1520
660241EB-EAF0-44A0-F152-08DEE9C18370 | TA00164 | 010-RV-004 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 10:15 | 2026-08-01 10:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1530
B896036B-8586-4FEF-F155-08DEE9C18370 | TA00164 | 010-RV-004 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 09:30 | 2026-08-02 09:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1540
ED76C85C-6F1B-4E58-F151-08DEE9C18370 | TA00164 | 010-RV-004 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 09:45 | 2026-08-02 10:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1550
3187231C-1835-4A7D-F14C-08DEE9C18370 | TA00163 | 010-RV-003 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 11:00 | 2026-07-31 11:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1460
7253ADCC-5476-4406-F150-08DEE9C18370 | TA00163 | 010-RV-003 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 11:15 | 2026-07-31 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1470
69E23A0C-A2C7-4A8B-F14D-08DEE9C18370 | TA00163 | 010-RV-003 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 10:00 | 2026-08-01 10:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1480
7922BFB4-0022-4EED-F14E-08DEE9C18370 | TA00163 | 010-RV-003 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 14:45 | 2026-08-01 15:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1490
90ECAB2E-0048-460C-F14F-08DEE9C18370 | TA00163 | 010-RV-003 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 15:30 | 2026-08-01 16:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1500
8B6D318D-5975-4108-F14A-08DEE9C18370 | TA00162 | 010-RV-002 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 10:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1410
224053B2-A7B2-4BA4-F14B-08DEE9C18370 | TA00162 | 010-RV-002 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 10:45 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1420
14EBBAE7-2E65-4E2E-F149-08DEE9C18370 | TA00162 | 010-RV-002 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 09:45 | 2026-08-01 10:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1430
9C8659F8-AD08-4BB4-F147-08DEE9C18370 | TA00162 | 010-RV-002 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 14:00 | 2026-08-01 14:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1440
4425F6BE-6463-4C0B-F148-08DEE9C18370 | TA00162 | 010-RV-002 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 14:15 | 2026-08-01 14:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1450
60512CCE-DED8-49E2-F143-08DEE9C18370 | TA00161 | 010-RV-001 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 10:00 | 2026-07-31 10:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1360
F14CFEE4-4ACC-47CB-F142-08DEE9C18370 | TA00161 | 010-RV-001 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 10:15 | 2026-07-31 10:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1370
6F1D2CB8-D414-4A67-F144-08DEE9C18370 | TA00161 | 010-RV-001 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 09:30 | 2026-08-01 09:45 | [6 empty] | 2026-07-25 09:53 | LDA.S1380
5C2FACE3-AE25-42CE-F146-08DEE9C18370 | TA00161 | 010-RV-001 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 13:00 | 2026-08-01 13:15 | [6 empty] | 2026-07-25 09:53 | LDA.S1390
EA8BBE6C-9029-48E6-F145-08DEE9C18370 | TA00161 | 010-RV-001 (1/4" FNPT) | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 13:30 | 2026-08-01 14:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1400
67D80DDE-DF56-41CD-F141-08DEE9C18370 | TA00160 | 640-PSE-001 (4"x4") | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 09:30 | 2026-07-30 10:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1300
13D28EDE-65FA-4E44-F13F-08DEE9C18370 | TA00160 | 640-PSE-001 (4"x4") | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 1.5 | 9 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 10:00 | 2026-07-30 11:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1310
072A486D-6B7D-4070-F13C-08DEE9C18370 | TA00160 | 640-PSE-001 (4"x4") | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 1 | 6 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 11:30 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | LDA.S1320
4C1EBD05-8AE7-40A7-F13E-08DEE9C18370 | TA00160 | 640-PSE-001 (4"x4") | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 1.5 | 9 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | LDA.S1330
463FB0F8-3414-44A2-F13D-08DEE9C18370 | TA00160 | 640-PSE-001 (4"x4") | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 15:50 | 2026-07-30 16:20 | [6 empty] | 2026-07-25 09:53 | LDA.S1340
10EEBD5C-50E0-464D-F140-08DEE9C18370 | TA00160 | 640-PSE-001 (4"x4") | Laila | LADR-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 16:20 | 2026-07-31 09:50 | [6 empty] | 2026-07-25 09:53 | LDA.S1350
6D01D15C-A975-4900-F133-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 10 | Perform System Backup |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1200
98D0B442-3A58-48F8-F138-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 20 | Backup Current Logic |  | 0.5 | 0.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 14:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1210
9DAF7F27-CF9B-4F53-F137-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 30 | Verify Control Program Application Version |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 14:30 | 2026-07-25 16:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1220
E25A8E92-1691-4EB8-F136-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 40 | Verify Fault Alarm Status |  | 1.5 | 1.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 16:00 | 2026-07-26 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1230
1F3A4E58-81EA-4F0B-F134-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 50 | IO Count Check |  | 5 | 5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 09:30 | 2026-07-26 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1240
85370AF0-E626-4F24-F131-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 60 | Verify Important Setting of MODICON PLC |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 16:30 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1250
BE7056A1-1547-49B1-F13B-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 70 | Perform Systems Diagnostic Health Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 11:30 | 2026-07-27 14:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1260
1F97F157-5151-418E-F139-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 80 | Measure and Record Power Supply Voltage |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 14:30 | 2026-07-28 11:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1270
AF279BB2-7170-4005-F130-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 90 | Identify Details of Power Supply Model and Part No. |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 11:30 | 2026-07-28 14:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1280
618CABEC-E090-4CE7-F13A-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 100 | Loose Connection Check |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 16:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1290
40B705D4-EB51-412D-F132-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 110 | Check Controller and Cabinet Temperature |  | 0.5 | 0.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 16:00 | 2026-07-28 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1300
2ACCE600-5314-4F98-F135-08DEE9C18370 | TA00159 | Modicon M580 PLC | Betty | BEDP-A |  | Local Control Panel | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 120 | Check Physical Condition Module Availability and Health Check |  | 3.5 | 3.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 16:30 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1310
D6C014E8-1163-4FA8-F12E-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 10 | Perform System Backup (at Bokor) |  | 3 | 3 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1100
C0423548-F419-4862-F12F-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 20 | Run DeltaV Diagnostics Check (at Bokor) |  | 3 | 3 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 16:30 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1110
79F9ABB4-5F6A-496F-F12B-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 30 | Install DeltaV workstation hotfixes to all DeltaV workstations (2 PCs at BEDP-A) |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1120
93981A6E-B09C-4E65-F12C-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 40 | Install Microsoft Security Updates sofware to all DeltaV (2 PCs at BEDP-A) |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 16:30 | 2026-07-27 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1130
F08A98C1-57EB-429B-F128-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 50 | Updated antivirus definitions on all DeltaV workstations (2 PCs at BEDP-A) |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1140
00B8D19A-B02E-4BB7-F129-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 60 | Perform Flashing and Upgrade on DeltaV Controller (4 ea) and IO Cards (at BEDP-A) |  | 7 | 7 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1150
51E17A41-00E9-401B-F12A-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 70 | Perform cabinet check on hardware conditions (at BEDP-A) |  | 8 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 15:30 | 2026-07-29 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1160
E1D2CAEF-A083-4446-F12D-08DEE9C18370 | TA00158 | Emerson DeltaV IPS/ FGS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | EMERSON | Execution | 80 | Gather the latest DeltaV System Registration/ Perform System Backup (at Bokor) |  | 6 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 16:30 | 2026-07-30 17:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1170
83E8386C-0EAC-461B-F127-08DEE9C18370 | TA00157 | Foxboro DCS | Betty | BEDP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 10 | Perform Backup (fom Pre-TA) |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1000
ADD219E8-6EC1-4D60-F124-08DEE9C18370 | TA00157 | Foxboro DCS | Betty | BEDP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 20 | Perform Quickfix installation |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1005
8B270433-D18D-4F1F-F122-08DEE9C18370 | TA00157 | Foxboro DCS | Betty | BEDP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 30 | Perform Antivirus Updates |  | 5 | 5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 14:00 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.I1010
F63214FE-887C-4DFA-F126-08DEE9C18370 | TA00157 | Foxboro DCS | Betty | BEDP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 40 | Perform Windows Patching |  | 6 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1020
9F55419B-DF00-435F-F125-08DEE9C18370 | TA00157 | Foxboro DCS | Betty | BEDP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 50 | Perform Database & Graphic Backup |  | 6 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 17:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1030
FD55A5E5-5BAB-4241-F121-08DEE9C18370 | TA00157 | Foxboro DCS | Betty | BEDP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 60 | Perform FCP and FBM firmware update |  | 6 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1040
9AE3113C-9901-4255-F123-08DEE9C18370 | TA00157 | Foxboro DCS | Betty | BEDP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | FOXBORO | Execution | 70 | Perform Workstation Backup |  | 6 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 16:30 | 2026-07-30 17:30 | [6 empty] | 2026-07-25 09:53 | BDA.I1050
CBF5D998-2445-40BA-F11E-08DEE9C18370 | TA00156 | BAT-7810B | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Preparation for battery discharge test & Perform cleaning on battery bank Tag No. BAT-7810B. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 09:00 | 2026-07-29 10:00 | [6 empty] | 2026-07-25 09:53 | BDA.E6010
EB11C1C5-5742-4D24-F11F-08DEE9C18370 | TA00156 | BAT-7810B | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Perform battery discharge test on battery bank Tag no. BAT-7810B. |  | 5 | 10 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-29 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.E6020
5E1E7996-F255-44C3-F120-08DEE9C18370 | TA00156 | BAT-7810B | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 30 | Normalise electrical isolation |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 10:00 | [6 empty] | 2026-07-25 09:53 | BDA.E6030
91A93A72-90A4-48DC-F11B-08DEE9C18370 | TA00155 | BAT-7840 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Transfer and set up load bank |  | 6 | 12 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.E5010
5D1552E3-6938-49ED-F11A-08DEE9C18370 | TA00155 | BAT-7840 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Preparation for battery discharge test & Perform cleaning on battery bank Tag No. BAT-7840. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 09:00 | 2026-07-27 10:00 | [6 empty] | 2026-07-25 09:53 | BDA.E5015
1EB5DE91-1EA2-410D-F11C-08DEE9C18370 | TA00155 | BAT-7840 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 30 | Perform battery discharge test on battery bank Tag no. BAT-7840. |  | 5 | 10 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 10:30 | 2026-07-27 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.E5020
77211921-19FF-4933-F11D-08DEE9C18370 | TA00155 | BAT-7840 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 40 | Normalise electrical isolation |  | 0.5 | 1 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 09:00 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.E5030
ABAC29B6-791C-4D94-F117-08DEE9C18370 | TA00154 | NCCP-7830 | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Perform electrical isolation |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 11:30 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | BDA.E2000
15D9C526-BD15-41DB-F119-08DEE9C18370 | TA00154 | NCCP-7830 | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Perform PPM on NCCP-7830 |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 16:00 | [6 empty] | 2026-07-25 09:53 | BDA.E2010
6720A6F7-3AE9-447F-F118-08DEE9C18370 | TA00154 | NCCP-7830 | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 30 | Normalise electrical isolation |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 16:00 | 2026-07-30 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.E2020
B7075A87-BD44-438D-F115-08DEE9C18370 | TA00153 | UPS-7810A/B | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Perform electrical isolation |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 09:30 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.E3000
55DCE554-5A29-4BA8-F114-08DEE9C18370 | TA00153 | UPS-7810A/B | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Perform PPM on UPS-7810A/B |  | 3.5 | 7 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 11:00 | 2026-07-28 16:00 | [6 empty] | 2026-07-25 09:53 | BDA.E3010
13E5F2CD-AE13-458A-F116-08DEE9C18370 | TA00153 | UPS-7810A/B | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 30 | Normalise electrical isolation |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 16:00 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.E3020
EB293E38-FA3D-4A35-F112-08DEE9C18370 | TA00152 | UPS-7840 | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Perform electrical isolation |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.E1000
32227C06-001E-4F4F-F113-08DEE9C18370 | TA00152 | UPS-7840 | Betty | BEDP-A |  | UPS Battery | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Perform PPM on UPS-7840. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.E1010
EC3EAEAC-A060-4FFE-F101-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 10 | (BEDP-A) 200-PG-1001-61492: PERFORM SURFACE PREP (VI-01) - Team 1 |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 09:30 | 2026-07-29 10:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2010
908CDCBC-F2B8-477A-F100-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 20 | (BEDP-A) 200-PG-1001-61492: MCI INSPECTION (VI-01) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-29 10:45 | [6 empty] | 2026-07-25 09:53 | BDA.C2020
954D95E8-4695-4E63-F0F2-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 30 | (BEDP-A) 200-PG-1001-61492: APPLY MRC (VI-01) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 10:45 | 2026-07-29 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2030
17705702-6D81-47A4-F0F6-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 40 | (BEDP-A) 200-PG-1001-61492: CURING (VI-01) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 11:00 | 2026-07-29 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2040
CABCA408-2C9D-4F74-F0FB-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 50 | (BEDP-A) 200-PG-1001-61492: APPLY WRAPPING (VI-01) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 13:00 | 2026-07-29 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2050
0E631C15-9515-4F8C-F10D-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 60 | (BEDP-A) 200-PG-1001-61492: PERFORM SURFACE PREP (VI-02) - Team 2 |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 14:00 | 2026-07-29 14:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2120
CE636E82-929A-45EA-F0FA-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 70 | (BEDP-A) 200-PG-1001-61492: MCI INSPECTION (VI-02) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 14:30 | 2026-07-29 14:45 | [6 empty] | 2026-07-25 09:53 | BDA.C2130
F4F0162C-B55C-4717-F0F5-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 80 | (BEDP-A) 200-PG-1001-61492: APPLY MRC (VI-02) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 14:45 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2140
ED4475E3-86C5-40FD-F103-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 90 | (BEDP-A) 200-PG-1001-61492: CURING (VI-02) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 15:00 | 2026-07-29 16:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2150
CED2392D-3646-45D0-F0FD-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 100 | (BEDP-A) 200-PG-1001-61492: APPLY WRAPPING (VI-02) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 16:00 | 2026-07-29 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2160
F49D72E4-B01F-4778-F10A-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 110 | (BEDP-A) 200-PG-1001-61492: PERFORM HARDNESS TEST (VI-02) - Team 1 |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 09:15 | [6 empty] | 2026-07-25 09:53 | BDA.C2161
DDAC75D7-4AB4-4911-F0EF-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 120 | (BEDP-A) 200-PG-1001-61492: PERFORM HARDNESS TEST (VI-01) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 09:15 | 2026-07-30 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2162
B73F7D70-D8F8-4FFC-F109-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 130 | (BEDP-A) 200-PG-1001-61492: PERFORM SURFACE PREP (VI-08) |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 09:30 | 2026-07-30 10:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2170
9F7BBC63-6074-47D3-F0F7-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 140 | (BEDP-A) 200-PG-1001-61492: MCI INSPECTION (VI-08) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 10:30 | 2026-07-30 10:45 | [6 empty] | 2026-07-25 09:53 | BDA.C2180
686E7007-D6F1-4F22-F106-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 150 | (BEDP-A) 200-PG-1001-61492: APPLY MRC (VI-08) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 10:45 | 2026-07-30 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2190
08C0E171-08D0-44D8-F102-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 160 | (BEDP-A) 200-PG-1001-61492: CURING (VI-08) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 11:00 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2200
BB42B719-A231-4D22-F0FC-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 170 | (BEDP-A) 200-PG-1001-61492: APPLY WRAPPING (VI-08) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2210
D578BFFD-D753-43F4-F0F8-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 180 | (BEDP-A) 200-PG-1001-61492: PERFORM SURFACE PREP (VI-09) |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 14:00 | 2026-07-30 14:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2220
66E45D25-5AE8-41F1-F110-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 190 | (BEDP-A) 200-PG-1001-61492: MCI INSPECTION (VI-09) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 14:30 | 2026-07-30 14:45 | [6 empty] | 2026-07-25 09:53 | BDA.C2230
F18CD42C-0059-4E7A-F0F1-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 200 | (BEDP-A) 200-PG-1001-61492: APPLY MRC (VI-09) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 14:45 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2240
4CA80975-897B-4CA1-F0FE-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 210 | (BEDP-A) 200-PG-1001-61492: CURING (VI-09) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 15:00 | 2026-07-30 16:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2250
8427A29F-5859-4FC0-F0FF-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 220 | (BEDP-A) 200-PG-1001-61492: APPLY WRAPPING (VI-09) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 16:00 | 2026-07-30 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2260
EB31E187-48C4-4D0E-F0F4-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 230 | (BEDP-A) 200-PG-1001-61492: PERFORM HARDNESS TEST (VI-09) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 09:15 | [6 empty] | 2026-07-25 09:53 | BDA.C2261
E10353EB-60F6-46E9-F0F0-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 240 | (BEDP-A) 200-PG-1001-61492: PERFORM HARDNESS TEST (VI-08) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 09:15 | 2026-07-31 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2262
35027FFE-9B0A-4C14-F0F9-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 250 | (BEDP-A) 200-PG-1001-61492: PERFORM SURFACE PREP (VI-04) - Team 2 |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2270
02003E51-30EF-4A94-F10B-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 260 | (BEDP-A) 200-PG-1001-61492: MCI INSPECTION (VI-04) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 09:30 | 2026-07-30 09:45 | [6 empty] | 2026-07-25 09:53 | BDA.C2280
77B7885A-A447-43E9-F107-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 270 | (BEDP-A) 200-PG-1001-61492: APPLY MRC (VI-04) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 09:45 | 2026-07-30 10:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2290
CF976E4F-95B6-40E9-F0F3-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 280 | (BEDP-A) 200-PG-1001-61492: CURING (VI-04) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 10:00 | 2026-07-30 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2300
FD1F2F44-AF88-4636-F0EE-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 290 | (BEDP-A) 200-PG-1001-61492: APPLY WRAPPING (VI-04) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 11:00 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2310
6576B942-144C-4788-F10F-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 300 | (BEDP-A) 200-PG-1001-61492: PERFORM SURFACE PREP (VI-10) |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2320
6C472058-F2B7-4C21-F105-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 310 | (BEDP-A) 200-PG-1001-61492: MCI INSPECTION (VI-10) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 13:45 | [6 empty] | 2026-07-25 09:53 | BDA.C2330
7BDB98FD-C302-4D1D-F10C-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 320 | (BEDP-A) 200-PG-1001-61492: APPLY MRC (VI-10) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 13:45 | 2026-07-30 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2340
2293B015-175D-4674-F104-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 330 | (BEDP-A) 200-PG-1001-61492: CURING (VI-10) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 14:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.C2350
50442ADD-AFC4-4486-F108-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 340 | (BEDP-A) 200-PG-1001-61492: APPLY WRAPPING (VI-10) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-30 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2360
A81218BB-AE77-432B-F111-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 350 | (BEDP-A) 200-PG-1001-61492: PERFORM HARDNESS TEST (VI-10) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 09:15 | [6 empty] | 2026-07-25 09:53 | BDA.C2361
8742D3D6-1EA1-4F53-F10E-08DEE9C18370 | TA00151 | 200-PG-1001-61492 - WRAPPING (TASK 27) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 360 | (BEDP-A) 200-PG-1001-61492: PERFORM HARDNESS TEST (VI-04) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 09:15 | 2026-07-31 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.C2362
97AAA784-4D42-4E94-F0E8-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEDP-A) V-1600: ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 10:00 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1500
503FAB0C-97E5-4E3C-F0E9-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEDP-A) V-1600: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ N6, DN 80 VALVE; V5 |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-27 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1510
64AAE172-41CA-4383-F0EA-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEDP-A) V-1600: INSTALL BOLTING AND GASKETS @ N6, DN 80 VALVE; V5 |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1520
1832DCB2-3F2D-4222-F0E7-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEDP-A) V-1600: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ N5, DN 80 VALVE; V6 |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1530
96B7D797-3718-4C58-F0EB-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEDP-A) V-1600: INSTALL BOLTING AND GASKETS @ N5, DN 80 VALVE; V6 |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-27 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.C1540
C6EE67DB-F5F3-4C6C-F0ED-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BEDP-A) V-1600: PERFORM BOLT TORQUING (BFJI - 4 NOS) |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 16:30 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.C1550
92E3CBA7-A61A-4648-F0EC-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BEDP-A) V-1600: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 8 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1560
E64273B7-53B7-430F-F0E6-08DEE9C18370 | TA00150 | V-1600 - STUDBOLT & GASKET REPLACEMENT (TASK 23) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 80 | (BEDP-A) V-1600: DE-ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 13:00 | 2026-07-28 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1570
B8E46764-C7C4-4C71-F0E1-08DEE9C18370 | TA00149 | V-6300 TO LEVEL GAUGE - STUDBOLT & GASKET REPLACEMENT (TASK 22) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEDP-A) V-6300: ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1000
6C4B12F2-CAEC-4EA4-F0E3-08DEE9C18370 | TA00149 | V-6300 TO LEVEL GAUGE - STUDBOLT & GASKET REPLACEMENT (TASK 22) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEDP-A) V-6300: REPLACE CORRODED GASKET AND STUDBOLT & NUTS; VI-15 (N7) |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-27 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1010
D035FEA5-6C3D-4B0F-F0E5-08DEE9C18370 | TA00149 | V-6300 TO LEVEL GAUGE - STUDBOLT & GASKET REPLACEMENT (TASK 22) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEDP-A) V-6300: PERFORM BOLT TORQUING (BFJI - 1 NOS 1") |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 08:30 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.C1020
082C9294-D7AA-4F27-F0E2-08DEE9C18370 | TA00149 | V-6300 TO LEVEL GAUGE - STUDBOLT & GASKET REPLACEMENT (TASK 22) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEDP-A) V-6300: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.C1030
14F459C2-1C18-4A77-F0E4-08DEE9C18370 | TA00149 | V-6300 TO LEVEL GAUGE - STUDBOLT & GASKET REPLACEMENT (TASK 22) | Betty | BEDP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEDP-A) V-6300: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 1.5 | 7.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 11:00 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | BDA.C1040
09BB561C-0F1F-40C3-F0DC-08DEE9C18370 | TA00148 | PSV P2 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 10:50 | 2026-07-28 11:05 | [6 empty] | 2026-07-25 09:53 | BDA.S1500
127AFF08-CCB6-4A03-F0DE-08DEE9C18370 | TA00148 | PSV P2 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 11:05 | 2026-07-28 11:20 | [6 empty] | 2026-07-25 09:53 | BDA.S1510
78A76BB0-C9E6-4719-F0DF-08DEE9C18370 | TA00148 | PSV P2 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 13:35 | 2026-07-28 13:50 | [6 empty] | 2026-07-25 09:53 | BDA.S1520
16BCC331-6919-4534-F0DD-08DEE9C18370 | TA00148 | PSV P2 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 15:45 | 2026-07-28 16:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1530
D503EEA2-0D83-4CA1-F0E0-08DEE9C18370 | TA00148 | PSV P2 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:45 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1540
AB235F7D-6FCA-4FB2-F0DB-08DEE9C18370 | TA00147 | PSV P1 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 09:50 | 2026-07-28 10:35 | [6 empty] | 2026-07-25 09:53 | BDA.S1450
F47380D9-AEDF-41E4-F0DA-08DEE9C18370 | TA00147 | PSV P1 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 10:35 | 2026-07-28 10:50 | [6 empty] | 2026-07-25 09:53 | BDA.S1460
88DAAA15-00AE-4CA5-F0D8-08DEE9C18370 | TA00147 | PSV P1 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 13:20 | 2026-07-28 13:35 | [6 empty] | 2026-07-25 09:53 | BDA.S1470
D2DC2BC3-0E86-41D1-F0D7-08DEE9C18370 | TA00147 | PSV P1 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 15:30 | 2026-07-28 15:45 | [6 empty] | 2026-07-25 09:53 | BDA.S1480
6F249987-83E1-471B-F0D9-08DEE9C18370 | TA00147 | PSV P1 (1/4" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:45 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1490
E3300FF9-CC10-4A1D-F0D6-08DEE9C18370 | TA00146 | PSV UU1 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 09:15 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | BDA.S1400
D5EBDF01-5B0D-46B0-F0D4-08DEE9C18370 | TA00146 | PSV UU1 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 09:35 | 2026-07-28 09:50 | [6 empty] | 2026-07-25 09:53 | BDA.S1410
F0708CF2-AEB4-41B0-F0D5-08DEE9C18370 | TA00146 | PSV UU1 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 13:05 | 2026-07-28 13:20 | [6 empty] | 2026-07-25 09:53 | BDA.S1420
DC4686F5-1A78-441A-F0D2-08DEE9C18370 | TA00146 | PSV UU1 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 14:45 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1430
76DB814A-28CF-496B-F0D3-08DEE9C18370 | TA00146 | PSV UU1 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:30 | 2026-07-28 16:45 | [6 empty] | 2026-07-25 09:53 | BDA.S1440
129D856E-8C62-489F-F0CF-08DEE9C18370 | TA00145 | PSV 1605 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 16:45 | 2026-07-27 17:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1350
991176D2-1C64-42F7-F0CD-08DEE9C18370 | TA00145 | PSV 1605 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 09:00 | 2026-07-28 09:15 | [6 empty] | 2026-07-25 09:53 | BDA.S1360
336EFF56-E5DC-48D2-F0D0-08DEE9C18370 | TA00145 | PSV 1605 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 11:50 | 2026-07-28 13:05 | [6 empty] | 2026-07-25 09:53 | BDA.S1370
2FB1C8B6-2ACA-4765-F0D1-08DEE9C18370 | TA00145 | PSV 1605 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 14:45 | [6 empty] | 2026-07-25 09:53 | BDA.S1380
E5F1B633-85E4-4357-F0CE-08DEE9C18370 | TA00145 | PSV 1605 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:15 | 2026-07-28 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.S1390
E559BFBC-D20B-41C2-F0CA-08DEE9C18370 | TA00144 | PSV 962 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 16:15 | 2026-07-27 16:30 | [6 empty] | 2026-07-25 09:53 | BDA.S1300
0897BBA7-F5BC-459C-F0CB-08DEE9C18370 | TA00144 | PSV 962 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 16:30 | 2026-07-27 16:45 | [6 empty] | 2026-07-25 09:53 | BDA.S1310
F4615519-94BA-4970-F0C9-08DEE9C18370 | TA00144 | PSV 962 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 11:35 | 2026-07-28 11:50 | [6 empty] | 2026-07-25 09:53 | BDA.S1320
256193D1-A4F5-4B65-F0C8-08DEE9C18370 | TA00144 | PSV 962 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 14:15 | 2026-07-28 14:30 | [6 empty] | 2026-07-25 09:53 | BDA.S1330
BBB520F4-24C9-4AB7-F0CC-08DEE9C18370 | TA00144 | PSV 962 (1/2" MNPT) | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:00 | 2026-07-28 16:15 | [6 empty] | 2026-07-25 09:53 | BDA.S1340
427817C8-EC67-4E34-F0C7-08DEE9C18370 | TA00143 | RV 611 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 09:45 | 2026-07-27 10:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1060
ACC6DA73-586D-4598-F0C6-08DEE9C18370 | TA00143 | RV 611 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 10:30 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1070
502D9643-6215-462A-F0C3-08DEE9C18370 | TA00143 | RV 611 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 11:30 | 2026-07-27 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1080
6016AAC7-B9A7-4FC3-F0C4-08DEE9C18370 | TA00143 | RV 611 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.33 | 2 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 13:20 | 2026-07-27 13:40 | [6 empty] | 2026-07-25 09:53 | BDA.S1090
FA71B742-0226-4A46-F0C5-08DEE9C18370 | TA00143 | RV 611 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 14:30 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1100
17AAEC1C-8D27-4649-F0C2-08DEE9C18370 | TA00143 | RV 611 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-27 15:45 | [6 empty] | 2026-07-25 09:53 | BDA.S1110
B9351BEA-5530-4887-F0BC-08DEE9C18370 | TA00142 | RV 612 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 09:00 | 2026-07-27 09:15 | [6 empty] | 2026-07-25 09:53 | BDA.S1000
F7A9C017-4A6E-4973-F0C0-08DEE9C18370 | TA00142 | RV 612 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 09:15 | 2026-07-27 09:45 | [6 empty] | 2026-07-25 09:53 | BDA.S1010
F92EA386-16E0-47D9-F0C1-08DEE9C18370 | TA00142 | RV 612 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-27 11:30 | [6 empty] | 2026-07-25 09:53 | BDA.S1020
07D2B00F-7348-487A-F0BE-08DEE9C18370 | TA00142 | RV 612 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.33 | 2 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-27 13:20 | [6 empty] | 2026-07-25 09:53 | BDA.S1030
B33052E9-51D1-4EE1-F0BD-08DEE9C18370 | TA00142 | RV 612 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 13:40 | 2026-07-27 14:10 | [6 empty] | 2026-07-25 09:53 | BDA.S1040
1691F388-3BE9-4422-F0BF-08DEE9C18370 | TA00142 | RV 612 (1" x 1") | Betty | BEDP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 14:10 | 2026-07-27 14:25 | [6 empty] | 2026-07-25 09:53 | BDA.S1050
480DF1F9-2C44-4265-F0BB-08DEE9C18370 | TA00141 | BEPA-ABV640 | Betty | BEP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BEPA-ABV640 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 14:30 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.RE1040
62C1240B-27C0-43A0-F0BA-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 10 | Lifting and transfer valve to work area and scaffolding by Construction team |  | 3.5 | 10.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.I1000
376F0340-3EF7-478D-F0B3-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 20 | Perform positive isolation (closed 3 manual valves) |  | 2 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 11:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1005
CC4D6C8E-3BE7-478E-F0B0-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 30 | Perform as found diagnostic. |  | 1 | 3 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1010
854A713E-BB20-401D-F0B9-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 40 | Remove tubing, cable and valve accessories. |  | 1 | 3 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-26 14:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1020
8A7889CE-926D-4294-F0B2-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 50 | Remove old control valve. |  | 4 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 14:30 | 2026-07-27 11:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1030
F39DB7B6-F72F-40B3-F0B8-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 60 | New control valve installation and stud bolt torqueing. |  | 6 | 18 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 11:30 | 2026-07-28 11:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1040
37122B15-83B5-44B9-F0B7-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 70 | Reinstate tubing, cable and valve accessories. |  | 2 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 11:30 | 2026-07-28 14:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1050
8547EA45-FDBC-473A-F0B4-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 80 | Perform JIT Verification by PCSB QAQC |  | 2 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.I1060
1B2B01DF-9BF4-452A-F0B1-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 90 | Valve calibration. (Stroke test locally) |  | 4 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 09:00 | 2026-07-29 14:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1070
54D9B7FD-D023-49AB-F0B6-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 100 | SAT with Operation (stroke test) |  | 4 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 14:30 | 2026-07-30 11:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1080
650F4E27-ABB0-439E-F0B5-08DEE9C18370 | TA00140 | PCV-211 (6"300#) | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | TRANSWATER | Execution | 110 | Perform De-isolation |  | 2 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 11:30 | 2026-07-30 14:30 | [6 empty] | 2026-07-25 09:53 | BPA.I1090
B48DBCA9-A8A1-49AC-F0AF-08DEE9C18370 | TA00139 | VB9 - 200-PG-06 3-31430 (8"300#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing for VB 9 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.P1080
4F628F35-7129-49C6-F0AE-08DEE9C18370 | TA00138 | VB8 - 200-PG-06 3-31430 (8"300#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing for VB 8 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.P1070
E81DFB57-935E-49AC-F0AD-08DEE9C18370 | TA00137 | VB7 - 200-PG-1001-61492 (10"600#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing for VB 7 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.P1060
205DE96D-DDFD-47A4-F0AC-08DEE9C18370 | TA00136 | VB6 - 150-PG-04 1-6101X (6"600#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing for VB 6 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-29 09:00 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.P1050
3E7A7E1D-50D5-4666-F0AB-08DEE9C18370 | TA00135 | VB5 - 200-PG-006-6101X (8"600#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing for VB 5 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-28 09:00 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.P1040
B1A1FD9A-DFA3-485C-F0AA-08DEE9C18370 | TA00134 | VB4 - 200-PG-006-6101X (8"600#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing for VB 4 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-27 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.P1030
8C12418E-7433-4CA9-F0A9-08DEE9C18370 | TA00133 | VB3 - 250-PG-053-1143 ((10"300#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing and fitting replacement for VB 3 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-27 09:00 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.P1020
CD016000-41D5-44C5-F0A8-08DEE9C18370 | TA00132 | VB2 - 250-PL0900 5-61430X (10"600#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing and fitting replacement for VB 2 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-26 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.P1010
28296412-0FAF-4F64-F0A7-08DEE9C18370 | TA00131 | VB1- 250-PL0900 5-61430X (10"600#) | Betty | BEP-A |  | Mechanical Valve | Piping | Maintenance | PPM | Prelim | ESSEM | Execution | 10 | Performing valve servicing and fitting replacement for VB 1 |  | 3 | 6 |  |  | APIOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.P1000
234A5C29-A50F-45DB-F09B-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 10 | (BEP-A) 250-PG-053-1143: PERFORM SURFACE PREP (VI-08) |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 14:00 | 2026-07-26 14:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2330
52B27CE5-1186-4157-F0A1-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 20 | (BEP-A) 250-PG-053-1143: MCI INSPECTION (VI-08) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 14:30 | 2026-07-26 14:45 | [6 empty] | 2026-07-25 09:53 | BPA.C2340
EF1AFD6A-D6CF-4705-F09C-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 30 | (BEP-A) 250-PG-053-1143: APPLY MRC (VI-08) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 14:45 | 2026-07-26 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2350
93B0FC0A-C8FE-4919-F0A6-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 40 | (BEP-A) 250-PG-053-1143: CURING (VI-08) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 15:00 | 2026-07-26 16:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2360
B0625F5C-5190-4AF3-F0A5-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 50 | (BEP-A) 250-PG-053-1143: APPLY WRAPPING (VI-08) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 16:00 | 2026-07-26 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2370
CA0F9352-8555-41EB-F0A2-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 60 | (BEP-A) 250-PG-053-1143: PERFORM SURFACE PREP (VI-09) |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 09:00 | 2026-07-27 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2450
C521FE8D-19BE-40E4-F09F-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 70 | (BEP-A) 250-PG-053-1143: MCI INSPECTION (VI-09) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 09:30 | 2026-07-27 09:45 | [6 empty] | 2026-07-25 09:53 | BPA.C2460
ED9F8145-6872-42A1-F09E-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 80 | (BEP-A) 250-PG-053-1143: APPLY MRC (VI-09) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 09:45 | 2026-07-27 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2470
1B0FF3D5-5647-4E62-F0A0-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 90 | (BEP-A) 250-PG-053-1143: CURING (VI-09) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 10:00 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2480
E83A4F26-4906-42DC-F0A4-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 100 | (BEP-A) 250-PG-053-1143: APPLY WRAPPING (VI-09) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-27 12:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2490
7174EBA7-1B3E-4E67-F09D-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 110 | (BEP-A) 250-PG-053-1143: PERFORM HARDNESS TEST (VI-09) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 09:00 | 2026-07-29 09:15 | [6 empty] | 2026-07-25 09:53 | BPA.C2500
4BBEFA89-7D65-4290-F0A3-08DEE9C18370 | TA00130 | 250-PG-053-1143 - WRAPPING (TASK 26) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 120 | (BEP-A) 250-PG-053-1143: PERFORM HARDNESS TEST (VI-08) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 09:15 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2505
25BB7897-822A-425D-F099-08DEE9C18370 | TA00129 | 50-PL-1130-1143 - WRAPPING (TASK 25) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 10 | Transfer material and site prep + scaffolding by Construction team |  | 3.5 | 7 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2389
D8AB0C5F-D3F9-4EA5-F096-08DEE9C18370 | TA00129 | 50-PL-1130-1143 - WRAPPING (TASK 25) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 20 | (BEP-A) 50-PL-1130-1143: PERFORM SURFACE PREP (VI-03) |  | 0.5 | 1 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2390
85B06B65-C426-4FB3-F097-08DEE9C18370 | TA00129 | 50-PL-1130-1143 - WRAPPING (TASK 25) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 30 | (BEP-A) 50-PL-1130-1143: MCI INSPECTION (VI-03) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 09:30 | 2026-07-26 09:45 | [6 empty] | 2026-07-25 09:53 | BPA.C2400
00619DD1-B9D0-4F54-F098-08DEE9C18370 | TA00129 | 50-PL-1130-1143 - WRAPPING (TASK 25) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 40 | (BEP-A) 50-PL-1130-1143: APPLY MRC (VI-03) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 09:45 | 2026-07-26 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2410
5FBC95EF-20F1-4C36-F094-08DEE9C18370 | TA00129 | 50-PL-1130-1143 - WRAPPING (TASK 25) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 50 | (BEP-A) 50-PL-1130-1143: CURING (VI-03) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 10:00 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2420
514F0828-3638-4C91-F095-08DEE9C18370 | TA00129 | 50-PL-1130-1143 - WRAPPING (TASK 25) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 60 | (BEP-A) 50-PL-1130-1143: APPLY WRAPPING (VI-03) |  | 1.5 | 3 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2430
E6F14214-9808-444C-F09A-08DEE9C18370 | TA00129 | 50-PL-1130-1143 - WRAPPING (TASK 25) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Gapura | Execution | 70 | (BEP-A) 50-PL-1130-1143: PERFORM HARDNESS TEST (VI-01) |  | 0.25 | 0.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-26 13:45 | [6 empty] | 2026-07-25 09:53 | BPA.C2440
6C3C4F3F-AA3D-490C-F090-08DEE9C18370 | TA00128 | V300 - PIPING REPLACEMENT (TASK 21) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEP-A) V-300: ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-29 16:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2270
A6983C87-991F-4F9D-F08F-08DEE9C18370 | TA00128 | V300 - PIPING REPLACEMENT (TASK 21) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEP-A) V-300: UNBOLT AND REMOVE CORRODED SPOOL (1 EA T-SPOOL) |  | 1.5 | 7.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 16:30 | 2026-07-30 11:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2280
AA410335-6339-4AE3-F092-08DEE9C18370 | TA00128 | V300 - PIPING REPLACEMENT (TASK 21) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEP-A) V-300: INSTALL AND BOLT UP NEW SPOOL (BFJI); V34 |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 11:30 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2290
906C349D-1E3D-4E4B-F08E-08DEE9C18370 | TA00128 | V300 - PIPING REPLACEMENT (TASK 21) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEP-A) V-300: PERFORM BOLT TORQUING (BFJI - 3 NOS) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-30 16:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2300
2ADD885F-6DA7-41C6-F091-08DEE9C18370 | TA00128 | V300 - PIPING REPLACEMENT (TASK 21) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEP-A) FROM S-610 TO LC-610: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 0.5 | 3 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 16:30 | 2026-07-30 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2310
77C51363-B325-4BF2-F093-08DEE9C18370 | TA00128 | V300 - PIPING REPLACEMENT (TASK 21) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BEP-A) V-300: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 17:00 | 2026-07-31 09:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2320
0F042259-8402-48F1-F08A-08DEE9C18370 | TA00127 | FROM S-610 TO LC-610 (S-610) - STUDBOLT & GASKET REPLACEMENT (TASK 20) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEP-A) FROM S-610 TO LC-610: ISOLATE LINEWORK |  | 0.8 | 4 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 09:18 | [6 empty] | 2026-07-25 09:53 | BPA.C2220
542DC339-9A4F-4395-F08B-08DEE9C18370 | TA00127 | FROM S-610 TO LC-610 (S-610) - STUDBOLT & GASKET REPLACEMENT (TASK 20) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEP-A) FROM S-610 TO LC-610: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ DN20 VALVE; V6 |  | 1.6 | 8 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 09:18 | 2026-07-29 11:24 | [6 empty] | 2026-07-25 09:53 | BPA.C2230
B131DDB5-49E8-4E6F-F08C-08DEE9C18370 | TA00127 | FROM S-610 TO LC-610 (S-610) - STUDBOLT & GASKET REPLACEMENT (TASK 20) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEP-A) FROM S-610 TO LC-610: PERFORM BOLT TORQUING (BFJI - 2 NOS) |  | 0.8 | 4 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 11:24 | 2026-07-29 13:12 | [6 empty] | 2026-07-25 09:53 | BPA.C2240
2CB6CD91-7695-41C8-F089-08DEE9C18370 | TA00127 | FROM S-610 TO LC-610 (S-610) - STUDBOLT & GASKET REPLACEMENT (TASK 20) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEP-A) FROM S-610 TO LC-610: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 13:12 | 2026-07-29 14:12 | [6 empty] | 2026-07-25 09:53 | BPA.C2250
893FAB62-4A97-4C83-F08D-08DEE9C18370 | TA00127 | FROM S-610 TO LC-610 (S-610) - STUDBOLT & GASKET REPLACEMENT (TASK 20) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEP-A) FROM S-610 TO LC-610: DE-ISOLATE LINEWORK |  | 0.8 | 4 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 14:12 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2260
F1AC1833-9C56-44B7-F087-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEP-A) 50-PG-065-31430: UNBOLT CORRODED SECTIONS, V1 & V4 - 1 SPOOL |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 14:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2520
A16B0AB7-C581-4A37-F084-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEP-A) 50-PG-065-31430: REMOVE CORRODED VALVE (2 NOS) |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 16:30 | 2026-07-29 12:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2530
61A1ABD7-6252-4E9D-F083-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEP-A) 50-PG-065-31430: REPLACE NEW VALVE (2 NOS), REPLACE GASKETS & BOLTINGS; V3 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 13:00 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2540
F123636B-168A-408E-F082-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEP-A) 50-PG-065-31430: INSTALL AND BOLT UP NEW SPOOL |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-30 14:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2550
86187633-0095-44A8-F085-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEP-A) 50-PG-065-31430: REPLACE GASKETS & BOLTINGS; V2 |  | 3 | 15 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 14:00 | 2026-07-30 17:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2560
A043697A-CF2D-47CD-F088-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BEP-A) 50-PG-065-31430: PERFORM BOLT TORQUING (BFJI - 3 NOS) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2570
B1431768-5C0C-454C-F081-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BEP-A) 50-PG-065-31430: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 10:00 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2580
0E66F2CD-F2D3-4BA7-F086-08DEE9C18370 | TA00126 | 50-PG-065-31430 - PIPING REPLACEMENT (TASK 19) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 80 | (BEP-A) 50-PG-065-31430: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 11:00 | 2026-07-31 12:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2590
6A64A13B-38AC-4BF9-F07B-08DEE9C18370 | TA00125 | [B] 100-PG-064-31430 - PIPING REPLACEMENT (TASK 18) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEP-A) 100-PG-064-31430: ISOLATE LINEWORK |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2000
6E2A1833-FB4A-41E5-F07A-08DEE9C18370 | TA00125 | [B] 100-PG-064-31430 - PIPING REPLACEMENT (TASK 18) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEP-A) 100-PG-064-31430: CUT AND REMOVE CORRODED PIPE; V7 |  | 7 | 42 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 17:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2010
68AFA336-8729-4C7A-F07C-08DEE9C18370 | TA00125 | [B] 100-PG-064-31430 - PIPING REPLACEMENT (TASK 18) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEP-A) 100-PG-064-31430: WELDING NEW PIPE SPOOL ( 1 JOINT HW) |  | 4 | 28 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 11:00 | 2026-07-28 16:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2030
809FF5EF-B6FC-45B6-F07D-08DEE9C18370 | TA00125 | [B] 100-PG-064-31430 - PIPING REPLACEMENT (TASK 18) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEP-A) 100-PG-064-31430: PERFORM RT |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 18:00 | 2026-07-28 19:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2060
8741FF78-63B4-4729-F080-08DEE9C18370 | TA00125 | [B] 100-PG-064-31430 - PIPING REPLACEMENT (TASK 18) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEP-A) 100-PG-064-31430: PERFORM BOLT TORQUING (BFJI - 1 NOS) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2070
A06D39C9-23C4-40DE-F07E-08DEE9C18370 | TA00125 | [B] 100-PG-064-31430 - PIPING REPLACEMENT (TASK 18) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BEP-A) 100-PG-064-31430: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 10:00 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2080
883AC335-5AA5-4F39-F07F-08DEE9C18370 | TA00125 | [B] 100-PG-064-31430 - PIPING REPLACEMENT (TASK 18) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BEP-A) 100-PG-064-31430: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 11:00 | 2026-07-31 12:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2090
635E3AB4-94ED-448B-F076-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEP-A) 250-PG-060-31430: ISOLATE LINEWORK |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2100
6F778CF8-485A-4848-F079-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEP-A) 250-PG-060-31430: PERFORM N2 PURGING |  | 3 | 15 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 12:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2105
E4CA56A2-190C-4B1E-F070-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEP-A) 250-PG-060-31430: CUT AND REMOVE CORRODED PIPE; V7, V9, V26 (3 joints) |  | 6 | 48 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 13:00 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2110
F0CB0402-632A-49CE-F06E-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEP-A) 250-PG-060-31430: WASHDOWN PRIOR TO HOTWORK |  | 1 | 4 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-27 12:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2120
08DDB221-E7C6-476F-F073-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEP-A) 250-PG-060-31430: WELDING NEW PIPE SPOOL (FFW: 2 JOINT) - 2 WELDER |  | 6 | 66 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2130
36865C93-6186-4BCB-F075-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BEP-A) 250-PG-060-31430: WELDING NEW PIPE SPOOL (FFW: 1 JOINT) - 1 WELDER |  | 6 | 36 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2140
BA65F515-14C9-4255-F078-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BEP-A) 250-PG-060-31430: PERFORM RT |  | 1 | 3 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 18:00 | 2026-07-28 19:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2150
0F827815-7555-4A59-F072-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 80 | (BEP-A) 250-PG-060-31430: ANALYZE RT RESULT |  | 5 | 15 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 | 2026-07-29 05:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2160
4F8B0C38-8360-413F-F077-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 90 | (BEP-A) 250-PG-060-31430: PERFORM HYDROTEST (3JTS HW) |  | 7 | 42 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 17:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2170
1B502216-A013-49FF-F071-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 100 | (BEP-A) 250-PG-060-31430: INSTALL AND BOLT UP 1 EA NEW SPOOL; V7, V9, V26 |  | 3 | 15 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 11:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2180
3B345DCD-8282-4B3E-F074-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 110 | (BEP-A) 250-PG-060-31430: PERFORM BOLT TORQUING (BFJI - 4 NOS) 1 Joints HTW |  | 3 | 15 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-31 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2190
6C6D8334-900A-4EB7-F06D-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 120 | (BEP-A) 250-PG-060-31430: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 09:30 | 2026-07-31 10:30 | [6 empty] | 2026-07-25 09:53 | BPA.C2200
A6237608-AD9F-4547-F06F-08DEE9C18370 | TA00124 | [HW] 250-PG-060-31430 - PIPING REPLACEMENT (TASK 17) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 130 | (BEP-A) 250-PG-060-31430: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 1.5 | 7.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 12:00 | [6 empty] | 2026-07-25 09:53 | BPA.C2210
11EF3303-19E6-456E-F069-08DEE9C18370 | TA00123 | 150-V-011-1101X - CWR VALVE REPLACEMENT (TASK 16) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BEP-A) 150-V-011-1101X: ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.C1000
E1107999-726C-4FDF-F06A-08DEE9C18370 | TA00123 | 150-V-011-1101X - CWR VALVE REPLACEMENT (TASK 16) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BEP-A) 150-V-011-1101X: REMOVE CORRODED VALVE; REPLACE NEW VALVES (1 NOS); V8 |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 10:00 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.C1010
E4DAF364-3C00-4D5B-F06B-08DEE9C18370 | TA00123 | 150-V-011-1101X - CWR VALVE REPLACEMENT (TASK 16) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BEP-A) 150-V-011-1101X: PERFORM BOLT TORQUING (BFJI - 2 NOS) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 14:00 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.C1020
C462D4A2-03CF-454E-F06C-08DEE9C18370 | TA00123 | 150-V-011-1101X - CWR VALVE REPLACEMENT (TASK 16) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BEP-A) 150-V-011-1101X: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-29 16:30 | [6 empty] | 2026-07-25 09:53 | BPA.C1030
C1588B36-6A4A-4816-F068-08DEE9C18370 | TA00123 | 150-V-011-1101X - CWR VALVE REPLACEMENT (TASK 16) | Betty | BEP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BEP-A) 150-V-011-1101X: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 16:30 | 2026-07-29 17:30 | [6 empty] | 2026-07-25 09:53 | BPA.C1040
350F0414-F7D8-4DF0-F067-08DEE9C18370 | TA00122 | RV 0102A (4"x6") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 11:15 | 2026-07-30 11:45 | [6 empty] | 2026-07-25 09:53 | BPA.S1000
C3734380-A352-4C9F-F062-08DEE9C18370 | TA00122 | RV 0102A (4"x6") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 1 | 6 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 11:45 | 2026-07-30 13:45 | [6 empty] | 2026-07-25 09:53 | BPA.S1010
C855F4A5-DEDC-4AB9-F064-08DEE9C18370 | TA00122 | RV 0102A (4"x6") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 1 | 6 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 14:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1020
DD39E3E5-D852-4198-F066-08DEE9C18370 | TA00122 | RV 0102A (4"x6") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 1 | 6 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 16:30 | 2026-07-31 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.S1030
F7DC3213-EB69-445A-F063-08DEE9C18370 | TA00122 | RV 0102A (4"x6") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 09:30 | 2026-07-31 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1040
186F620B-EB6F-4D2F-F065-08DEE9C18370 | TA00122 | RV 0102A (4"x6") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1050
E2200473-A2A5-4BC0-F061-08DEE9C18370 | TA00121 | PSV1604 (3/8" MNPT) | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 10:45 | 2026-07-30 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1260
FB7C3C99-EB71-41D6-F05D-08DEE9C18370 | TA00121 | PSV1604 (3/8" MNPT) | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 11:00 | 2026-07-30 11:15 | [6 empty] | 2026-07-25 09:53 | BPA.S1270
34A0A850-6D16-4D07-F05E-08DEE9C18370 | TA00121 | PSV1604 (3/8" MNPT) | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-30 15:45 | [6 empty] | 2026-07-25 09:53 | BPA.S1280
ECE1B748-0F32-40D4-F05F-08DEE9C18370 | TA00121 | PSV1604 (3/8" MNPT) | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 16:00 | 2026-07-30 16:15 | [6 empty] | 2026-07-25 09:53 | BPA.S1290
D4034DA3-2CE0-42FB-F060-08DEE9C18370 | TA00121 | PSV1604 (3/8" MNPT) | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 16:15 | 2026-07-30 16:30 | [6 empty] | 2026-07-25 09:53 | BPA.S1310
6F8068D8-4294-49CF-F057-08DEE9C18370 | TA00120 | RV0301 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-29 11:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1200
CA886781-4AD7-4257-F05C-08DEE9C18370 | TA00120 | RV0301 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 1 | 6 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 11:00 | 2026-07-29 12:00 | [6 empty] | 2026-07-25 09:53 | BDA.S1210
171EE4C4-653C-4826-F059-08DEE9C18370 | TA00120 | RV0301 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.67 | 4 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 13:00 | 2026-07-29 13:40 | [6 empty] | 2026-07-25 09:53 | BDA.S1220
998A4538-966A-4CD2-F05A-08DEE9C18370 | TA00120 | RV0301 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 14:50 | 2026-07-29 15:50 | [6 empty] | 2026-07-25 09:53 | BDA.S1230
6DD16A33-4A3F-45E1-F058-08DEE9C18370 | TA00120 | RV0301 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 15:50 | 2026-07-29 16:20 | [6 empty] | 2026-07-25 09:53 | BDA.S1240
D86D845C-7E95-451C-F05B-08DEE9C18370 | TA00120 | RV0301 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 16:20 | 2026-07-29 16:50 | [6 empty] | 2026-07-25 09:53 | BPA.S1051
3752D2C6-E000-4725-F055-08DEE9C18370 | TA00119 | RV 620 (2"x3") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 09:00 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.S1060
839E4A12-AFD5-4208-F054-08DEE9C18370 | TA00119 | RV 620 (2"x3") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 09:30 | 2026-07-29 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1070
FA3F5E22-4CC3-49C3-F053-08DEE9C18370 | TA00119 | RV 620 (2"x3") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.67 | 4 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 13:40 | 2026-07-29 14:20 | [6 empty] | 2026-07-25 09:53 | BPA.S1080
490F866F-EC59-4666-F052-08DEE9C18370 | TA00119 | RV 620 (2"x3") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 14:20 | 2026-07-29 14:50 | [6 empty] | 2026-07-25 09:53 | BPA.S1090
683D1845-A959-4196-F051-08DEE9C18370 | TA00119 | RV 620 (2"x3") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.S1100
1565D8B8-E085-47BD-F056-08DEE9C18370 | TA00119 | RV 620 (2"x3") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 09:30 | 2026-07-30 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1110
40DF4D78-ADFB-478A-F04B-08DEE9C18370 | TA00118 | RV500 (1"x2") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 11:15 | [6 empty] | 2026-07-25 09:53 | BPA.S1120
09394EED-65DD-434E-F04C-08DEE9C18370 | TA00118 | RV500 (1"x2") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:15 | 2026-07-26 11:45 | [6 empty] | 2026-07-25 09:53 | BPA.S1130
54F82368-0AF9-4917-F050-08DEE9C18370 | TA00118 | RV500 (1"x2") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 13:25 | 2026-07-26 13:55 | [6 empty] | 2026-07-25 09:53 | BPA.S1140
683A68FD-F013-48D4-F04E-08DEE9C18370 | TA00118 | RV500 (1"x2") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 14:25 | 2026-07-26 14:55 | [6 empty] | 2026-07-25 09:53 | BPA.S1150
1A868E9F-0273-4182-F04D-08DEE9C18370 | TA00118 | RV500 (1"x2") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 16:25 | 2026-07-26 16:40 | [6 empty] | 2026-07-25 09:53 | BPA.S1160
FE10A674-29B4-4E8C-F04F-08DEE9C18370 | TA00118 | RV500 (1"x2") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 16:40 | 2026-07-26 16:55 | [6 empty] | 2026-07-25 09:53 | BPA.S1165
F807893D-B09C-4D0E-F046-08DEE9C18370 | TA00117 | RV0502 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 09:30 | 2026-07-26 10:00 | [6 empty] | 2026-07-25 09:53 | BPA.S11206
099D4CCC-6074-4200-F04A-08DEE9C18370 | TA00117 | RV0502 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 10:30 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1210
AEDFBB6A-3B5C-4705-F047-08DEE9C18370 | TA00117 | RV0502 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.67 | 4 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:45 | 2026-07-26 13:25 | [6 empty] | 2026-07-25 09:53 | BPA.S1220
B0549F64-C3E9-43E5-F045-08DEE9C18370 | TA00117 | RV0502 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 13:55 | 2026-07-26 14:25 | [6 empty] | 2026-07-25 09:53 | BPA.S1230
5D07353A-77AC-4E04-F049-08DEE9C18370 | TA00117 | RV0502 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 14:55 | 2026-07-26 15:55 | [6 empty] | 2026-07-25 09:53 | BPA.S1240
15AF19CD-E505-437B-F048-08DEE9C18370 | TA00117 | RV0502 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 15:55 | 2026-07-26 16:25 | [6 empty] | 2026-07-25 09:53 | BPA.S1250
C29799BC-BCCC-4E3E-F041-08DEE9C18370 | TA00116 | RV0501 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 13:30 | [6 empty] | 2026-07-25 09:53 | BPA.S1166
357501F1-1294-46B4-F042-08DEE9C18370 | TA00116 | RV0501 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:30 | 2026-07-25 14:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1170
D343F6DB-1571-4306-F044-08DEE9C18370 | TA00116 | RV0501 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 1 | 6 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1180
30250E44-2BD1-49B3-F043-08DEE9C18370 | TA00116 | RV0501 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 16:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1190
835D11F8-FE2F-464A-F03F-08DEE9C18370 | TA00116 | RV0501 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform JIT Verification by PCSB QAQC |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 16:00 | 2026-07-25 16:30 | [6 empty] | 2026-07-25 09:53 | BPA.S1200
37915209-1196-4634-F040-08DEE9C18370 | TA00116 | RV0501 (3"x4") | Betty | BEP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 60 | Perform De-isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 16:30 | 2026-07-25 17:00 | [6 empty] | 2026-07-25 09:53 | BPA.S1205
80275B31-3ECD-4083-F03E-08DEE9C18370 | TA00115 | BODF-060SDV-002 | Bokor | BODP-F |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODPE-060SDV-002 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 16:00 | 2026-07-26 16:30 | [6 empty] | 2026-07-25 09:53 | DPE.RE1030
E9BFB5DF-30C3-4681-F03D-08DEE9C18370 | TA00114 | BODF-290SDV-061 | Bokor | BODP-F |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODPE-290SDV-061 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 15:30 | 2026-07-26 16:00 | [6 empty] | 2026-07-25 09:53 | DPE.RE1020
140E9B3D-D7FD-48CF-F03C-08DEE9C18370 | TA00113 | BODF-135SDV-050 | Bokor | BODP-F |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODF-135SDV050 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 14:30 | 2026-07-26 15:00 | [6 empty] | 2026-07-25 09:53 | DPF.RE1000
1AFE9A22-A4D1-4338-F038-08DEE9C18370 | TA00112 | Yokogawa SIS/FGS | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 10 | Perform SCS Health Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 10:30 | [6 empty] | 2026-07-25 09:53 | DPF.I1100
B2E3FD2B-5100-49F4-F03A-08DEE9C18370 | TA00112 | Yokogawa SIS/FGS | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 10:30 | 2026-08-04 13:30 | [6 empty] | 2026-07-25 09:53 | DPF.I1110
4104C6A1-9BEE-4257-F03B-08DEE9C18370 | TA00112 | Yokogawa SIS/FGS | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 30 | Cabinet Temperature & Humidity Measurement |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 13:30 | 2026-08-04 16:00 | [6 empty] | 2026-07-25 09:53 | DPF.I1120
A37ECD84-5749-4531-F039-08DEE9C18370 | TA00112 | Yokogawa SIS/FGS | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 40 | General cleaning |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 16:00 | 2026-08-04 18:00 | [6 empty] | 2026-07-25 09:53 | DPF.I1130
E81874CC-FE2D-4833-F037-08DEE9C18370 | TA00111 | Yokogawa DCS | Bokor | BODP-F |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 10 | Perform FCS Health Check and General Cleaning at BODP-F |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 08:30 | 2026-08-04 11:00 | [6 empty] | 2026-07-25 09:53 | DPF.I1000
33DFF2B4-0D02-4C8C-F036-08DEE9C18370 | TA00110 | BODPE-135SDV-050 | Bokor | BODP-E |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODPE-135SDV-050 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 13:00 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | DPE.RE1010
E031B118-565B-43C4-F035-08DEE9C18370 | TA00109 | BODPE-290SDV-061 | Bokor | BODP-E |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODPE-290SDV-061 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 12:00 | [6 empty] | 2026-07-25 09:53 | DPE.RE1000
E75B6B8A-B294-4189-F032-08DEE9C18370 | TA00108 | Yokogawa SIS/FGS | Bokor | BODP-E |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 10 | Perform SCS Health Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 08:00 | 2026-08-03 10:30 | [6 empty] | 2026-07-25 09:53 | DPE.I1100
C068E1F0-629A-4474-F034-08DEE9C18370 | TA00108 | Yokogawa SIS/FGS | Bokor | BODP-E |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 10:30 | 2026-08-03 13:30 | [6 empty] | 2026-07-25 09:53 | DPE.I1110
742ECE55-5630-48FD-F031-08DEE9C18370 | TA00108 | Yokogawa SIS/FGS | Bokor | BODP-E |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 30 | Cabinet Temperature & Humidity Measurement |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 13:30 | 2026-08-03 16:00 | [6 empty] | 2026-07-25 09:53 | DPE.I1120
242A5FB0-AEF9-4783-F033-08DEE9C18370 | TA00108 | Yokogawa SIS/FGS | Bokor | BODP-E |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 40 | General cleaning |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 16:00 | 2026-08-03 18:00 | [6 empty] | 2026-07-25 09:53 | DPE.I1130
386C1DA5-AA10-4AD8-F030-08DEE9C18370 | TA00107 | Yokogawa DCS | Bokor | BODP-E |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 10 | Perform FCS Health Check and General Cleaning at BODP-E |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 08:30 | 2026-08-03 11:00 | [6 empty] | 2026-07-25 09:53 | DPE.I1000
5B02BA8D-406B-40AF-F02F-08DEE9C18370 | TA00106 | BODD-070SDV-001 | Bokor | BODP-D |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODD-070SDV-001 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 10:00 | 2026-07-26 10:30 | [6 empty] | 2026-07-25 09:53 | DPD.RE1010
AED154BA-5142-4DED-F02B-08DEE9C18370 | TA00105 | Yokogawa SIS/FGS | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 10 | Perform SCS Health Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 10:30 | [6 empty] | 2026-07-25 09:53 | DPD.I1100
9441D87C-B8EB-4AE5-F02C-08DEE9C18370 | TA00105 | Yokogawa SIS/FGS | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 10:30 | 2026-08-02 13:30 | [6 empty] | 2026-07-25 09:53 | DPD.I1110
41C274C2-4802-423A-F02D-08DEE9C18370 | TA00105 | Yokogawa SIS/FGS | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 30 | Cabinet Temperature & Humidity Measurement |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 13:30 | 2026-08-02 16:00 | [6 empty] | 2026-07-25 09:53 | DPD.I1120
23162842-28F9-47C8-F02E-08DEE9C18370 | TA00105 | Yokogawa SIS/FGS | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 40 | General cleaning |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 16:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | DPD.I1130
61CC1009-018F-47F0-F02A-08DEE9C18370 | TA00104 | Yokogawa DCS | Bokor | BODP-D |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 10 | Perform FCS Health Check and General Cleaning at BODP-D |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 08:30 | 2026-08-02 11:00 | [6 empty] | 2026-07-25 09:53 | DPD.I1000
4CA18EC4-F276-4090-F029-08DEE9C18370 | TA00103 | BODC-ABV0101 | Bokor | BODP-C |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODC-ABV0101 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-26 08:30 | [6 empty] | 2026-07-25 09:53 | DPC.RE1000
E302C2E5-BD47-4F4A-F025-08DEE9C18370 | TA00102 | Fire & Gas Panel (Fire and Gas System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | To perform Offline Download prior PM job |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 11:30 | 2026-08-03 13:30 | [6 empty] | 2026-07-25 09:53 | DPC.I1235
2F3604C6-599A-4372-F027-08DEE9C18370 | TA00102 | Fire & Gas Panel (Fire and Gas System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Site inspection and system verification for BODP-C FGS LERC |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 13:30 | 2026-08-03 16:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1240
7178B763-E3AF-437C-F028-08DEE9C18370 | TA00102 | Fire & Gas Panel (Fire and Gas System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Check system error for BODP-C FGS LERC |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 16:00 | 2026-08-04 09:30 | [6 empty] | 2026-07-25 09:53 | DPC.I1250
23E11FDD-81EF-4079-F024-08DEE9C18370 | TA00102 | Fire & Gas Panel (Fire and Gas System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Backup program for BODP-C FGS LERC |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 10:00 | 2026-08-04 12:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1260
F23DB39F-BCA3-4679-F026-08DEE9C18370 | TA00102 | Fire & Gas Panel (Fire and Gas System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 50 | Perform fault rectification for BODP-C FGS LERC |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 13:00 | 2026-08-04 15:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1270
D16F9D2F-3233-4BA6-F022-08DEE9C18370 | TA00101 | ESP-WSS-4510 (ESP Well Shutdown System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | To perform Offline Download prior PM job |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 08:30 | 2026-08-02 09:30 | [6 empty] | 2026-07-25 09:53 | DPC.I1195
0DC882C1-F12C-4694-F01F-08DEE9C18370 | TA00101 | ESP-WSS-4510 (ESP Well Shutdown System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Site inspection and system verification for BODP-C WSS ESP |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 10:00 | 2026-08-02 12:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1200
100B8DAE-70E2-4F9A-F023-08DEE9C18370 | TA00101 | ESP-WSS-4510 (ESP Well Shutdown System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Check system error for BODP-C WSS ESP |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 13:00 | 2026-08-02 15:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1210
46631755-C3C2-4806-F021-08DEE9C18370 | TA00101 | ESP-WSS-4510 (ESP Well Shutdown System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Backup program for BODP-C WSS ESP |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 15:30 | 2026-08-03 09:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1220
4D140F7A-8146-486A-F020-08DEE9C18370 | TA00101 | ESP-WSS-4510 (ESP Well Shutdown System) | Bokor | BODP-C |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 50 | Perform fault rectification for for BODP-C WSS ESP |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-03 09:00 | 2026-08-03 11:30 | [6 empty] | 2026-07-25 09:53 | DPC.I1230
33DD59B7-FEAC-4C19-F01C-08DEE9C18370 | TA00100 | Yokogawa SIS/FGS | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 10 | Perform SCS Health Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 08:00 | 2026-08-01 10:30 | [6 empty] | 2026-07-25 09:53 | DPC.I1100
457D2B7F-1F36-47AB-F01B-08DEE9C18370 | TA00100 | Yokogawa SIS/FGS | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 10:30 | 2026-08-01 13:30 | [6 empty] | 2026-07-25 09:53 | DPC.I1110
AEF5E883-4B75-4BBE-F01D-08DEE9C18370 | TA00100 | Yokogawa SIS/FGS | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 30 | Cabinet Temperature & Humidity Measurement |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 13:30 | 2026-08-01 16:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1120
C61F928C-36D5-4EB1-F01E-08DEE9C18370 | TA00100 | Yokogawa SIS/FGS | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 40 | General cleaning |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 16:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1130
5F01F4A1-DA65-4E1E-F019-08DEE9C18370 | TA00099 | Yokogawa DCS | Bokor | BODP-C |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 10 | Perform FCS Health Check and General Cleaning at BODP-C |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1000
D9441760-6684-455D-F01A-08DEE9C18370 | TA00099 | Yokogawa DCS | Bokor | BODP-C |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 20 | Perform HIS Health Check and General Cleaning and updating of Windows O/S Patch and Antivirus and Scan for Viruses |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 11:00 | 2026-08-01 14:00 | [6 empty] | 2026-07-25 09:53 | DPC.I1010
D82A4603-AB01-40AD-F018-08DEE9C18370 | TA00098 | BAT-001 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Transfer and set-up of load bank |  | 6.5 | 13 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 08:30 | 2026-08-02 17:00 | [6 empty] | 2026-07-25 09:53 | DPC.E1000
72D9BFF4-32EA-479C-F017-08DEE9C18370 | TA00098 | BAT-001 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Perform electrical isolation |  | 0.5 | 1 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 08:30 | 2026-08-03 09:00 | [6 empty] | 2026-07-25 09:53 | DPC.E1005
F837DE08-9580-4136-F015-08DEE9C18370 | TA00098 | BAT-001 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 30 | Preparation for battery discharge test & perform cleaning on battery bank Tag No. BAT-001. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 09:00 | 2026-08-03 11:30 | [6 empty] | 2026-07-25 09:53 | DPC.E1010
0691C3A3-02EA-49CD-F016-08DEE9C18370 | TA00098 | BAT-001 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 40 | Perform battery discharge test on battery bank Tag no. BAT-001. |  | 5 | 10 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 11:30 | 2026-08-03 16:30 | [6 empty] | 2026-07-25 09:53 | DPC.E1020
133B1029-80E2-467B-F014-08DEE9C18370 | TA00098 | BAT-001 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 50 | Normalise electrical isolation |  | 0.5 | 1 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 16:30 | 2026-08-03 17:00 | [6 empty] | 2026-07-25 09:53 | DPC.E1030
37414358-56BD-4A09-F00F-08DEE9C18370 | TA00097 | 150-PG-1001-61432X - CWR VALVE REPLACEMENT (TASK 15) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-C) 150-PG-1001-61432X: ISOLATE LINEWORK |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 13:30 | 2026-08-04 16:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1080
F0C13669-828A-4C9A-F010-08DEE9C18370 | TA00097 | 150-PG-1001-61432X - CWR VALVE REPLACEMENT (TASK 15) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-C) 150-PG-1001-61432X: REMOVE JAMMED 6" 600# VALVE; REPLACE NEW VALVE (1 NOS) |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 08:30 | 2026-08-05 14:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1090
11130F8F-C094-4B43-F013-08DEE9C18370 | TA00097 | 150-PG-1001-61432X - CWR VALVE REPLACEMENT (TASK 15) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-C) 150-PG-1001-61432X: PERFORM BOLT TORQUING (BFJI - 2 NOS) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 14:00 | 2026-08-05 15:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1100
4DD86530-F3DC-4C52-F012-08DEE9C18370 | TA00097 | 150-PG-1001-61432X - CWR VALVE REPLACEMENT (TASK 15) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-C) 150-PG-1001-61432X: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 15:30 | 2026-08-05 16:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1110
8D43DA71-F2CB-4C7A-F011-08DEE9C18370 | TA00097 | 150-PG-1001-61432X - CWR VALVE REPLACEMENT (TASK 15) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-C) 150-PG-1001-61432X: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 16:30 | 2026-08-06 14:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1120
C4B7A6BF-96BE-4087-F009-08DEE9C18370 | TA00096 | 100-P-035-93411 (C311-LS) - PIPING REPLACEMENT (TASK 14) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-C) 100-P-035-93411 (C311LS): ISOLATE LINEWORK |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 08:30 | 2026-08-03 11:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1130
1F2C1AE6-0A90-451F-F00C-08DEE9C18370 | TA00096 | 100-P-035-93411 (C311-LS) - PIPING REPLACEMENT (TASK 14) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-C) 100-P-035-93411 (C311LS): REMOVE SPOOL (1 NOS, 8 FLANGES) |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 11:00 | 2026-08-03 16:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1140
F8D7D20E-CB67-4147-F00E-08DEE9C18370 | TA00096 | 100-P-035-93411 (C311-LS) - PIPING REPLACEMENT (TASK 14) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-C) 100-P-035-93411 (C311LS): INSTALL SPOOL (1 NOS, 8 FLANGES) |  | 8 | 40 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 16:30 | 2026-08-05 09:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1150
003F8CAC-67CA-4EF6-F00B-08DEE9C18370 | TA00096 | 100-P-035-93411 (C311-LS) - PIPING REPLACEMENT (TASK 14) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-C) 100-P-035-93411 (C311LS): PERFORM BOLT TORQUING (BFJI - 8 NOS) - 1 joints HTW |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 10:00 | 2026-08-05 15:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1180
BE249A77-BE12-4EBB-F00A-08DEE9C18370 | TA00096 | 100-P-035-93411 (C311-LS) - PIPING REPLACEMENT (TASK 14) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-C) 100-P-001-93411 (BO301): PERFORM JIT VERIFICATION BY PCSB QAQC |  | 3 | 18 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 15:30 | 2026-08-06 14:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1181
E37ECA67-162A-4D78-F00D-08DEE9C18370 | TA00096 | 100-P-035-93411 (C311-LS) - PIPING REPLACEMENT (TASK 14) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-C) 100-P-001-93411 (BO301): DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-06 14:00 | 2026-08-06 16:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1190
1A1BE1F3-2E20-4A6A-F003-08DEE9C18370 | TA00095 | 100-P-001-93411(BO301) - PIPING REPLACEMENT (TASK 13) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-C) 100-P-001-93411 (BO301): ISOLATE LINEWORK |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1000
BD4EA508-CF9E-4E10-F008-08DEE9C18370 | TA00095 | 100-P-001-93411(BO301) - PIPING REPLACEMENT (TASK 13) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-C) 100-P-001-93411 (BO301): REMOVE SPOOL (1 NOS, 8 FLANGES) |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 11:00 | 2026-08-01 16:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1010
D7B4F7FF-01E8-471D-F006-08DEE9C18370 | TA00095 | 100-P-001-93411(BO301) - PIPING REPLACEMENT (TASK 13) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-C) 100-P-001-93411 (BO301): INSTALL SPOOL (1 NOS, 8 FLANGES) |  | 8 | 40 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 16:30 | 2026-08-03 09:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1020
A5E84814-2A1F-42B1-F007-08DEE9C18370 | TA00095 | 100-P-001-93411(BO301) - PIPING REPLACEMENT (TASK 13) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-C) 100-P-001-93411 (BO301): PERFORM BOLT TORQUING (BFJI - 8 NOS) - 2 joints HTW |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 10:00 | 2026-08-03 15:00 | [6 empty] | 2026-07-25 09:53 | DPC.C1050
4867776A-7098-486D-F004-08DEE9C18370 | TA00095 | 100-P-001-93411(BO301) - PIPING REPLACEMENT (TASK 13) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-C) 100-P-001-93411 (BO301): PERFORM JIT VERIFICATION BY PCSB QAQC |  | 3 | 18 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 15:30 | 2026-08-04 10:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1060
69A8410E-AD30-4D7C-F005-08DEE9C18370 | TA00095 | 100-P-001-93411(BO301) - PIPING REPLACEMENT (TASK 13) | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-C) 100-P-001-93411 (BO301): DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 10:30 | 2026-08-04 13:30 | [6 empty] | 2026-07-25 09:53 | DPC.C1070
0315889E-BB53-4DED-F001-08DEE9C18370 | TA00094 | PSV QQQ-2A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 15:30 | 2026-08-03 16:00 | [6 empty] | 2026-07-25 09:53 | DPC.S1300
FC1AE9C5-6B87-49F8-F002-08DEE9C18370 | TA00094 | PSV QQQ-2A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 16:00 | 2026-08-03 16:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1310
B7B3577C-642E-4C77-F000-08DEE9C18370 | TA00094 | PSV QQQ-2A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 13:30 | 2026-08-04 13:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1320
7470D73E-3095-4755-EFFF-08DEE9C18370 | TA00094 | PSV QQQ-2A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 13:00 | 2026-08-05 13:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1330
BE15DC4C-DF22-452B-EFFE-08DEE9C18370 | TA00094 | PSV QQQ-2A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 13:15 | 2026-08-05 13:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1340
255742D9-3E8A-4D2D-EFFD-08DEE9C18370 | TA00093 | PSV QQQ-1A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 14:15 | 2026-08-03 14:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1250
A0C24CEB-869A-4584-EFFB-08DEE9C18370 | TA00093 | PSV QQQ-1A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 14:45 | 2026-08-03 15:00 | [6 empty] | 2026-07-25 09:53 | DPC.S1260
4A843A46-FB1B-4076-EFF9-08DEE9C18370 | TA00093 | PSV QQQ-1A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 13:15 | 2026-08-04 13:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1270
D070FE16-6C93-4D39-EFFA-08DEE9C18370 | TA00093 | PSV QQQ-1A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 11:15 | 2026-08-05 11:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1280
51220E31-4923-473F-EFFC-08DEE9C18370 | TA00093 | PSV QQQ-1A (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 11:45 | 2026-08-05 12:00 | [6 empty] | 2026-07-25 09:53 | DPC.S1290
2C13AE72-5E05-4B76-EFF6-08DEE9C18370 | TA00092 | PSV TTT-1A (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 13:30 | 2026-08-03 14:00 | [6 empty] | 2026-07-25 09:53 | DPC.S1200
1AD2A4F5-1AD3-47A6-EFF8-08DEE9C18370 | TA00092 | PSV TTT-1A (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 14:00 | 2026-08-03 14:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1210
2EB4573F-9CB7-4813-EFF4-08DEE9C18370 | TA00092 | PSV TTT-1A (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 13:00 | 2026-08-04 13:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1220
FC545100-A369-405D-EFF5-08DEE9C18370 | TA00092 | PSV TTT-1A (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 10:30 | 2026-08-05 10:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1230
EB6F4689-2628-4D0D-EFF7-08DEE9C18370 | TA00092 | PSV TTT-1A (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 11:00 | 2026-08-05 11:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1240
7832574B-0F24-4413-EFF2-08DEE9C18370 | TA00091 | PSV JJ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 11:45 | 2026-08-03 13:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1150
25D2A4D5-E5A3-47CF-EFF0-08DEE9C18370 | TA00091 | PSV JJ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 13:15 | 2026-08-03 13:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1160
ED730625-C3FD-4AE9-EFEF-08DEE9C18370 | TA00091 | PSV JJ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 11:45 | 2026-08-04 12:00 | [6 empty] | 2026-07-25 09:53 | DPC.S1170
643A1578-058F-46D4-EFF1-08DEE9C18370 | TA00091 | PSV JJ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 09:15 | 2026-08-05 09:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1180
0D6119A5-B316-4FEC-EFF3-08DEE9C18370 | TA00091 | PSV JJ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 10:15 | 2026-08-05 10:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1190
CDA5D6EC-6EE1-4709-EFEE-08DEE9C18370 | TA00090 | PSV QQQ-2 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 11:00 | 2026-08-03 11:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1100
074D6942-0003-430E-EFED-08DEE9C18370 | TA00090 | PSV QQQ-2 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 11:30 | 2026-08-03 11:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1110
D6FEBDAF-09B2-49E6-EFEC-08DEE9C18370 | TA00090 | PSV QQQ-2 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 11:30 | 2026-08-04 11:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1120
2386D20C-4A8A-43CD-EFEB-08DEE9C18370 | TA00090 | PSV QQQ-2 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 08:30 | 2026-08-05 08:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1130
D3DFB0A8-8191-485A-EFEA-08DEE9C18370 | TA00090 | PSV QQQ-2 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 09:00 | 2026-08-05 09:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1140
2ADA87A2-6517-4FE1-EFE6-08DEE9C18370 | TA00089 | PSV QQQ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 10:15 | 2026-08-03 10:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1050
BEE9E334-F4B4-415D-EFE8-08DEE9C18370 | TA00089 | PSV QQQ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 10:45 | 2026-08-03 11:00 | [6 empty] | 2026-07-25 09:53 | DPC.S1060
128ADC02-34C5-4407-EFE7-08DEE9C18370 | TA00089 | PSV QQQ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 11:15 | 2026-08-04 11:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1070
CB2EE8AB-E98B-4856-EFE9-08DEE9C18370 | TA00089 | PSV QQQ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 16:30 | 2026-08-04 16:45 | [6 empty] | 2026-07-25 09:53 | DPC.S1080
5AA3760E-7F99-4F10-EFE5-08DEE9C18370 | TA00089 | PSV QQQ-1 (1/4" OD) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 16:45 | 2026-08-04 17:00 | [6 empty] | 2026-07-25 09:53 | DPC.S1090
5311E880-102B-4D35-EFE4-08DEE9C18370 | TA00088 | PSV TTT-1 (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 09:00 | 2026-08-03 09:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1000
12ECA9B2-4371-456F-EFE2-08DEE9C18370 | TA00088 | PSV TTT-1 (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 10:00 | 2026-08-03 10:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1010
08FB7CDC-282D-4D08-EFE0-08DEE9C18370 | TA00088 | PSV TTT-1 (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 11:00 | 2026-08-04 11:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1020
F2AC6910-4047-47D2-EFE3-08DEE9C18370 | TA00088 | PSV TTT-1 (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 16:00 | 2026-08-04 16:15 | [6 empty] | 2026-07-25 09:53 | DPC.S1030
7F2CD68C-513F-4BE4-EFE1-08DEE9C18370 | TA00088 | PSV TTT-1 (1/4" FNPT) | Bokor | BODP-C |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 16:15 | 2026-08-04 16:30 | [6 empty] | 2026-07-25 09:53 | DPC.S1040
2D991111-5C55-434A-EFDF-08DEE9C18370 | TA00087 | BODB-ABV912 | Bokor | BODP-B |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODB-ABV912 |  | 1 | 2 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 17:00 | 2026-07-25 18:00 | [6 empty] | 2026-07-25 09:53 | DPB.RE1020
496C1427-D7B7-43F5-EFDE-08DEE9C18370 | TA00086 | BODB-ABV932 | Bokor | BODP-B |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODB-ABV932 |  | 1 | 2 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 16:00 | 2026-07-25 17:00 | [6 empty] | 2026-07-25 09:53 | DPB.RE1010
96A72504-E7A4-4F48-EFDD-08DEE9C18370 | TA00085 | BODB-ABV942 | Bokor | BODP-B |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODB-ABV942 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 16:00 | [6 empty] | 2026-07-25 09:53 | DPB.RE1000
37D04792-E24F-42C4-EFD8-08DEE9C18370 | TA00084 | LCP-0450 (Desander) | Bokor | BODP-B |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | To perform Offline Download prior PM job |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-05 08:30 | 2026-08-05 09:30 | [6 empty] | 2026-07-25 09:53 | DPB.I1195
B426405F-2003-4EE1-EFDB-08DEE9C18370 | TA00084 | LCP-0450 (Desander) | Bokor | BODP-B |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Site inspection and system verification for BODP-B Desander |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-05 10:00 | 2026-08-05 12:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1200
C32A67A0-4B95-4EEC-EFDA-08DEE9C18370 | TA00084 | LCP-0450 (Desander) | Bokor | BODP-B |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Check system error for BODP-B Desander |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-05 13:00 | 2026-08-05 15:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1210
204C741C-7FC4-4871-EFDC-08DEE9C18370 | TA00084 | LCP-0450 (Desander) | Bokor | BODP-B |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Backup program for BODP-B Desander |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-05 15:30 | 2026-08-06 12:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1220
A1D4EFDA-84DE-4BA6-EFD9-08DEE9C18370 | TA00084 | LCP-0450 (Desander) | Bokor | BODP-B |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 50 | Perform fault rectification for BODP-B Desander |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-06 13:00 | 2026-08-06 15:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1230
3D9BF157-8045-47D6-EFD5-08DEE9C18370 | TA00083 | Yokogawa SIS/FGS | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 10 | Perform SCS Health Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-07-31 10:30 | [6 empty] | 2026-07-25 09:53 | DPB.I1100
777C9005-827E-4DF3-EFD7-08DEE9C18370 | TA00083 | Yokogawa SIS/FGS | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | DPB.I1110
6D3613D5-0408-4907-EFD6-08DEE9C18370 | TA00083 | Yokogawa SIS/FGS | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 30 | Cabinet Temperature & Humidity Measurement |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 16:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1120
3AFA89EE-A85F-47D2-EFD4-08DEE9C18370 | TA00083 | Yokogawa SIS/FGS | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 40 | General cleaning |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 16:00 | 2026-07-31 18:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1130
7EB1941C-001F-4184-EFD3-08DEE9C18370 | TA00082 | Yokogawa DCS | Bokor | BODP-B |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 10 | Perform FCS Health Check and General Cleaning at BODP-B |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 08:30 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1000
30580958-5FBB-4C4B-EFD2-08DEE9C18370 | TA00082 | Yokogawa DCS | Bokor | BODP-B |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 20 | Perform HIS Health Check and General Cleaning and updating of Windows O/S Patch and Antivirus and Scan for Viruses |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 11:00 | 2026-07-31 14:00 | [6 empty] | 2026-07-25 09:53 | DPB.I1010
C2819E03-ABE7-4B6F-EFCD-08DEE9C18370 | TA00081 | VCB-7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 10 | Perform power supply isolation and proof dead. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 08:30 | 2026-08-02 09:30 | [6 empty] | 2026-07-25 09:53 | DPB.E2000
EC200009-A5EF-4504-EFD1-08DEE9C18370 | TA00081 | VCB-7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 20 | Perform functional check to open/trip and close circuit. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 10:00 | 2026-08-02 12:00 | [6 empty] | 2026-07-25 09:53 | DPB.E2010
550D3374-A6B9-427C-EFCC-08DEE9C18370 | TA00081 | VCB-7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 30 | Check primary and secondary/arcing contact, control cable connections, arc quenching component, operating mechanism, |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 13:00 | 2026-08-02 15:00 | [6 empty] | 2026-07-25 09:53 | DPB.E2020
3ADBF03A-531D-4A5B-EFCE-08DEE9C18370 | TA00081 | VCB-7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 40 | Lightly lubricate operating mechanism. Perform timing test for VBC/ACB contact and record the result. |  | 3 | 6 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 15:30 | 2026-08-03 10:30 | [6 empty] | 2026-07-25 09:53 | DPB.E2030
BE9A11B9-CE7F-4AC0-EFCF-08DEE9C18370 | TA00081 | VCB-7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 50 | Clean with vacuum cleaner/clean lint free rags. Perform electrical test (contact resistance and Insulation resistance) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 10:30 | 2026-08-03 13:30 | [6 empty] | 2026-07-25 09:53 | DPB.E2040
7C0DAA3A-C1BF-4A1F-EFD0-08DEE9C18370 | TA00081 | VCB-7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 60 | Perform power supply normalisation. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 13:30 | 2026-08-03 14:30 | [6 empty] | 2026-07-25 09:53 | DPB.E2050
9ED011F0-0406-412F-EFC9-08DEE9C18370 | TA00080 | BT-001 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Transfer and set-up of load bank |  | 6.5 | 13 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 08:30 | 2026-08-04 17:00 | [6 empty] | 2026-07-25 09:53 | DPB.E1000
070459C5-28C4-4805-EFCB-08DEE9C18370 | TA00080 | BT-001 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Perform electrical isolation |  | 0.5 | 1 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 08:30 | 2026-08-05 09:00 | [6 empty] | 2026-07-25 09:53 | DPB.E1005
B9031CFF-452F-4310-EFC7-08DEE9C18370 | TA00080 | BT-001 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 30 | Preparation for battery discharge test & perform cleaning on battery bank Tag No. BT-001. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 09:00 | 2026-08-05 11:30 | [6 empty] | 2026-07-25 09:53 | DPB.E1010
7457C397-4FE8-4F4E-EFC8-08DEE9C18370 | TA00080 | BT-001 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 40 | Perform battery discharge test on battery bank Tag no. BT-001. |  | 5 | 10 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 11:30 | 2026-08-05 16:30 | [6 empty] | 2026-07-25 09:53 | DPB.E1020
C9F50D14-F2D6-4CFC-EFCA-08DEE9C18370 | TA00080 | BT-001 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 50 | Normalise electrical isolation |  | 0.5 | 1 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 16:30 | 2026-08-05 17:00 | [6 empty] | 2026-07-25 09:53 | DPB.E1030
B65FF21A-2C53-4A7E-EFC6-08DEE9C18370 | TA00079 | 300-PG-627-61430X - STUDBOLT & GASKET REPLACEMENT (TASK 12) | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-B) 300-PG-627-61430X: ISOLATE LINEWORK |  | 3 | 15 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 08:00 | 2026-08-01 11:30 | [6 empty] | 2026-07-25 09:53 | DPB.C1000
DD95040F-C793-419A-EFC2-08DEE9C18370 | TA00079 | 300-PG-627-61430X - STUDBOLT & GASKET REPLACEMENT (TASK 12) | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-B) 300-PG-627-61430X: REPLACE CORRODED GASKET AND STUDBOLT & NUTS; VI-07, VI-09, VI-10, VI-12, VI-17, VI-18, VI-27 |  | 6 | 30 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 11:30 | 2026-08-02 09:00 | [6 empty] | 2026-07-25 09:53 | DPB.C1010
3C0A5A4E-1E42-4E4C-EFC4-08DEE9C18370 | TA00079 | 300-PG-627-61430X - STUDBOLT & GASKET REPLACEMENT (TASK 12) | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-B) 300-PG-627-61430X: PERFORM BOLT TORQUING (BFJI - 6 NOS 1/2") |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 09:30 | 2026-08-02 12:00 | [6 empty] | 2026-07-25 09:53 | DPB.C1020
EA5B6AF2-CD4B-439B-EFC3-08DEE9C18370 | TA00079 | 300-PG-627-61430X - STUDBOLT & GASKET REPLACEMENT (TASK 12) | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-B) 300-PG-627-61430X: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 12 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 13:00 | 2026-08-02 15:00 | [6 empty] | 2026-07-25 09:53 | DPB.C1030
C02C902B-00CE-4F04-EFC5-08DEE9C18370 | TA00079 | 300-PG-627-61430X - STUDBOLT & GASKET REPLACEMENT (TASK 12) | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-B) 300-PG-627-61430X: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 15:30 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | DPB.C1040
BB239BA1-0961-44AD-EFC0-08DEE9C18370 | TA00078 | PSV P4 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-27 16:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1300
AFB24150-BFC7-45C8-EFBF-08DEE9C18370 | TA00078 | PSV P4 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 16:00 | 2026-07-27 16:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1310
555C9682-A026-49C6-EFBD-08DEE9C18370 | TA00078 | PSV P4 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 10:30 | 2026-07-28 10:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1320
86048F44-25F9-4895-EFBE-08DEE9C18370 | TA00078 | PSV P4 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 10:00 | 2026-07-29 10:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1330
88A50EEC-5FD5-492D-EFC1-08DEE9C18370 | TA00078 | PSV P4 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 10:15 | 2026-07-29 10:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1340
1127AA0D-1654-4E21-EFB9-08DEE9C18370 | TA00077 | PSV P3 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 14:15 | 2026-07-27 14:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1250
A27B4619-4E70-48A4-EFBA-08DEE9C18370 | TA00077 | PSV P3 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 14:45 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1260
88E13C9E-7831-4F3F-EFB8-08DEE9C18370 | TA00077 | PSV P3 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 10:15 | 2026-07-28 10:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1270
8D0505AD-F730-457D-EFBB-08DEE9C18370 | TA00077 | PSV P3 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 08:45 | 2026-07-29 09:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1280
CCC7FECC-CB6B-43C7-EFBC-08DEE9C18370 | TA00077 | PSV P3 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 09:15 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1290
79EB7E1B-0084-4FDA-EFB5-08DEE9C18370 | TA00076 | PSV P2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1200
7125D0CB-DD31-41D3-EFB3-08DEE9C18370 | TA00076 | PSV P2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-27 14:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1210
7A774426-AFE7-4D59-EFB6-08DEE9C18370 | TA00076 | PSV P2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 10:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1220
1A963360-AF90-4CE0-EFB7-08DEE9C18370 | TA00076 | PSV P2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:45 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1230
C467270F-4581-45B9-EFB4-08DEE9C18370 | TA00076 | PSV P2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 08:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1240
651D4559-D0E5-4BAB-EFB1-08DEE9C18370 | TA00075 | PSV P1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 11:45 | 2026-07-27 13:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1150
BCD4238C-19A9-4050-EFB2-08DEE9C18370 | TA00075 | PSV P1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 13:15 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1160
39D49777-D47C-4D41-EFB0-08DEE9C18370 | TA00075 | PSV P1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 09:15 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1170
BE25C800-0D61-4101-EFAF-08DEE9C18370 | TA00075 | PSV P1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:00 | 2026-07-28 16:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1180
003AE28C-7EF4-44F1-EFAE-08DEE9C18370 | TA00075 | PSV P1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 16:30 | 2026-07-28 16:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1190
CC4347F7-0F56-4F96-EFA9-08DEE9C18370 | TA00074 | PSV EE1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-27 11:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1100
61CE6B71-7703-4045-EFAD-08DEE9C18370 | TA00074 | PSV EE1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 11:30 | 2026-07-27 11:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1110
C1A83E0C-5837-4737-EFAB-08DEE9C18370 | TA00074 | PSV EE1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 09:00 | 2026-07-28 09:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1120
544E6481-286A-4C66-EFAC-08DEE9C18370 | TA00074 | PSV EE1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 14:45 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1130
24F1E2C0-F7F4-45CE-EFAA-08DEE9C18370 | TA00074 | PSV EE1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 15:45 | 2026-07-28 16:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1140
FD7A53E3-FC82-4832-EFA8-08DEE9C18370 | TA00073 | PSV DD2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 10:15 | 2026-07-27 10:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1050
BEFB9AAD-E21C-4F8B-EFA7-08DEE9C18370 | TA00073 | PSV DD2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 10:45 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1060
7F34CE3D-25A5-4DA6-EFA4-08DEE9C18370 | TA00073 | PSV DD2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 08:45 | 2026-07-28 09:00 | [6 empty] | 2026-07-25 09:53 | DPB.S1070
E85012ED-0519-4AE9-EFA5-08DEE9C18370 | TA00073 | PSV DD2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 14:15 | 2026-07-28 14:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1080
A9C6E72F-5DCB-48A7-EFA6-08DEE9C18370 | TA00073 | PSV DD2 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 14:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1090
EA9CD32E-2CAC-472B-EFA3-08DEE9C18370 | TA00072 | PSV R1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 09:00 | 2026-07-27 09:30 | [6 empty] | 2026-07-25 09:53 | DPB.S1000
AF6CE312-2C48-4A8F-EFA2-08DEE9C18370 | TA00072 | PSV R1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & blind the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 10:00 | 2026-07-27 10:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1010
D74F05D0-C3BF-4257-EFA0-08DEE9C18370 | TA00072 | PSV R1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 08:30 | 2026-07-28 08:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1020
353B9022-C7E7-441D-EF9F-08DEE9C18370 | TA00072 | PSV R1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Deblind & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 13:30 | 2026-07-28 13:45 | [6 empty] | 2026-07-25 09:53 | DPB.S1030
C97A0485-BFA9-4AF2-EFA1-08DEE9C18370 | TA00072 | PSV R1 (1/4" MNPT) | Bokor | BODP-B |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 14:00 | 2026-07-28 14:15 | [6 empty] | 2026-07-25 09:53 | DPB.S1040
C2DEBA91-D1F1-4678-EF9E-08DEE9C18370 | TA00071 | BODA-ABV921 | Bokor | BODP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODA-ABV921 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 17:30 | 2026-07-25 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.RE1060
375251EE-6626-4270-EF9D-08DEE9C18370 | TA00070 | BODA-ABV936 | Bokor | BODP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODA-ABV936 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 17:30 | 2026-07-25 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.RE1050
15825819-1780-4681-EF9C-08DEE9C18370 | TA00069 | BODA-ABV911 | Bokor | BODP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODA-ABV911 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 17:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.RE1040
354191A3-CCB2-46DC-EF9B-08DEE9C18370 | TA00068 | BODPA-ABV933 | Bokor | BODP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BODPA-ABV933 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 17:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.RE1030
DFADC37D-A7E5-445A-EF9A-08DEE9C18370 | TA00067 | RMCS-ESP (Remote Monitoring and Control System) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | Site inspection and system verification for BODP-A RMCS ESP |  | 1.5 | 1.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 11:00 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1280
F788FFA1-FA23-4B9E-EF99-08DEE9C18370 | TA00067 | RMCS-ESP (Remote Monitoring and Control System) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Check system error for BODP-A RMCS ESP |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 16:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1290
C2D052C2-2AFF-430E-EF98-08DEE9C18370 | TA00067 | RMCS-ESP (Remote Monitoring and Control System) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Backup program for BODP-A RMCS ESP |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 16:00 | 2026-07-30 09:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1300
2B953401-912F-4AF4-EF97-08DEE9C18370 | TA00067 | RMCS-ESP (Remote Monitoring and Control System) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Perform fault rectification for BODP-A RMCS ESP |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 10:00 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1310
D751474A-6F18-46AE-EF96-08DEE9C18370 | TA00066 | HVAC-01 (HVAC Control Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | Site inspection and system verification for BODP-A AHU |  | 1.5 | 1.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1240
E1ED28F6-5B75-468F-EF93-08DEE9C18370 | TA00066 | HVAC-01 (HVAC Control Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Check system error for BODP-A AHU |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 11:30 | 2026-07-28 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1250
64D75A31-47BB-462F-EF95-08DEE9C18370 | TA00066 | HVAC-01 (HVAC Control Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Backup program for BODP-A AHU |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1260
E8B12871-47EB-4584-EF94-08DEE9C18370 | TA00066 | HVAC-01 (HVAC Control Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Perform fault rectification for BODP-A AHU |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 11:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1270
D7EDC3C6-C90A-4F21-EF92-08DEE9C18370 | TA00065 | PP-01 (Purge Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | Site inspection and system verification for BODP-A Purge panel |  | 1.5 | 1.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 08:30 | 2026-07-27 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1200
57305EF0-6DA4-48B5-EF8F-08DEE9C18370 | TA00065 | PP-01 (Purge Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Check system error for BODP-A Purge panel |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 10:30 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1210
1DB712C3-D470-4ED4-EF90-08DEE9C18370 | TA00065 | PP-01 (Purge Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Backup program for BODP-A Purge panel |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-27 16:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1220
074DC4E0-7FCF-4B2A-EF91-08DEE9C18370 | TA00065 | PP-01 (Purge Panel) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Perform fault rectification for BODP-A Purge panel |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 16:00 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1230
EA1257DC-528D-4332-EF88-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 10 | Cold cut structure |  | 4 | 16 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1000
38E5920F-A185-4B96-EF8A-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 20 | Install rigging gear |  | 4 | 24 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 14:00 | [6 empty] | 2026-07-25 09:53 | DPA.I10001
AC7ED312-833C-45B1-EF80-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 30 | Assist physical isolation preparation by operation team |  | 3 | 18 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1005
4F6E6ADC-2E48-4920-EF81-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 40 | Remove control panel accessories from actuator / remote |  | 3 | 18 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 13:00 | 2026-07-26 16:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1010
FB150036-971A-4D03-EF85-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 50 | Remove actuator from existing valve |  | 10 | 60 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 16:30 | 2026-07-28 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1020
65274A9B-6472-47A0-EF86-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 60 | Topwork measurement for mounting harware (MHW) fabrication onshore |  | 3.5 | 21 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 13:00 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1030
72176EAB-934D-4646-EF83-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 70 | Mounting Hard Ware (MHW) fabrication onshore |  | 26 | 156 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-08-01 17:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1040
A34DD506-7F6D-485C-EF8E-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 80 | Lifting and transfer new MHW from FCB to work location |  | 1 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 08:30 | 2026-08-02 09:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1050
BF2BA451-FF1E-43EF-EF82-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 90 | Installation of new MHW and actuator onto existing ball valve |  | 12 | 72 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 11:00 | 2026-08-04 09:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1060
CADDE9ED-9E74-464B-EF8B-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 100 | Instrumentation work (Control panel installation, tubing tie in & cable glanding) |  | 2 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 10:00 | 2026-08-04 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1070
A51D265A-3DD3-406A-EF87-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 110 | Welding structure |  | 10 | 20 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-04 13:00 | 2026-08-05 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1071
4D7F24E9-C286-49CA-EF89-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 120 | Touch up painting actuator |  | 1 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-05 15:30 | 2026-08-05 16:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1080
AE4FB083-EFFE-4345-EF7F-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 130 | Connect greasing hose to the greasing port |  | 1 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-05 16:30 | 2026-08-06 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1090
AD162546-D248-44C4-EF84-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 140 | Pump new olivals grease to the greasing port |  | 2 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-06 13:00 | 2026-08-06 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.I1100
CACD8A31-C22F-4FC1-EF8C-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 150 | Stroke the valve to ensure smooth environment |  | 3 | 18 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-06 15:30 | 2026-08-07 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1110
4A91F317-78E2-444F-EF8D-08DEE9C18370 | TA00064 | ABV933 (12"1500#) | Bokor | BODP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | WEHAYA-I | Execution | 160 | Pre-testing & testing commissioning (Stroke test) |  | 1 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-07 10:30 | 2026-08-07 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.I1120
02F65679-1419-44E5-EF7B-08DEE9C18370 | TA00063 | 50-PG-115-61432P - PIPING PG REPLACEMENT (TASK 4) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-PG-115-61432P: ISOLATE LINEWORK |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 13:00 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3200
474FD0F9-E691-4F44-EF7D-08DEE9C18370 | TA00063 | 50-PG-115-61432P - PIPING PG REPLACEMENT (TASK 4) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-PG-115-61432P: UNBOLT AND REMOVE CORRODED SPOOL (2 EA) |  | 8 | 40 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 15:30 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3210
F7BF826E-438B-4F08-EF7A-08DEE9C18370 | TA00063 | 50-PG-115-61432P - PIPING PG REPLACEMENT (TASK 4) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-PG-115-61432P: INSTALL AND BOLT UP NEW SPOOL (6 FLANGES); V1 - V21 |  | 10 | 50 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-30 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3220
E6E44620-A6A6-45FF-EF79-08DEE9C18370 | TA00063 | 50-PG-115-61432P - PIPING PG REPLACEMENT (TASK 4) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-PG-115-61432P: PERFORM BOLT TORQUING (BFJI - 6 NOS) |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3230
AC39C0AD-E908-4C01-EF7E-08DEE9C18370 | TA00063 | 50-PG-115-61432P - PIPING PG REPLACEMENT (TASK 4) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-PG-115-31432P: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 12 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 16:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3240
DA76FC89-6197-4B55-EF7C-08DEE9C18370 | TA00063 | 50-PG-115-61432P - PIPING PG REPLACEMENT (TASK 4) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-PG-115-61432P: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 16:00 | 2026-07-31 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3250
BAEDD716-7A1E-4E99-EF74-08DEE9C18370 | TA00062 | [B] 50-PG-133-61452 - PIPING PG REPLACEMENT (TASK 7) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-PG-133-61452: ISOLATE LINEWORK |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 08:00 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3440
DFE04B20-EF50-4B56-EF75-08DEE9C18370 | TA00062 | [B] 50-PG-133-61452 - PIPING PG REPLACEMENT (TASK 7) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-PG-133-61452: UNBOLT AND REMOVE CORRODE SPOOL (2EA) (Cut 1 jts, flange 1 , joint, drop 1 spool) |  | 7.5 | 37.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-28 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3450
91757586-9A14-473E-EF72-08DEE9C18370 | TA00062 | [B] 50-PG-133-61452 - PIPING PG REPLACEMENT (TASK 7) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-PG-133-61452: WELDING NEW SPOOL (4 JTS BONLOK); V6 - V20; V28 - V36 |  | 24 | 168 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3460
30394A65-544D-4407-EF77-08DEE9C18370 | TA00062 | [B] 50-PG-133-61452 - PIPING PG REPLACEMENT (TASK 7) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-PG-130-61432P: PERFORM RT (4 JTS BONLOK) |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 | 2026-08-03 01:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3470
71251826-B211-455A-EF73-08DEE9C18370 | TA00062 | [B] 50-PG-133-61452 - PIPING PG REPLACEMENT (TASK 7) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-PG-133-61452: TIE-IN 4 FLANGES & PERFORM BOLT TORQUING (BFJI - 4 NOS) |  | 10.5 | 52.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 16:00 | 2026-08-06 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3480
9C65075B-E392-47D7-EF78-08DEE9C18370 | TA00062 | [B] 50-PG-133-61452 - PIPING PG REPLACEMENT (TASK 7) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-PG-133-31430: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 12 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-06 11:30 | 2026-08-06 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3490
0585E440-6F3D-447C-EF76-08DEE9C18370 | TA00062 | [B] 50-PG-133-61452 - PIPING PG REPLACEMENT (TASK 7) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BODP-A) 50-PG-133-61452: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-06 14:30 | 2026-08-06 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3500
176938FF-952F-4FB8-EF6E-08DEE9C18370 | TA00061 | [B] 50-PG-131-61432 - PIPING PG REPLACEMENT (TASK 6) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-PG-131-61432: ISOLATE LINEWORK + LIFTING |  | 4.5 | 22.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3370
9911EE72-093F-485B-EF6D-08DEE9C18370 | TA00061 | [B] 50-PG-131-61432 - PIPING PG REPLACEMENT (TASK 6) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-PG-131-61432: UNBOLT AND REMOVE CORRODED SPOOL (2 EA) (Cut 1 jts, flange 1 , joint, drop 1 spool) |  | 8 | 40 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-26 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3380
7091E02E-ECFF-4AA1-EF70-08DEE9C18370 | TA00061 | [B] 50-PG-131-61432 - PIPING PG REPLACEMENT (TASK 6) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-PG-131-61432: WELDING NEW SPOOL (3 JTS); V5 - V14; V15 - V17 |  | 16 | 112 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3390
8357665B-22C5-4229-EF71-08DEE9C18370 | TA00061 | [B] 50-PG-131-61432 - PIPING PG REPLACEMENT (TASK 6) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-PG-131-61432P: PERFORM RT |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 01:00 | 2026-08-03 02:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3400
14A3DC02-6299-45CB-EF6C-08DEE9C18370 | TA00061 | [B] 50-PG-131-61432 - PIPING PG REPLACEMENT (TASK 6) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-PG-131-61432: TIE-IN 4 FLANGES & PERFORM BOLT TORQUING (BFJI - 4 NOS) |  | 10 | 50 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 08:00 | 2026-08-04 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3410
F5297B76-98FA-4AF4-EF6B-08DEE9C18370 | TA00061 | [B] 50-PG-131-61432 - PIPING PG REPLACEMENT (TASK 6) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-PG-131-31432: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 10:30 | 2026-08-04 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3420
80C281E5-F887-4090-EF6F-08DEE9C18370 | TA00061 | [B] 50-PG-131-61432 - PIPING PG REPLACEMENT (TASK 6) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BODP-A) 50-PG-131-61432: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 11:30 | 2026-08-04 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3430
CD9352EC-392F-4D9D-EF66-08DEE9C18370 | TA00060 | 50-PG-126-61430 - PIPING PG REPLACEMENT (TASK 8) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-PG-126-61430: ISOLATE LINEWORK |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 11:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3510
78C8ED83-48F0-499F-EF69-08DEE9C18370 | TA00060 | 50-PG-126-61430 - PIPING PG REPLACEMENT (TASK 8) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-PG-126-61430: UNBOLT AND REMOVE CORRODE SPOOL (1EA) |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 11:00 | 2026-08-04 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3520
103CDF38-9D3D-4BC4-EF6A-08DEE9C18370 | TA00060 | 50-PG-126-61430 - PIPING PG REPLACEMENT (TASK 8) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-PG-126-61430: INSTALL AND BOLT UP NEW SPOOL (2 FLANGESI); V5 - V14 |  | 2.5 | 12.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 14:30 | 2026-08-04 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3530
7A6A2F3C-59DE-4E43-EF68-08DEE9C18370 | TA00060 | 50-PG-126-61430 - PIPING PG REPLACEMENT (TASK 8) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-PG-126-61430: PERFORM BOLT TORQUING (BFJI - 2 NOS) |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 17:30 | 2026-08-05 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3540
08DBFBD7-CA77-4834-EF65-08DEE9C18370 | TA00060 | 50-PG-126-61430 - PIPING PG REPLACEMENT (TASK 8) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-PG-126-31430: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 12 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 13:00 | 2026-08-05 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3550
ED0B5C10-4F8C-459A-EF67-08DEE9C18370 | TA00060 | 50-PG-126-61430 - PIPING PG REPLACEMENT (TASK 8) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-PG-126-61430: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 15:30 | 2026-08-05 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3560
22C29963-ADC6-4231-EF61-08DEE9C18370 | TA00059 | 50-PG-127-61430 - PIPING PG REPLACEMENT (TASK 9) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-PG-127-61430: ISOLATE LINEWORK |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3640
E736BAE2-0D3F-4D0D-EF60-08DEE9C18370 | TA00059 | 50-PG-127-61430 - PIPING PG REPLACEMENT (TASK 9) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-PG-127-61430: REMOVE CORRODED SECTIONS; V2 (1EA) |  | 3.5 | 17.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3650
87972887-AE03-482E-EF5F-08DEE9C18370 | TA00059 | 50-PG-127-61430 - PIPING PG REPLACEMENT (TASK 9) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-PG-127-61430: INSTALL AND BOLT UP NEW SPOOL (3 FLANGES) |  | 3.5 | 17.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-30 09:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3660
2CFF25F9-C09A-43FE-EF64-08DEE9C18370 | TA00059 | 50-PG-127-61430 - PIPING PG REPLACEMENT (TASK 9) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-PG-127-61430: PERFORM BOLT TORQUING (BFJI - 3 NOS) |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 09:30 | 2026-07-30 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3670
9A1D9DB9-5CE9-4C34-EF63-08DEE9C18370 | TA00059 | 50-PG-127-61430 - PIPING PG REPLACEMENT (TASK 9) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-PG-127-61430: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 14:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3680
4595642B-36E6-42F2-EF62-08DEE9C18370 | TA00059 | 50-PG-127-61430 - PIPING PG REPLACEMENT (TASK 9) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-PG-127-61430: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-30 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3690
FE361DA3-7AD0-4837-EF59-08DEE9C18370 | TA00058 | [B) 50-PG-130-61432P - PIPING PG REPLACEMENT (TASK 5) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-PG-130-61432P: ISOLATE LINEWORK |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 16:00 | 2026-07-27 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3300
7218CCDA-C7D7-4B39-EF5A-08DEE9C18370 | TA00058 | [B) 50-PG-130-61432P - PIPING PG REPLACEMENT (TASK 5) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-PG-130-61432P: UNBOLT AND REMOVE CORRODED SPOOL (3EA) (Cut 1 jts, flange 1 joint, drop 1 spool) |  | 9 | 45 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 20:00 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3310
23D47747-E41F-4497-EF5E-08DEE9C18370 | TA00058 | [B) 50-PG-130-61432P - PIPING PG REPLACEMENT (TASK 5) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-PG-130-61432P: WELDING NEW SPOOL (2 JTS BONLOK & ); V6 - V8, V15 - V24 |  | 16 | 112 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3320
3F131806-77F8-421D-EF5D-08DEE9C18370 | TA00058 | [B) 50-PG-130-61432P - PIPING PG REPLACEMENT (TASK 5) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-PG-130-61432P: PERFORM RT |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 | 2026-08-02 01:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3330
FA6350D3-5E00-48E8-EF5C-08DEE9C18370 | TA00058 | [B) 50-PG-130-61432P - PIPING PG REPLACEMENT (TASK 5) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-PG-130-61432P: TIE-IN & PERFORM BOLT TORQUING (BFJI - 8 NOS) |  | 13 | 65 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-03 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3340
D0F2F0E5-5495-4118-EF58-08DEE9C18370 | TA00058 | [B) 50-PG-130-61432P - PIPING PG REPLACEMENT (TASK 5) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-PG-130-31432P: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 14:30 | 2026-08-03 16:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3350
0B429EA6-E663-40CD-EF5B-08DEE9C18370 | TA00058 | [B) 50-PG-130-61432P - PIPING PG REPLACEMENT (TASK 5) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BODP-A) 50-PG-130-61432P: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 16:00 | 2026-08-03 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3360
09E91E91-9F99-454A-EF52-08DEE9C18370 | TA00057 | 50-PG-104-61432P - PIPING PG REPLACEMENT (TASK 3) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-PG-104-61432P: ISOLATE LINEWORK |  | 4.5 | 22.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3000
19D3920A-5F8F-471E-EF54-08DEE9C18370 | TA00057 | 50-PG-104-61432P - PIPING PG REPLACEMENT (TASK 3) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-PG-104-61432P: UNBOLT AND REMOVE CORRODED SPOOL (7 EA) |  | 13.5 | 67.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3010
3EDFE5DF-44AB-4817-EF57-08DEE9C18370 | TA00057 | 50-PG-104-61432P - PIPING PG REPLACEMENT (TASK 3) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-PG-104-61432P: INSTALL AND BOLT UP NEW SPOOL (13 FLANGES); V1 - V27 |  | 13 | 65 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 15:30 | 2026-07-29 11:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3020
C4425529-0E95-4426-EF56-08DEE9C18370 | TA00057 | 50-PG-104-61432P - PIPING PG REPLACEMENT (TASK 3) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-PG-104-61432P: PERFORM BOLT TORQUING (BFJI - 13 NOS) |  | 8 | 40 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 08:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3030
D00EF7B6-9234-4E19-EF55-08DEE9C18370 | TA00057 | 50-PG-104-61432P - PIPING PG REPLACEMENT (TASK 3) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-PG-104-31432P: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 3 | 18 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3040
1CA4DC03-F002-4112-EF53-08DEE9C18370 | TA00057 | 50-PG-104-61432P - PIPING PG REPLACEMENT (TASK 3) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-PG-104-61432P: DE-ISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 11:30 | 2026-08-02 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3050
5B36358B-90E9-4581-EF51-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 50-INSTRUMENT AIR HEADER: ISOLATE LINEWORK |  | 4 | 20 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1070
1A0BEA18-54F6-468F-EF40-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V7 & V8 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-26 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1080
9FFC5853-5BC5-4B7E-EF41-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 10:30 | 2026-07-26 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1090
AB448A4B-FBE9-4045-EF4D-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V9 & V10 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 13:00 | 2026-07-26 15:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1100
FB9DBF5B-D28E-4C54-EF3D-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF), REPLACE CORRODED GASKETS & BOLTING |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 15:30 | 2026-07-26 16:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1110
2E177D9B-145A-4E16-EF3F-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V11 & V12 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-26 16:30 | 2026-07-27 08:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1120
DDA47F08-46B1-4526-EF44-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF), REPLACE CORRODED GASKETS & BOLTING |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 08:30 | 2026-07-27 10:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1130
DF64FA05-7B7C-4CCD-EF50-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 80 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V13 & V14 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 10:00 | 2026-07-27 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1140
0682FD87-2456-4AEC-EF46-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 90 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF), REPLACE CORRODED GASKETS & BOLTING |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 13:00 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1150
AF7B1461-0EC6-4143-EF4F-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 100 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V16 & V17 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-27 16:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1160
436A0D66-D898-4A9A-EF38-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 110 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF), REPLACE CORRODED GASKETS & BOLTING |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-27 16:30 | 2026-07-27 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1170
1A627702-5767-4796-EF3C-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 120 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V18 & V19 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 08:00 | 2026-07-28 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1180
41149313-6581-4B07-EF3A-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 130 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP NEW VALVE, REPLACE CORRODED GASKETS & BOLTINGS |  | 3 | 15 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-28 10:30 | 2026-07-28 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1190
94D6DEE7-5955-4391-EF45-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 140 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED BLIND; V22 & V24 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 10:30 | 2026-08-03 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1200
1CAD456C-AE39-4FA3-EF49-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 150 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND REPLACE WITH BLIND FLANGE, REPLACE CORRODED GASKETS & BOLTINGS |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 13:30 | 2026-08-03 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1210
AEEC5D4B-601F-41F2-EF4E-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 160 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED BLIND; V27 & V28 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 14:30 | 2026-08-03 17:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1220
332BED17-22F9-4922-EF3E-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 170 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND REPLACE WITH BLIND FLANGE, REPLACE CORRODED GASKETS & BOLTINGS |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 17:00 | 2026-08-03 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1230
17B61E2B-3D32-42CC-EF47-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 180 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V31 & V32 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1240
1DCCDCEF-C3D0-460A-EF48-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 190 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF), REPLACE CORRODED GASKETS & BOLTING |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 10:30 | 2026-08-04 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1250
B4854693-E769-4F6E-EF39-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 200 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE; V34 & V35 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 11:30 | 2026-08-04 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1260
C8951CAD-BA3D-42B8-EF43-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 210 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF), REPLACE CORRODED GASKETS & BOLTING |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 14:30 | 2026-08-04 16:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1270
E5C09E9B-62B1-41FC-EF42-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 220 | (BODP-A) 50-INSTRUMENT AIR HEADER: UNBOLT AND REMOVED CORRODED VALVE |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-04 16:00 | 2026-08-04 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1271
92EB9706-D295-4CF6-EF4B-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 230 | (BODP-A) 50-INSTRUMENT AIR HEADER: INSTALL AND BOLT UP WITH BLIND FLANGE (BLIND OFF), REPLACE CORRODED GASKETS & BOLTING |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 08:00 | 2026-08-05 09:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1272
7E51D642-E0A3-407E-EF3B-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 240 | (BODP-A) 50-INSTRUMENT AIR HEADER: PERFORM BOLT TORQUING (BFJI - 12 NOS) |  | 8 | 40 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-05 09:30 | 2026-08-06 12:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1280
F51D9BE6-ADF9-4F72-EF4C-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 250 | (BODP-A) 50-INSTRUMENT AIR HEADER: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 3 | 18 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-06 13:30 | 2026-08-06 17:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1290
021944E1-88E4-4AB9-EF4A-08DEE9C18370 | TA00056 | IA HEADER - VALVE REMOVAL & BLIND OFF (TASK 2) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 260 | (BODP-A) 50-INSTRUMENT AIR HEADER: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-07 08:00 | 2026-08-07 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1300
0B137CC4-954C-462E-EF35-08DEE9C18370 | TA00055 | [B] 25-IA- LINE - PIPING REPLACEMENT (TASK 10) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 25-IA-LINE: ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 11:30 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3570
758BDE51-9FF1-4F00-EF34-08DEE9C18370 | TA00055 | [B] 25-IA- LINE - PIPING REPLACEMENT (TASK 10) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 25-IA-LINE: REMOVE CORRODE SPOOL/ THREADED JOINTS (1EA) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C3580
EFA48901-859D-4395-EF37-08DEE9C18370 | TA00055 | [B] 25-IA- LINE - PIPING REPLACEMENT (TASK 10) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 25-IA-LINE: WELDING NEW SPOOL WITH THREADED JOINT (V1 & V2) - 1 JTS HW |  | 8 | 56 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3590
8A10795B-C236-412E-EF32-08DEE9C18370 | TA00055 | [B] 25-IA- LINE - PIPING REPLACEMENT (TASK 10) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 25-IA-LINE: PERFORM RT (1 JTS) |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 | 2026-08-03 01:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3600
10FC2209-8DE4-47F6-EF36-08DEE9C18370 | TA00055 | [B] 25-IA- LINE - PIPING REPLACEMENT (TASK 10) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 25-IA-LINE: TIE-IN FLANGE & PERFORM BOLT TORQUING (BFJI - 1 NOS) |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 14:30 | 2026-08-03 16:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3610
D874B171-CCB0-4742-EF33-08DEE9C18370 | TA00055 | [B] 25-IA- LINE - PIPING REPLACEMENT (TASK 10) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 25-IA-LINE: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 16:00 | 2026-08-03 17:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3620
66C0F595-4C3E-4171-EF31-08DEE9C18370 | TA00055 | [B] 25-IA- LINE - PIPING REPLACEMENT (TASK 10) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BODP-A) 25-IA-LINE: DE-ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 17:00 | 2026-08-03 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C3630
CE50AA2D-29C1-4BDA-EF2B-08DEE9C18370 | TA00054 | [B] 25-IA-502-1101X - PIPING REPLACEMENT (TASK 1) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BODP-A) 25-IA-502-1101X: ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 09:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1000
EAA8A8D1-088F-4ECA-EF30-08DEE9C18370 | TA00054 | [B] 25-IA-502-1101X - PIPING REPLACEMENT (TASK 1) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BODP-A) 25-IA-502-1101X: CUT AND REMOVE CORRODED SECTIONS; V2 (1 SPOOL) - 1 flange 2 cut |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-29 09:30 | 2026-07-29 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1010
BCB62837-FB5C-4980-EF2A-08DEE9C18370 | TA00054 | [B] 25-IA-502-1101X - PIPING REPLACEMENT (TASK 1) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BODP-A) 25-IA-502-1101X: WELDING NEW SPOOL (2 JOINTS HW) |  | 8 | 48 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1020
7686129C-0FC4-40A0-EF2C-08DEE9C18370 | TA00054 | [B] 25-IA-502-1101X - PIPING REPLACEMENT (TASK 1) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BODP-A) 25-IA-502-1101X: PERFORM RT |  | 1 | 2 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 | 2026-08-03 01:00 | [6 empty] | 2026-07-25 09:53 | DPA.C1030
9DAD41AB-A17E-4166-EF2D-08DEE9C18370 | TA00054 | [B] 25-IA-502-1101X - PIPING REPLACEMENT (TASK 1) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BODP-A) 25-IA-502-1101X: TIE-IN FLANGE & PERFORM BOLT TORQUING (BFJI - 1 NOS) |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 08:00 | 2026-08-03 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1040
4058B2CE-05DD-498B-EF2E-08DEE9C18370 | TA00054 | [B] 25-IA-502-1101X - PIPING REPLACEMENT (TASK 1) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BODP-A) 25-IA-502-1101X: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 1 | 6 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 10:30 | 2026-08-03 11:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1050
175FF30A-0109-4CA1-EF2F-08DEE9C18370 | TA00054 | [B] 25-IA-502-1101X - PIPING REPLACEMENT (TASK 1) | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BODP-A) 25-IA-502-1101X: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-03 11:30 | 2026-08-03 14:30 | [6 empty] | 2026-07-25 09:53 | DPA.C1060
3E629DBC-59C9-4A53-EF22-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 10 | REMOVE 10" EXISTING SPOOL (COLD CUT) @ TP-03 & TP-04 of 150-P-036-153411 |  | 12 | 72 |  |  | APROTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1450
707B8EB0-3586-470A-EF24-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 20 | PRE-LAY NEW MODIFICATION SPOOL @ TP-03 & TP-04 of 150-P-036-15S600 (6") |  | 12 | 72 |  |  | APROTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-28 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1460
07DD8FAE-5AD6-4E46-EF23-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 30 | ERECT HABITAT FOR PIPE SUPPORT |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1465
AD39BC1D-BF92-49C6-EF25-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 40 | PRE-LAY NEW PS-07 for 150-P-036-15S600 |  | 4 | 16 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 08:00 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1466
65FF3E1C-7022-45A8-EF27-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 50 | TO WELD NEW PS-07 for 150-P-036-15S600 |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1467
05FCD3A5-70BB-4C9D-EF29-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 60 | BOX-UP NEW MODIFICATION SPOOL & INSTALL 2nos of NEW 6" BALL VALVE, 1nos of NEW 3/4" GATE VALVE @ TP-03 & TP-04 |  | 16 | 96 |  |  | APROTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1480
A1205C2F-AF97-4792-EF28-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 70 | Perform JIT Verification by PCSB QAQC |  | 4 | 20 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1481
6918D681-8C70-4387-EF26-08DEE9C18370 | TA00053 | TP-03 & 04 - Team 3 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 80 | TO PERFORM REINSTATEMENT LEAK TEST AT TP-03/04 |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 13:30 | 2026-08-03 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1505
5FBBED22-247E-4F96-EF18-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 10 | INSTALL MANIFOLD FOR LP HEADER BANK 'B' |  | 8 | 64 |  |  | APROTH00 |  |  | 0 |  | 2026-07-28 08:00 | 2026-07-28 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3120
FE2580C2-0C46-4CBD-EF1A-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 20 | PRE-LAY NEW MODIFICATION SPOOL (MANIFOLD) of 250-P-060-15S600 |  | 8 | 64 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3130
EF804363-B84B-447A-EF1C-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 30 | ISOLATE SUMP CAISSON (prior HW) |  | 4.5 | 27 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 13:00 | 2026-07-29 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3135
563768D5-FAF3-4C0A-EF16-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 40 | WELD 2jts NEW MODIFICATION SPOOL (MANIFOLD) of 250-P-060-15S600 |  | 32 | 384 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 08:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3140
B6C6F923-5F82-4BB8-EF1E-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 50 | PEROFRM RT FOR 2jts NEW MODIFICATION SPOOL (MANIFOLD) of 250-P-060-15S600 |  | 1 | 2 |  |  | APROTH00 |  |  | 0 |  | 2026-08-03 | 2026-08-03 01:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3150
FF516D29-8CE5-48A4-EF1D-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 60 | ANALYZE RT RESULT FOR 2jts NEW MODIFICATION SPOOL (MANIFOLD) of 250-P-060-15S600 |  | 4 | 8 |  |  | APROTH00 |  |  | 0 |  | 2026-08-03 01:00 | 2026-08-03 05:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3160
0C34CC4A-5A30-4A81-EF19-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 70 | PERFORM HYDROTEST for 2jts of NEW MODI SPOOL (MANIFOLD) of 250-P-060-15S600 |  | 8 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-08-03 08:00 | 2026-08-03 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3170
C6ED6D63-55FE-44CC-EF17-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 80 | PERFORM BOLT TORQUING (2 joints) |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 13:30 | 2026-08-05 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3171
8649F05D-DF28-4714-EF21-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 90 | Perform JIT Verification by PCSB QAQC |  | 3 | 15 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 14:30 | 2026-08-05 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3180
E34A338C-B07A-4FB6-EF1B-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 100 | PERFORM REINSTATEMENT LEAK TEST FOR TP02 |  | 8 | 56 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 14:30 | 2026-08-06 17:30 | [6 empty] | 2026-07-25 09:53 | DPA.F3190
28895CEE-28BE-4FB6-EF1F-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 110 | DESPADING ALL POSITIVE ISOLATION (FOR NEW EXTENSION HEADER & SPOOL REPLACEMENT) |  | 2.5 | 15 |  |  | APROTH00 |  |  | 0 |  | 2026-08-07 08:00 | 2026-08-07 11:00 | [6 empty] | 2026-07-25 09:53 | DPA.F3195
D41D55D1-C462-463E-EF20-08DEE9C18370 | TA00052 | Manifold A (Upper Section) - Team 2 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 120 | DE-ISOLATE SUMP CAISSON |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-07 08:00 | 2026-08-07 10:30 | [6 empty] | 2026-07-25 09:53 | DPA.F3196
4AEAB7B9-7EF6-404B-EF13-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 10 | Positive isolation |  | 4.5 | 27 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1346
93BBA6D8-DA69-4E97-EF11-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 20 | DRAINING BY OPNS + LIFTING & TRANSFER SPOOL/VALVE |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-26 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1347
15133DA2-DC75-4DF7-EF0E-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 30 | REMOVE 12" BLIND FLANGE @ TP-02 of 300-P-0025-153411 |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-27 08:00 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1350
C375F160-9607-4506-EF10-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 40 | PRE-LAY & INSTALL (2 EA - 12") NEW MODIFICATION SPOOL @ TP-02 of 250-P-0060-15S600 |  | 12 | 72 |  |  | APROTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-28 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1360
2F273CB1-DC67-48CB-EF12-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 50 | PRE-LAY & INSTALL 1 NOS of NEW 10" BALL VALVE & 1nos of NEW 3/4" GATE VALVE @ 300-P-0025-15S600 |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1370
DAC8363A-E031-4BB7-EF0C-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 60 | PRE-LAY NEW PS-04 for 250-P-061-15S600 |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1390
EA451CB0-8363-4944-EF0F-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 70 | TO WELD NEW PS-04 for 250-P-061-15S600 |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 18:00 | [6 empty] | 2026-07-25 09:53 | DPA.F1400
F3A1BCB6-1A79-49E2-EF14-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 80 | PRE-LAY NEW PS-05 for 250-P-061-15S600 |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1410
B6C59444-AD57-43FF-EF15-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 90 | TO WELD NEW PS-02 for 250-P-061-15S600 |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-08-01 08:00 | 2026-08-01 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1420
4707D9CB-3CAA-4FB6-EF0A-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 100 | PRE-LAY & INSTALL 1 NOS of NEW 10" BALL VALVE |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1423
9BFBA4C3-B89A-42AA-EF0D-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 110 | PERFORM BOLT TORQUING (6 joints) |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-08-04 13:30 | 2026-08-05 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1424
B7A3C49C-F805-41EE-EF0B-08DEE9C18370 | TA00051 | TP-02 (Lower section) - Team 1 | Bokor | BODP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 120 | Perform JIT Verification by PCSB QAQC |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 10:30 | 2026-08-05 13:30 | [6 empty] | 2026-07-25 09:53 | DPA.F1425
68CD32FB-79E9-40D0-EF09-08DEE9C18370 | TA00050 | BOPA-ABV1123 | Bokor | BOP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOKA-ABV1123 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 16:30 | 2026-07-25 17:00 | [6 empty] | 2026-07-25 09:53 | PA.RE1030
C4403757-E02C-4BC7-EF08-08DEE9C18370 | TA00049 | BOPA-ABV971 | Bokor | BOP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOKA-ABV971 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 16:00 | 2026-07-25 16:30 | [6 empty] | 2026-07-25 09:53 | PA.RE1020
0219C899-BA37-4A9B-EF07-08DEE9C18370 | TA00048 | BOPA-ABV1020 | Bokor | BOP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOKA-ABV1020 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 16:00 | [6 empty] | 2026-07-25 09:53 | PA.RE1010
363A53C8-E0E4-43B6-EF06-08DEE9C18370 | TA00047 | BOPA-ABV980A | Bokor | BOP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOKA-ABV980A |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 16:00 | [6 empty] | 2026-07-25 09:53 | PA.RE1000
90B5E105-8889-4AED-EF05-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 10 | (BOP-A) 150-P-0115-61432P: ISOLATE LINEWORK |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 08:30 | 2026-07-30 10:00 | [6 empty] | 2026-07-25 09:53 | PA.C1000
16FBB62F-DB01-417C-EF03-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 20 | (BOP-A) 150-P-0115-61432P: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ DN 150 VALVE; V1 (Ball valve) |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 10:00 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | PA.C1010
D4FABA12-C55B-438E-EEFF-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 30 | (BOP-A) 150-P-0115-61432P: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ DN15 FLANGE; V2 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | PA.C1020
292C4124-9DA9-483E-EF01-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 40 | (BOP-A) 150-P-0115-61432P: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ DN15 FLANGE; V3 |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-30 17:30 | [6 empty] | 2026-07-25 09:53 | PA.C1030
8EE2672B-4826-4363-EEFD-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 50 | (BOP-A) 150-P-0115-61432P: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ DN80 VALVE; V4 (Ball Valve) |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-30 17:30 | 2026-07-31 10:00 | [6 empty] | 2026-07-25 09:53 | PA.C1040
B890C518-D995-4BE2-EF04-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 60 | (BOP-A) 150-P-0115-61432P: UNBOLT AND REMOVED CORRODED GASKETS AND BOLTINGS @ DN80 VALVE; V5 (Check Valve) |  | 2 | 10 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 10:00 | 2026-07-31 12:00 | [6 empty] | 2026-07-25 09:53 | PA.C1050
E495847B-0946-44E6-EEFE-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 70 | (BOP-A) 150-P-0115-61432P: INSTALL NEW GASKETS & BOLTINGS |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 13:00 | 2026-07-31 14:00 | [6 empty] | 2026-07-25 09:53 | PA.C1060
177689F0-E414-4CA0-EEFC-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 80 | (BOP-A) 150-P-0115-61432P: PERFORM BOLT TORQUING (BFJI - 7 NOS) |  | 3.5 | 17.5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-07-31 14:00 | 2026-07-31 18:00 | [6 empty] | 2026-07-25 09:53 | PA.C1070
4DBDB5D3-EDEF-4148-EF00-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 90 | (BOP-A) 150-P-0115-61432P: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 8 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 08:00 | 2026-08-01 10:30 | [6 empty] | 2026-07-25 09:53 | PA.C1080
4E560443-C96E-4858-EF02-08DEE9C18370 | TA00046 | 150-P-0115-61432P - STUDBOLT & GASKET REPLACEMENT (TASK 11) | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | DESB-C | Execution | 100 | (BOP-A) 150-P-0115-61432P: DEISOLATE LINEWORK & APPLY GREASE TO FLANGES |  | 1 | 5 |  |  | ACOOTH00 |  |  | 0 |  | 2026-08-01 10:30 | 2026-08-01 11:30 | [6 empty] | 2026-07-25 09:53 | PA.C1090
FD7DB215-FB66-4320-EEFB-08DEE9C18370 | TA00045 | BOKA-ABV9601 | Bokor | BOK-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOKA-ABV9601 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 14:30 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | KA.RE1010
480721BA-9592-430D-EEFA-08DEE9C18370 | TA00044 | BOKA-ABV9201 | Bokor | BOK-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOKA-ABV9201 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 14:30 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | KA.RE1000
76D68545-289E-4249-EEF6-08DEE9C18370 | TA00043 | HCP-5001 (HVAC Control Panel) | Bokor | BOK-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | Site inspection and system verification for BOK-A AHU |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | KA.I1200
DC138F0C-2DFD-43F2-EEF9-08DEE9C18370 | TA00043 | HCP-5001 (HVAC Control Panel) | Bokor | BOK-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Check system error for BOK-A AHU |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | KA.I1210
44C0415B-1649-40B3-EEF7-08DEE9C18370 | TA00043 | HCP-5001 (HVAC Control Panel) | Bokor | BOK-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Backup program for BOK-A AHU |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 14:00 | [6 empty] | 2026-07-25 09:53 | KA.I1220
8AD206DD-C62A-4502-EEF8-08DEE9C18370 | TA00043 | HCP-5001 (HVAC Control Panel) | Bokor | BOK-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Perform fault rectification for BOK-A AHU |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 14:00 | 2026-07-26 16:30 | [6 empty] | 2026-07-25 09:53 | KA.I1230
9EF0BFD2-8181-4A58-EEF3-08DEE9C18370 | TA00042 | Yokogawa SIS/FGS | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 10 | Perform SCS Health Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 10:30 | [6 empty] | 2026-07-25 09:53 | KA.I1100
89FBCB52-4B51-4889-EEF5-08DEE9C18370 | TA00042 | Yokogawa SIS/FGS | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | KA.I1110
BB011617-94DA-4F99-EEF2-08DEE9C18370 | TA00042 | Yokogawa SIS/FGS | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 30 | Cabinet Temperature & Humidity Measurement |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 16:00 | [6 empty] | 2026-07-25 09:53 | KA.I1120
F8365374-AA8A-40EE-EEF4-08DEE9C18370 | TA00042 | Yokogawa SIS/FGS | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 40 | General cleaning |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 16:00 | 2026-07-29 18:00 | [6 empty] | 2026-07-25 09:53 | KA.I1130
F6D348C2-134B-4815-EEF1-08DEE9C18370 | TA00041 | Yokogawa DCS | Bokor | BOK-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 10 | Perform FCS Health Check and General Cleaning at BODP-B |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 13:00 | 2026-07-29 17:30 | [6 empty] | 2026-07-25 09:53 | KA.I1000
099A6561-AEE3-4685-EEEF-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 10 | Isolate the ACB/VCB |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 08:30 | 2026-08-05 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E2500
AD04F3E1-7A93-41FB-EEF0-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 20 | Check condition of CT/VT |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 11:00 | 2026-08-05 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E2510
A6576C29-2AFF-47D0-EEED-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 30 | Record protection relay settings |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 13:00 | 2026-08-05 14:00 | [6 empty] | 2026-07-25 09:53 | KA.E2520
869A181B-F93B-4640-EEEE-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 40 | Test equipment setup with wiring connection |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 14:00 | 2026-08-05 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E2530
9486C1DD-C9B2-4E9B-EEEC-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 50 | Perform primary / secondary injection test |  | 3 | 6 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 15:30 | 2026-08-06 14:00 | [6 empty] | 2026-07-25 09:53 | KA.E2540
A1D85301-A36F-4DD6-EEE9-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 60 | Record measurement |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-06 14:00 | 2026-08-06 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E2550
5647E110-BE54-459E-EEEA-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 70 | Reset protection relay |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-06 15:30 | 2026-08-06 16:30 | [6 empty] | 2026-07-25 09:53 | KA.E2560
EBF02455-8CAA-4330-EEEB-08DEE9C18370 | TA00040 | MCC-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 80 | Normalize ACB/VCB & housekeeping |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-06 16:30 | 2026-08-07 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E2570
91EAF665-3989-49D8-EEE1-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 10 | Isolate the ACB/VCB |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 08:30 | 2026-08-03 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E2400
F4CED425-275B-450F-EEE8-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 20 | Check condition of CT/VT |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 11:00 | 2026-08-03 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E2410
C0C00206-C106-4060-EEE2-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 30 | Record protection relay settings |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 13:00 | 2026-08-03 14:00 | [6 empty] | 2026-07-25 09:53 | KA.E2420
6C3EB529-65E1-4CE3-EEE7-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 40 | Test equipment setup with wiring connection |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 14:00 | 2026-08-03 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E2430
6C1EBBE2-205F-4FF9-EEE4-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 50 | Perform primary / secondary injection test |  | 3 | 6 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 15:30 | 2026-08-04 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E2440
2AFC46F0-C766-4EE6-EEE3-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 60 | Record measurement |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 10:30 | 2026-08-04 11:30 | [6 empty] | 2026-07-25 09:53 | KA.E2450
0F15DBBF-11DD-4BE2-EEE5-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 70 | Reset protection relay |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 11:30 | 2026-08-04 13:30 | [6 empty] | 2026-07-25 09:53 | KA.E2460
7057FB42-E147-4CA2-EEE6-08DEE9C18370 | TA00039 | SG-201, ACB-201 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 80 | Normalize ACB/VCB & housekeeping |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 13:30 | 2026-08-04 16:00 | [6 empty] | 2026-07-25 09:53 | KA.E2470
101114EA-B02B-463C-EED9-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 10 | Isolate the ACB/VCB |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E2300
053BCD33-DE49-415D-EEDE-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 20 | Check condition of CT/VT |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 11:00 | 2026-08-01 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E2310
8960BD1A-A0EA-4A6B-EEDC-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 30 | Record protection relay settings |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 13:00 | 2026-08-01 14:00 | [6 empty] | 2026-07-25 09:53 | KA.E2320
7A5D8A62-A2D7-4178-EEE0-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 40 | Test equipment setup with wiring connection |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 14:00 | 2026-08-01 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E2330
E063010C-5333-431F-EEDB-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 50 | Perform primary / secondary injection test |  | 3 | 6 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 15:30 | 2026-08-02 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E2340
4F3F4499-2B05-46EC-EEDA-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 60 | Record measurement |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 10:30 | 2026-08-02 11:30 | [6 empty] | 2026-07-25 09:53 | KA.E2350
3E91CE76-25F8-4EBA-EEDD-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 70 | Reset protection relay |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 11:30 | 2026-08-02 13:30 | [6 empty] | 2026-07-25 09:53 | KA.E2360
23E2D4CC-A74C-44C8-EEDF-08DEE9C18370 | TA00038 | SG-201, ACB-200 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 80 | Normalize ACB/VCB & housekeeping |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 13:30 | 2026-08-02 16:00 | [6 empty] | 2026-07-25 09:53 | KA.E2370
3E63678F-667E-4A4B-EED3-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 10 | Isolate the ACB/VCB |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 08:30 | 2026-07-30 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E2000
EB428E91-98ED-4EE8-EED8-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 20 | Check condition of CT/VT |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 11:00 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E2010
5A933E80-B691-4C98-EED1-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 30 | Record protection relay settings |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 14:00 | [6 empty] | 2026-07-25 09:53 | KA.E2020
6E86A34A-6409-4674-EED2-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 40 | Test equipment setup with wiring connection |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 14:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E2030
8E1EADB0-7D9E-45AC-EED6-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 50 | Perform primary / secondary injection test |  | 3 | 6 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-31 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E2040
7DD4314D-F536-4C6C-EED5-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 60 | Record measurement |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 11:30 | [6 empty] | 2026-07-25 09:53 | KA.E2050
98FA5FFF-E16F-4E09-EED7-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 70 | Reset protection relay |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 11:30 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | KA.E2060
D12F8456-F325-47F4-EED4-08DEE9C18370 | TA00037 | SB-7710, Cubicle 4 | Bokor | BOK-A |  | Protection Relay | Electrical | Maintenance | PPM | Prelim | UPS PROTECTION | Execution | 80 | Normalize ACB/VCB & housekeeping |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-07-31 16:00 | [6 empty] | 2026-07-25 09:53 | KA.E2070
4A222B50-F122-4FA0-EED0-08DEE9C18370 | TA00036 | SB-7710, ACB-7710-6 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 10 | Perform power supply isolation and proof dead. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 08:30 | 2026-07-31 09:30 | [6 empty] | 2026-07-25 09:53 | KA.E1600
4F7ABAEA-A26E-42F8-EECB-08DEE9C18370 | TA00036 | SB-7710, ACB-7710-6 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 20 | Perform functional check to open/trip and close circuit. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 10:00 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E1610
BEA682BB-E24A-46EC-EECE-08DEE9C18370 | TA00036 | SB-7710, ACB-7710-6 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 30 | Check primary and secondary/arcing contact, control cable connections, arc quenching component, operating mechanism, |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 11:00 | 2026-07-31 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E1620
0C20CC99-52E5-4741-EECF-08DEE9C18370 | TA00036 | SB-7710, ACB-7710-6 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 40 | Lightly lubricate operating mechanism. Perform timing test for VBC/ACB contact and record the result. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 13:00 | 2026-07-31 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E1630
DC64B38B-46A1-4976-EECC-08DEE9C18370 | TA00036 | SB-7710, ACB-7710-6 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 50 | Clean with vacuum cleaner/clean lint free rags. Perform electrical test (contact resistance and Insulation resistance) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 15:30 | 2026-08-01 09:00 | [6 empty] | 2026-07-25 09:53 | KA.E1640
629381C3-BE55-41D0-EECD-08DEE9C18370 | TA00036 | SB-7710, ACB-7710-6 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 60 | Perform power supply normalisation. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 09:00 | 2026-08-01 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E1650
CA5EB89B-8ACD-42D9-EEC8-08DEE9C18370 | TA00035 | SB-7710, ACB-7710-2 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 10 | Perform power supply isolation and proof dead. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 14:30 | 2026-07-29 16:00 | [6 empty] | 2026-07-25 09:53 | KA.E1500
8C7EE45F-7461-4A2E-EEC6-08DEE9C18370 | TA00035 | SB-7710, ACB-7710-2 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 20 | Perform functional check to open/trip and close circuit. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 16:00 | 2026-07-29 17:00 | [6 empty] | 2026-07-25 09:53 | KA.E1510
1CB5F88B-DEEF-4963-EEC9-08DEE9C18370 | TA00035 | SB-7710, ACB-7710-2 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 30 | Check primary and secondary/arcing contact, control cable connections, arc quenching component, operating mechanism, |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 08:30 | 2026-07-30 09:30 | [6 empty] | 2026-07-25 09:53 | KA.E1520
964E07D9-8176-4617-EEC7-08DEE9C18370 | TA00035 | SB-7710, ACB-7710-2 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 40 | Lightly lubricate operating mechanism. Perform timing test for VBC/ACB contact and record the result. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 10:00 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E1530
414C170E-B401-4013-EECA-08DEE9C18370 | TA00035 | SB-7710, ACB-7710-2 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 50 | Clean with vacuum cleaner/clean lint free rags. Perform electrical test (contact resistance and Insulation resistance) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E1540
BF468A6A-1758-4F81-EEC5-08DEE9C18370 | TA00035 | SB-7710, ACB-7710-2 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 60 | Perform power supply normalisation. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-30 16:30 | [6 empty] | 2026-07-25 09:53 | KA.E1550
6B587855-77AA-461D-EEC4-08DEE9C18370 | TA00034 | SB-7710, ACB-7710-1 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 10 | Perform power supply isolation and proof dead. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 13:00 | 2026-07-28 14:00 | [6 empty] | 2026-07-25 09:53 | KA.E1400
0144BB05-E57F-4ECA-EEBF-08DEE9C18370 | TA00034 | SB-7710, ACB-7710-1 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 20 | Perform functional check to open/trip and close circuit. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 14:00 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E1410
2DADE730-A03C-4C42-EEC2-08DEE9C18370 | TA00034 | SB-7710, ACB-7710-1 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 30 | Check primary and secondary/arcing contact, control cable connections, arc quenching component, operating mechanism, |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 15:30 | 2026-07-28 16:30 | [6 empty] | 2026-07-25 09:53 | KA.E1420
9EC95ED7-A975-45D8-EEC3-08DEE9C18370 | TA00034 | SB-7710, ACB-7710-1 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 40 | Lightly lubricate operating mechanism. Perform timing test for VBC/ACB contact and record the result. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 16:30 | 2026-07-29 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E1430
345D0F6F-BF53-4367-EEC1-08DEE9C18370 | TA00034 | SB-7710, ACB-7710-1 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 50 | Clean with vacuum cleaner/clean lint free rags. Perform electrical test (contact resistance and Insulation resistance) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | KA.E1440
ADE1F7AA-D0EE-457A-EEC0-08DEE9C18370 | TA00034 | SB-7710, ACB-7710-1 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 60 | Perform power supply normalisation. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 14:30 | [6 empty] | 2026-07-25 09:53 | KA.E1450
E3AAAEAA-6298-47D7-EEBD-08DEE9C18370 | TA00033 | SG-201, ACB-201 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 10 | Perform power supply isolation and proof dead. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 10:30 | 2026-07-27 11:30 | [6 empty] | 2026-07-25 09:53 | KA.E1300
74185B8B-0A7D-4966-EEBB-08DEE9C18370 | TA00033 | SG-201, ACB-201 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 20 | Perform functional check to open/trip and close circuit. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 11:30 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | KA.E1310
FB821EE7-CE1D-4645-EEBC-08DEE9C18370 | TA00033 | SG-201, ACB-201 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 30 | Check primary and secondary/arcing contact, control cable connections, arc quenching component, operating mechanism, |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-27 14:30 | [6 empty] | 2026-07-25 09:53 | KA.E1320
5ED91A7D-3278-448F-EEBA-08DEE9C18370 | TA00033 | SG-201, ACB-201 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 40 | Lightly lubricate operating mechanism. Perform timing test for VBC/ACB contact and record the result. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 14:30 | 2026-07-27 17:00 | [6 empty] | 2026-07-25 09:53 | KA.E1330
148D9317-13A5-4958-EEBE-08DEE9C18370 | TA00033 | SG-201, ACB-201 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 50 | Clean with vacuum cleaner/clean lint free rags. Perform electrical test (contact resistance and Insulation resistance) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 08:30 | 2026-07-28 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E1340
37626A70-0050-4F73-EEB9-08DEE9C18370 | TA00033 | SG-201, ACB-201 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 60 | Perform power supply normalisation. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-28 11:00 | 2026-07-28 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E1350
9394661B-2173-4387-EEB4-08DEE9C18370 | TA00032 | SG-201, ACB-200 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 10 | Perform power supply isolation and proof dead. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 09:30 | [6 empty] | 2026-07-25 09:53 | KA.E1200
36C56D0D-B4AF-4E8D-EEB7-08DEE9C18370 | TA00032 | SG-201, ACB-200 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 20 | Perform functional check to open/trip and close circuit. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 10:00 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E1210
69B3F392-4CC3-47BA-EEB3-08DEE9C18370 | TA00032 | SG-201, ACB-200 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 30 | Check primary and secondary/arcing contact, control cable connections, arc quenching component, operating mechanism, |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E1220
9FEAF0FF-8260-4338-EEB8-08DEE9C18370 | TA00032 | SG-201, ACB-200 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 40 | Lightly lubricate operating mechanism. Perform timing test for VBC/ACB contact and record the result. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 13:00 | 2026-07-26 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E1230
3E8CAA68-A956-4EB6-EEB6-08DEE9C18370 | TA00032 | SG-201, ACB-200 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 50 | Clean with vacuum cleaner/clean lint free rags. Perform electrical test (contact resistance and Insulation resistance) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-26 15:30 | 2026-07-27 09:00 | [6 empty] | 2026-07-25 09:53 | KA.E1240
143F416E-2842-4A8A-EEB5-08DEE9C18370 | TA00032 | SG-201, ACB-200 | Bokor | BOK-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | OCEANCARE_ACB | Execution | 60 | Perform power supply normalisation. |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-27 09:00 | 2026-07-27 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E1250
D6521EE0-955A-443E-EEB2-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 10 | Isolation of circuit and verify on site |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 14:30 | 2026-08-01 16:00 | [6 empty] | 2026-07-25 09:53 | KA.E1100
722E1A9A-0011-46F0-EEAF-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 20 | Functional check on space heater |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 16:00 | 2026-08-02 09:30 | [6 empty] | 2026-07-25 09:53 | KA.E1110
B90A8409-652A-468F-EEB1-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 30 | Functional test on interlock (electrical and mechanical) and Automatic Transfer Switch (ATS) |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 10:00 | 2026-08-02 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E1120
EB49665C-8372-4746-EEA9-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 40 | Functional test on interlock within panel and inter-trip between upstream & downstream |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 15:30 | 2026-08-03 11:30 | [6 empty] | 2026-07-25 09:53 | KA.E1130
1BD075E2-30EA-4C9D-EEAB-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 50 | Physical Inspection on busbar compartment, dropper bars and cable compartments of HV Switchgear/LV MCC |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 11:30 | 2026-08-03 17:00 | [6 empty] | 2026-07-25 09:53 | KA.E1140
DA148BD3-33EC-428F-EEB0-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 60 | Cleaning for panel, auxiliary and insulation resistance test on main conductor |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 08:30 | 2026-08-04 14:00 | [6 empty] | 2026-07-25 09:53 | KA.E1150
38D63BF7-68DA-4FDF-EEAE-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 70 | Contact resistance test and torque check for busbar, dropper bars |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 14:00 | 2026-08-04 15:00 | [6 empty] | 2026-07-25 09:53 | KA.E1160
BDCFF737-9851-4DDC-EEAD-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 80 | Online partial discharge measurement (for HV switchgear) |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 15:30 | 2026-08-04 16:30 | [6 empty] | 2026-07-25 09:53 | KA.E1170
CDC6D9F1-8E32-4276-EEAC-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 90 | Reinstate equipment after maintenance |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 16:30 | 2026-08-05 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E1180
1F56B3A5-BA79-4F3A-EEAA-08DEE9C18370 | TA00031 | SB-7710 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 100 | Normalise circuit |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 10:30 | 2026-08-05 11:30 | [6 empty] | 2026-07-25 09:53 | KA.E1190
2243122B-CE63-4C89-EEA5-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 10 | Isolation of circuit and verify on site |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | KA.E1000
7D460264-80D7-43F4-EEA4-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 20 | Functional check on space heater |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 10:00 | 2026-07-29 12:00 | [6 empty] | 2026-07-25 09:53 | KA.E1010
4AC18034-1F00-4099-EEA1-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 30 | Functional test on interlock (electrical and mechanical) and Automatic Transfer Switch (ATS) |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-29 13:00 | 2026-07-30 09:00 | [6 empty] | 2026-07-25 09:53 | KA.E1020
84228467-5D9C-4742-EE9F-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 40 | Functional test on interlock within panel and inter-trip between upstream & downstream |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 14:30 | [6 empty] | 2026-07-25 09:53 | KA.E1030
E6FF7304-FB65-4C30-EEA3-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 50 | Physical Inspection on busbar compartment, dropper bars and cable compartments of HV Switchgear/LV MCC |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 14:30 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | KA.E1040
8E7BBFD6-BA0F-46FD-EEA0-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 60 | Cleaning for panel, auxiliary and insulation resistance test on main conductor |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 11:00 | 2026-07-31 16:30 | [6 empty] | 2026-07-25 09:53 | KA.E1050
E0DBE75E-E621-488F-EEA6-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 70 | Contact resistance test and torque check for busbar, dropper bars |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 16:30 | 2026-08-01 09:00 | [6 empty] | 2026-07-25 09:53 | KA.E1060
FF2AC515-36DC-4A44-EEA2-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 80 | Online partial discharge measurement (for HV switchgear) |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 09:00 | 2026-08-01 10:30 | [6 empty] | 2026-07-25 09:53 | KA.E1070
26A3A2FC-DF38-448A-EEA7-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 90 | Reinstate equipment after maintenance |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 10:30 | 2026-08-01 13:30 | [6 empty] | 2026-07-25 09:53 | KA.E1080
D08987EE-0436-4BFD-EEA8-08DEE9C18370 | TA00030 | SG-201 | Bokor | BOK-A |  | Switchgear | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Switch | Execution | 100 | Normalise circuit |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 13:30 | 2026-08-01 14:30 | [6 empty] | 2026-07-25 09:53 | KA.E1090
BC3550CA-BA30-4906-EE8D-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 10 | Perform isolation |  | 2 | 14 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2000
807B82F1-8A4D-473C-EE98-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 20 | Cold wash |  | 4 | 28 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 08:30 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2010
6FC9ED5F-FD62-44BC-EE9C-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 30 | Borescope ports removal |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-28 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2020
0DCBF0D0-5367-4CC2-EE90-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 40 | Borescope inspection |  | 6 | 18 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-28 10:30 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2030
7531723A-F848-4A57-EE8A-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 50 | Reinstate back attachments to the GT after borescope |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-29 10:00 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2040
C9E88BE8-89C3-476B-EE8E-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 60 | Inspection of GT package & compressor (fire damper, enclosure, skid etc). Lubricate VGV linkage.Inspect the exhaust ther |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-30 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2050
8DB2B725-071C-4516-EE9A-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 70 | Replace air intake filters & perform cleaning inside air intake housing. |  | 6 | 18 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-30 11:30 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2060
5AA00B81-AB8E-4935-EE8C-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 80 | Inspect & replace fuel gas filter and instrument air supply filters. |  | 3 | 9 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-31 11:00 | 2026-07-31 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2070
38A03537-CC5B-4670-EE9E-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 90 | Inspect & replace lube oil filters. |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-31 15:30 | 2026-08-01 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2080
4D6AB656-9B97-40BC-EE91-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 100 | Replace enclosure filters. |  | 2 | 6 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-01 13:30 | 2026-08-01 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2090
2D5E9E30-2D6D-4034-EE99-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 110 | Health check & calibration of PT & PS devices. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-26 14:30 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2100
1B6B8FA4-978C-48AC-EE92-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 120 | Health check & calibration of RTD, TT & TS devices. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2110
886C3707-EE89-49A9-EE88-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 130 | Health check & calibration of vibration probe and speed sensors. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-28 13:30 | 2026-07-29 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2120
5958151D-D664-4F12-EE89-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 140 | Inspection of UCP condition, controller, IO cards & lamp test. |  | 4 | 16 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-29 13:00 | 2026-07-30 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2130
AB7B3A39-E339-4887-EE96-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 150 | Inspection of field instrument, motors and junction boxes. |  | 4 | 16 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2140
1B3A51EC-3B0B-440F-EE9B-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 160 | Loop verification - speed. |  | 4 | 16 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-28 13:30 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2150
F25132D1-7D88-41D0-EE93-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 170 | Loop verification - thermocouples. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2160
22C11A49-4091-4A18-EE8B-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 180 | Loop verification - pressure, flow, level transmitter. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-26 14:30 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2170
6478F06B-8E50-44A1-EE94-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 190 | Loop verification for RTD reading & troubleshooting. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-30 14:30 | 2026-07-31 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2180
06DFA9AA-D088-49CE-EE95-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 200 | Functional test eletronic valves - EBV, VGV & EGF |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-01 16:00 | 2026-08-02 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2190
63758CC7-3140-4AB4-EE9D-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 210 | Loop verification vibration gap voltage reading & troubleshooting |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-02 13:00 | 2026-08-03 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.R2200
FD89A125-3DC0-4E87-EE8F-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 220 | Functional test fire damper |  | 3 | 9 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-03 11:30 | 2026-08-03 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2210
2B40D25F-53B5-4150-EE97-08DEE9C18370 | TA00029 | K-2410 B | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 230 | Normalise the UCP/De-isolation. |  | 3 | 21 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-04 08:30 | 2026-08-04 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.R2220
ED08F870-732F-4365-EE7F-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 10 | Perform isolation |  | 2 | 14 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1000
02039AC0-5ACA-4980-EE7C-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 20 | Cold wash |  | 4 | 28 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1010
D1EFFA76-D473-430B-EE7E-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 30 | Borescope ports removal |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 08:30 | 2026-07-27 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1020
C38981C5-BF6F-41A6-EE85-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 40 | Borescope inspection |  | 6 | 18 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 14:00 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1030
E615FDB1-5467-4308-EE76-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 50 | Reinstate back attachments to the GT after borescope |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-28 13:30 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1040
617FD5C6-228B-448E-EE73-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 60 | Inspection of GT package & compressor (fire damper, enclosure, skid etc). Lubricate VGV linkage.Inspect the exhaust ther |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-29 10:00 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1050
56EA321E-E609-483B-EE72-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 70 | Replace air intake filters & perform cleaning inside air intake housing. |  | 6 | 18 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-30 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1060
81BE3F33-6607-4C31-EE87-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 80 | Inspect & replace fuel gas filter, diesel fuel filter, dry gas seal & instrument air supply filters. |  | 3 | 9 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-30 14:30 | 2026-07-31 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1070
9E8F4971-8C1A-4DEB-EE78-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 90 | Inspect & replace lube oil filters. |  | 3 | 9 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-31 10:00 | 2026-07-31 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1080
85406447-8A60-44BE-EE83-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 100 | Replace enclosure filters. |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-31 14:00 | 2026-08-01 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1090
F369C4CB-72FE-4013-EE7D-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 110 | Health check & calibration of PT & PS devices. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1100
D6FD4777-F0AA-41EF-EE71-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 120 | Health check & calibration of RTD, TT & TS devices. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-28 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1110
DD301481-7CAE-4752-EE74-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 130 | Health check & calibration of vibration probe and speed sensors. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-28 10:30 | 2026-07-29 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1120
1158D3A4-BDDF-4CF4-EE82-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 140 | Inspection of UCP condition, controller, IO cards & lamp test. |  | 4 | 16 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-29 10:00 | 2026-07-29 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1130
13EAF53F-D06F-42DA-EE80-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 150 | Inspection of field instrument, motors and junction boxes. |  | 4 | 16 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-29 15:30 | 2026-07-30 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1140
502E482F-2352-4299-EE7B-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 160 | Loop verification - speed. |  | 4 | 16 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-28 10:30 | 2026-07-28 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1150
044741E6-6230-4CB0-EE77-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 170 | Loop verification - thermocouples. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-27 11:00 | 2026-07-28 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1160
F576EE1D-3BCC-4C21-EE86-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 180 | Loop verification - pressure, flow, level transmitter. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-27 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1170
0DBE6BCF-E3C4-4D28-EE75-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 190 | Loop verification for RTD reading & troubleshooting. |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-07-30 11:30 | 2026-07-31 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1180
A3FAFAF4-FA9E-45D6-EE81-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 200 | Functional test eletronic valves - EBV, VGV & EGF |  | 4 | 12 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-01 10:30 | 2026-08-01 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1190
66FA3177-8F45-43C9-EE7A-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 210 | Loop verification vibration gap voltage reading & troubleshooting |  | 6 | 24 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-01 16:00 | 2026-08-02 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.R1200
5A0A7622-A36D-4964-EE84-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 220 | Functional test fire damper |  | 3 | 9 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-02 15:30 | 2026-08-03 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1210
BA123CC4-82EC-40E4-EE79-08DEE9C18370 | TA00028 | K-2410 A | Bokor | BOCPP-A |  | Rotary Compressor | Rotating | Maintenance | PPM | Prelim | TTES | Execution | 230 | Normalise the UCP/De-isolation. |  | 3 | 21 |  |  | AREOTH00 |  |  | 0 |  | 2026-08-03 10:30 | 2026-08-03 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.R1220
0710962B-E106-4504-EE70-08DEE9C18370 | TA00027 | BOCPPA- 060SDV130 | Bokor | BOCPP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOCPPA-060SDV130 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.RE1020
B3848E29-3596-44B8-EE6F-08DEE9C18370 | TA00026 | BOCPPA-133SDV101 | Bokor | BOCPP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOCPPA-133SDV101 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 13:30 | 2026-07-25 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.RE1010
4D148FA1-1927-4C3F-EE6E-08DEE9C18370 | TA00025 | BOCPPA-131SDV-101 | Bokor | BOCPP-A |  | Mechanical Valve | Reliability | Maintenance | PPM | Prelim | PREVELD | Execution | 10 | Perform VPAD Inspection for BOCPPA-131SDV101 |  | 0.5 | 1 |  |  | ARLOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.RE1000
7A1B340A-6755-4C5F-EE63-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 10 | Perform logic backup before start work. |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 08:30 | 2026-07-30 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.I500
7180CE54-84C0-4450-EE6D-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 20 | Export IO list extracted from logic program and save a copy or print for reference. |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 14:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I510
949F267E-5B9C-4091-EE67-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 30 | Perform hardware checking and record |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-31 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.I520
054F53EB-09E1-42B7-EE68-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 40 | Verify any trouble triggered on the EQP Faceplate and record. |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 11:30 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I530
66719D73-27AF-4706-EE6A-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 50 | Perform physical inspection IO Status. |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.I540
34F12493-4C7D-4092-EE62-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 60 | Bypassed critical signal connected to the system |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 11:00 | 2026-08-01 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.I550
0F3C0190-1630-4814-EE64-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 70 | Perform Loop check by trigger any input (Upon request and approval) |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 13:00 | 2026-08-01 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I560
B424B020-967D-40E9-EE66-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 80 | Verify controller status |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 15:30 | 2026-08-01 16:30 | [6 empty] | 2026-07-25 09:53 | CPP.I570
F7233D5C-3958-43B4-EE6C-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 90 | Perform redundancy test |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 16:30 | 2026-08-02 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.I580
8954630F-5254-4900-EE61-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 100 | Earthing measurement |  | 0.5 | 0.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 09:00 | 2026-08-02 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.I590
495E71CF-2B79-4A12-EE6B-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 110 | EQP panel inspection (Fans, door handle, lamp) |  | 0.5 | 0.5 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 10:00 | 2026-08-02 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.I600
A21AB017-DCEB-4FBA-EE69-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 120 | Record all the reading and findings in check sheet |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 10:30 | 2026-08-02 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.I610
21AF5C6B-660C-4FB6-EE65-08DEE9C18370 | TA00024 | EQP Addressable System | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | TRISYSTEM | Execution | 130 | Housekeeping |  | 1 | 1 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 16:00 | 2026-08-02 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I620
D9ADB267-73B2-4ECD-EE5F-08DEE9C18370 | TA00023 | LCP-6230-2 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | Site inspection and system verification for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I3090
0102A9D2-F57D-4601-EE5D-08DEE9C18370 | TA00023 | LCP-6230-2 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Check system error for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.I3100
E5FD3F34-3E61-4E7C-EE5E-08DEE9C18370 | TA00023 | LCP-6230-2 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Backup program for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 11:00 | 2026-08-01 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.I3110
D946E1E5-8CDE-4971-EE60-08DEE9C18370 | TA00023 | LCP-6230-2 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Perform fault rectification for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 14:00 | 2026-08-01 16:30 | [6 empty] | 2026-07-25 09:53 | CPP.I3120
FB8985C9-6AEA-4D15-EE5A-08DEE9C18370 | TA00022 | LCP-6230-1 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 10 | Site inspection and system verification for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I400
25D1E8EA-D239-4126-EE5B-08DEE9C18370 | TA00022 | LCP-6230-1 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 20 | Check system error for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-31 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.I410
FB0B886F-2215-45D9-EE59-08DEE9C18370 | TA00022 | LCP-6230-1 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 30 | Backup program for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.I420
9D41CC99-73E8-4CE0-EE5C-08DEE9C18370 | TA00022 | LCP-6230-1 (Flare Ignition Control Panel) | Bokor | BOCPP-A |  | PLC | Instrument & Control | Maintenance | PPM | Prelim | SEDIA TEGUH | Execution | 40 | Perform fault rectification for BOCPP Flare |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 11:30 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.I430
626D0A7B-303A-42A9-EE51-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 10 | Perform database validity check tools for all SCS and made available at offshore back up disk |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I3000
8BE4EB52-2A8F-4451-EE55-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 20 | Collect System Health Check Report |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 17:30 | [6 empty] | 2026-07-25 09:53 | CPP.I3010
4C2FA747-56C2-4030-EE57-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 30 | Perform Antivirus Patch and DAT Update and scanning for PC at CCR |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.I3020
B2011DC5-43F4-42F3-EE52-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 40 | Perform Software Patch and Windows O/S Patch for PC at CCR |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-26 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.I3030
088EF45D-0484-42E8-EE58-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 50 | Perform backup of System Database SENG collected information |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 08:00 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.I3040
0C755483-4DB1-4127-EE50-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 60 | SOE(Sequence of Event) Backup. |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-27 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.I3050
FB9B8992-5174-4607-EE56-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 70 | Perform SENG Health Check and General Cleaning at CCR |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 08:00 | 2026-07-28 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.I3060
6247E02F-4B1E-4144-EE54-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 80 | Perform SCS Health Check, Hardware Inspection, Power Supply & Grounding Check at IER, BOCPPA |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 10:30 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.I3070
C4A1BC5B-1F85-4926-EE53-08DEE9C18370 | TA00021 | Yokogawa SIS/FGS | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA FGS | Execution | 90 | Perform SCS Power Supply, Cabinet Temperature & Humidity Measurement and General Cleaning at IER, BOCPPA |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 13:30 | 2026-07-28 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.I3080
D86344AC-C3A8-418F-EE4F-08DEE9C18370 | TA00020 | Yokogawa DCS | Bokor | BOCPP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 10 | Perform backup of System Database and Tuning Parameters |  | 2 | 2 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I2000
447778E4-1E50-40FD-EE4E-08DEE9C18370 | TA00020 | Yokogawa DCS | Bokor | BOCPP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 20 | Perform FCS Health Check and General Cleaning at BOCPP-A |  | 6 | 6 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-26 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.I2010
E1CB3E0B-38E2-4B6D-EE4D-08DEE9C18370 | TA00020 | Yokogawa DCS | Bokor | BOCPP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 30 | Perform HIS Health Check and General Cleaning and updating of Windows O/S Patch and Antivirus and Scan for Viruses |  | 24 | 24 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 13:00 | 2026-07-29 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.I2020
C7AED7E7-AB35-49CD-EE4C-08DEE9C18370 | TA00020 | Yokogawa DCS | Bokor | BOCPP-A |  | DCS | Instrument & Control | Maintenance | PPM | Prelim | YOKOGAWA DCS | Execution | 40 | Perform Offline Download prior PM jobs at Bokor Jacket |  | 4 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 08:00 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.I2030
9CDD9A96-64EC-4DC1-EE40-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 10 | Proess line isolation check + drain |  | 3 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 15:30 | 2026-07-27 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1500
712FA867-CF4B-43C9-EE4A-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 20 | Remove the control valve from piping + install blind flange |  | 3 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 10:30 | 2026-07-27 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1510
43996472-6BCC-456A-EE3F-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 30 | Perform pre-test |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1520
5A13656F-D059-4884-EE45-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 40 | Dismantle the valve body and actuator |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 10:30 | 2026-07-31 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1530
5C2B676D-B68B-4258-EE47-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 50 | Perform cleaning on external/ internal valve body & actuator |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 11:30 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1540
B600DEFD-397D-4151-EE3E-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 60 | Perform lapping new plug & seat ring |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1550
5D0A8BFB-4979-4461-EE46-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 70 | Replace new soft/ hard part |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-31 16:00 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1560
0E39199B-C506-4319-EE49-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 80 | Assembly valve body & actuator |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1570
9BE75868-7841-43BE-EE42-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 90 | Perform seat leak & hydro test + witness |  | 3 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 11:00 | 2026-08-01 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1580
8E3799E8-62F8-43E5-EE44-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 100 | Reinstate CV to piping |  | 2.5 | 10 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-01 15:30 | 2026-08-02 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1590
D902585F-1CAF-4A87-EE41-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 110 | Perform torque tightening |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 10:00 | 2026-08-02 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1600
8AD2BAF4-933E-4413-EE4B-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 120 | Install positioner, accessories, Install tubing & fitting |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 11:00 | 2026-08-02 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1610
7438301D-0BC4-4C3C-EE43-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 130 | Calibration & stroke test + witness |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 13:00 | 2026-08-02 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1620
27E8BDDC-410C-4B5E-EE48-08DEE9C18370 | TA00019 | 244LCV-106 (1"150#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 140 | Perform JIT Verification by PCSB QAQC |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-08-02 14:00 | 2026-08-02 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1630
2C28A84A-CA6E-4E73-EE3B-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 10 | Proess line isolation check + drain + accessories removal |  | 3.5 | 14 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1000
8F040E4A-91AF-46C8-EE36-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 20 | Remove the control valve from piping + install blind flange |  | 5 | 20 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-26 08:30 | 2026-07-26 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1010
18273D15-FFB0-4DFF-EE34-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 30 | Perform pre-test (seat test) |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-27 14:30 | 2026-07-27 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1020
D5DD9328-B526-4BE9-EE38-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 40 | Dismantle the valve body and actuator |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 09:00 | 2026-07-28 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1030
603675E8-BA83-4A7E-EE30-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 50 | Perform cleaning on external/ internal valve body & actuator |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 11:30 | 2026-07-28 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1040
06696D8E-4C43-43B8-EE37-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 60 | Perform lapping new plug & seat ring |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-28 14:30 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1050
E8E05FFE-7642-442E-EE31-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 70 | Replace new soft/ hard part |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 08:30 | 2026-07-29 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1060
BF54CBF8-1775-4C2E-EE3C-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 80 | Assembly valve body & actuator |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 11:00 | 2026-07-29 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1070
96E4B8CB-3433-47B2-EE35-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 90 | Perform seat leak & hydro test + witness |  | 3 | 12 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-29 14:00 | 2026-07-30 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1080
771906E4-97A6-44AF-EE3A-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 100 | Reinstate CV to piping |  | 2 | 8 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 09:00 | 2026-07-30 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1090
6AC5EC31-B32B-424C-EE3D-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 110 | Perform torque tightening - 2 joints |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 11:30 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1100
4F8BE1EE-511D-48DA-EE33-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 120 | Install positioner, accessories, Install tubing & fitting |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.I1110
6061CE78-83BE-4AAB-EE39-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 130 | Calibration & stroke test + witness |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 14:30 | 2026-07-30 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1120
B4B6C453-DE96-45CB-EE32-08DEE9C18370 | TA00018 | 221PCV-101 (6"600#) | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | PENAGA | Execution | 140 | Perform JIT Verification by PCSB QAQC |  | 1 | 4 |  |  | AICOTH00 |  |  | 0 |  | 2026-07-30 16:00 | 2026-07-30 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.I1130
1467B55E-D2D1-4F98-EE2A-08DEE9C18370 | TA00017 | TF-7522 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 10 | Isolate the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 08:30 | 2026-08-05 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3300
2ACA15F6-34D0-465A-EE2F-08DEE9C18370 | TA00017 | TF-7522 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 20 | Perform inspection, cleaning, IR and PI test. |  | 2.5 | 5 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 10:00 | 2026-08-05 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3310
F967A121-00E2-4981-EE2E-08DEE9C18370 | TA00017 | TF-7522 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 30 | Perform turns ratio test |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 13:30 | 2026-08-05 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3320
5C6364D9-F5CB-4E7A-EE2B-08DEE9C18370 | TA00017 | TF-7522 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 40 | Perform transformer winding (micro-ohm) resistance measurement. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-05 16:00 | 2026-08-06 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3330
DDD6BE08-AC9A-48C0-EE29-08DEE9C18370 | TA00017 | TF-7522 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 50 | Perform resistance measurement of NER (if applicable) |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-06 13:30 | 2026-08-06 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3340
D2065E37-809A-48A5-EE2D-08DEE9C18370 | TA00017 | TF-7522 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 60 | Normalize transformer |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-06 14:30 | 2026-08-06 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3350
BACDB229-B8D0-4A5B-EE2C-08DEE9C18370 | TA00017 | TF-7522 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 70 | Normalise the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-06 16:00 | 2026-08-06 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3360
DA418293-06B9-45D1-EE27-08DEE9C18370 | TA00016 | TF-7521 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 10 | Isolate the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 08:30 | 2026-08-03 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3200
70665CDE-78D0-4F07-EE28-08DEE9C18370 | TA00016 | TF-7521 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 20 | Perform inspection, cleaning, IR and PI test. |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 10:00 | 2026-08-03 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3210
3AB682B2-785A-4E7D-EE26-08DEE9C18370 | TA00016 | TF-7521 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 30 | Perform turns ratio test |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-03 15:30 | 2026-08-04 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3220
A5DE964A-54CB-4A32-EE24-08DEE9C18370 | TA00016 | TF-7521 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 40 | Perform transformer winding (micro-ohm) resistance measurement. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 09:00 | 2026-08-04 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3230
344508A4-179D-4E7E-EE25-08DEE9C18370 | TA00016 | TF-7521 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 50 | Perform resistance measurement of NER (if applicable) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 11:30 | 2026-08-04 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3240
30D1D985-FB8B-4BCE-EE23-08DEE9C18370 | TA00016 | TF-7521 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 60 | Normalize transformer |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 14:30 | 2026-08-04 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3250
F005C57D-BF41-4554-EE22-08DEE9C18370 | TA00016 | TF-7521 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 70 | Normalise the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-04 16:00 | 2026-08-04 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3260
BBA40FDD-F0E3-4558-EE1C-08DEE9C18370 | TA00015 | TF-7512 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 10 | Isolate the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3100
942F26EB-C443-4F8E-EE1F-08DEE9C18370 | TA00015 | TF-7512 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 20 | Perform inspection, cleaning, IR and PI test. |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 10:00 | 2026-08-01 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3110
D7A31EB7-47DD-4715-EE1B-08DEE9C18370 | TA00015 | TF-7512 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 30 | Perform turns ratio test |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 15:30 | 2026-08-02 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3120
3AC617BB-C18E-474E-EE21-08DEE9C18370 | TA00015 | TF-7512 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 40 | Perform transformer winding (micro-ohm) resistance measurement. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 09:00 | 2026-08-02 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3130
D2235B76-B862-40AE-EE1D-08DEE9C18370 | TA00015 | TF-7512 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 50 | Perform resistance measurement of NER (if applicable) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 11:30 | 2026-08-02 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3140
A2541971-4BC1-4FFE-EE20-08DEE9C18370 | TA00015 | TF-7512 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 60 | Normalize transformer |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 14:30 | 2026-08-02 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3150
A8C992A9-02BF-4924-EE1E-08DEE9C18370 | TA00015 | TF-7512 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 70 | Normalise the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-02 16:00 | 2026-08-02 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3160
4202C714-8168-4C76-EE16-08DEE9C18370 | TA00014 | TF-7511 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 10 | Isolate the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 08:30 | 2026-07-30 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3000
A8A0C9CF-61BE-4588-EE1A-08DEE9C18370 | TA00014 | TF-7511 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 20 | Perform inspection, cleaning, IR and PI test. |  | 4 | 8 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 10:00 | 2026-07-30 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3010
483E138B-EF8B-4FEB-EE17-08DEE9C18370 | TA00014 | TF-7511 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 30 | Perform turns ratio test |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-30 15:30 | 2026-07-31 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3020
09C4A65D-9C6A-4AC4-EE15-08DEE9C18370 | TA00014 | TF-7511 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 40 | Perform transformer winding (micro-ohm) resistance measurement. |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 09:00 | 2026-07-31 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3030
FF83C250-64B4-44BF-EE18-08DEE9C18370 | TA00014 | TF-7511 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 50 | Perform resistance measurement of NER (if applicable) |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 11:30 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.E3040
0D65B522-1249-41FC-EE19-08DEE9C18370 | TA00014 | TF-7511 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 60 | Normalize transformer |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3050
AF3BD264-4D4C-463D-EE14-08DEE9C18370 | TA00014 | TF-7511 | Bokor | BOCPP-A |  | Transformer Rectifier Unit | Electrical | Maintenance | PPM | Prelim | OCEANCARE_Transformer | Execution | 70 | Normalise the ACB/VCB |  | 1 | 2 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 16:00 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.E3060
AEB19E7F-F523-4B3D-EDFD-08DEE9C18370 | TA00012 | BT-8910 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 10 | Transfer and set-up of load bank |  | 6.5 | 13 |  |  | AEEOTH00 |  |  | 0 |  | 2026-07-31 08:30 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.E1000
B0AF4BFD-F4B0-4570-EDFE-08DEE9C18370 | TA00012 | BT-8910 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 20 | Perform electrical isolation |  | 0.5 | 1 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.E1005
249C09A2-43B0-480C-EDFB-08DEE9C18370 | TA00012 | BT-8910 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 30 | Preparation for battery discharge test & perform cleaning on battery bank Tag No. BT-8910 |  | 2 | 4 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 09:00 | 2026-08-01 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.E1010
CA6557DF-4020-491A-EDFF-08DEE9C18370 | TA00012 | BT-8910 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 40 | Perform battery discharge test on battery bank Tag no. BT-8910 |  | 5 | 10 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 11:30 | 2026-08-01 16:30 | [6 empty] | 2026-07-25 09:53 | CPP.E1020
B41BB19A-BF85-40DB-EDFC-08DEE9C18370 | TA00012 | BT-8910 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | TEGAS | Execution | 50 | Normalise electrical isolation |  | 0.5 | 1 |  |  | AEEOTH00 |  |  | 0 |  | 2026-08-01 16:30 | 2026-08-01 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.E1030
CF343A12-38B1-40A8-EDF7-08DEE9C18370 | TA00011 | 404RV-114 (1/2" MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 14:00 | 2026-07-25 14:15 | [6 empty] | 2026-07-25 09:53 | CPP.S3066
674E58F7-AE53-4D7A-EDF6-08DEE9C18370 | TA00011 | 404RV-114 (1/2" MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & cap the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 14:15 | 2026-07-25 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S3070
9BC5B9C5-2FF9-4F13-EDF9-08DEE9C18370 | TA00011 | 404RV-114 (1/2" MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 10:00 | 2026-07-26 10:15 | [6 empty] | 2026-07-25 09:53 | CPP.S3080
0F8C1801-7C11-4227-EDF8-08DEE9C18370 | TA00011 | 404RV-114 (1/2" MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Uncap & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 11:15 | [6 empty] | 2026-07-25 09:53 | CPP.S3090
C1928D8B-5A50-43A8-EDFA-08DEE9C18370 | TA00011 | 404RV-114 (1/2" MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:45 | 2026-07-26 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.S3100
2DC4B5FD-D8CB-4DED-EDF2-08DEE9C18370 | TA00010 | 404RV-131 (3/4"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:30 | 2026-07-25 13:45 | [6 empty] | 2026-07-25 09:53 | CPP.S3036
E96314EC-5055-4BE0-EDF5-08DEE9C18370 | TA00010 | 404RV-131 (3/4"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & cap the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:45 | 2026-07-25 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.S3040
5CC9E5AD-5E21-4A83-EDF3-08DEE9C18370 | TA00010 | 404RV-131 (3/4"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 09:15 | 2026-07-26 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.S3050
57A5E5F4-2BFC-446D-EDF4-08DEE9C18370 | TA00010 | 404RV-131 (3/4"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Uncap & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 10:45 | 2026-07-26 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.S3060
A9E3A029-5770-4CCE-EDF1-08DEE9C18370 | TA00010 | 404RV-131 (3/4"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:30 | 2026-07-26 11:45 | [6 empty] | 2026-07-25 09:53 | CPP.S3065
A42FF235-4754-404A-EDEE-08DEE9C18370 | TA00009 | 681RV-111 (1/2"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 10 | Perform isolation |  | 0.25 | 1.5 | 0 |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 13:15 | [6 empty] | 2026-07-25 09:53 | CPP.S3000
0B69EA5E-0303-496C-EDEC-08DEE9C18370 | TA00009 | 681RV-111 (1/2"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 20 | Removal of PSV/RV & cap the line |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:15 | 2026-07-25 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.S3010
8316B5F1-4890-458F-EDED-08DEE9C18370 | TA00009 | 681RV-111 (1/2"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 30 | Servicing / recertification of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 09:15 | [6 empty] | 2026-07-25 09:53 | CPP.S3020
1E4A821B-97E8-4286-EDEF-08DEE9C18370 | TA00009 | 681RV-111 (1/2"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 40 | Uncap & reinstall of PSV/RV |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 10:30 | 2026-07-26 10:45 | [6 empty] | 2026-07-25 09:53 | CPP.S3030
0263172D-B62D-4928-EDF0-08DEE9C18370 | TA00009 | 681RV-111 (1/2"MNPT) | Bokor | BOCPP-A |  | Pressure Safety Valve (PSV) | Static | Maintenance | PPM | Prelim | WEHAYA-S | Execution | 50 | Perform De-isolation |  | 0.25 | 1.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:15 | 2026-07-26 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.S3035
35B07F49-D775-43D4-EDE4-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 10 | Perform Physical Isolation and Drain Out Remaining Fluid |  | 4 | 40 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2200
AA15B5A2-6A18-495D-EDEA-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 20 | Mark Header Plugs to be Opened |  | 1 | 2 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-26 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2210
0A7F3075-C16B-4F08-EDDF-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 30 | Remove Header Plugs (20% - 238 plugs) |  | 4.5 | 45 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 08:30 | 2026-07-27 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2220
8BECB68F-4EE9-4CFE-EDE1-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 40 | Perform gas test |  | 1 | 2 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 08:30 | 2026-07-28 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2230
06717E4E-9565-4F4B-EDE9-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 50 | Perform Maintenance Cleaning Activities Using HPWJ |  | 4 | 24 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 10:00 | 2026-07-28 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2240
C273A26B-005D-4DED-EDE2-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 60 | Service Header Plugs |  | 4 | 16 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 11:30 | 2026-07-28 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2250
7C5B6AA8-0903-4438-EDEB-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 70 | SECT inspection at tubes internal (10% - 59 tubes) |  | 8 | 16 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2260
8C40FB1A-A3C2-4F30-EDE7-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 80 | Borescope (videoscope) inspection at tubes internal (10% - 59 tubes) |  | 8 | 16 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-30 13:00 | 2026-07-31 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2270
BF8D297F-2365-443A-EDE3-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 90 | DPI/MPI at Heat Exchanger Header Box and Nozzles |  | 2 | 4 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-01 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2280
C5440854-F541-4FF3-EDE0-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 100 | Reinstate Header Plugs and Perform Torqueing |  | 8 | 80 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 10:30 | 2026-08-03 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2290
D3FB98F8-3522-4B38-EDE5-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 110 | Perform Leak Test using N2 |  | 2 | 20 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 15:00 | 2026-08-03 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2300
4196237C-2369-46F3-EDE8-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 120 | Remove Physical Isolation and Reinstate Flange Connections |  | 6 | 60 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 08:30 | 2026-08-05 16:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2310
7E3223D0-FB36-4372-EDE6-08DEE9C18370 | TA00008 | E-2420B | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 130 | Perform JIT Verification by PCSB QAQC |  | 2 | 4 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-06 11:30 | 2026-08-06 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2320
2C2D9F3C-9336-44F2-EDDA-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 10 | Perform Physical Isolation and Drain Out Remaining Fluid |  | 4 | 40 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-26 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2000
A081A111-A8FC-4E2E-EDD5-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 20 | Mark Header Plugs to be Opened |  | 1 | 2 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 09:00 | 2026-07-26 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2010
43AB06DF-6DFA-4F12-EDD7-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 30 | Remove Header Plugs (20% - 238 plugs) |  | 4 | 40 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 11:00 | 2026-07-26 16:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2020
41E5AB1A-6FF6-4841-EDD9-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 40 | Perform gas test |  | 1 | 2 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 08:30 | 2026-07-27 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2030
FD3BABD4-58B3-473C-EDDC-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 50 | Perform Maintenance Cleaning Activities Using HPWJ |  | 4 | 24 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 10:00 | 2026-07-27 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2040
9527986F-4E03-47B2-EDD6-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 60 | Service Header Plugs |  | 4 | 16 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 11:30 | 2026-07-27 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2050
0F9FFB15-69A5-427C-EDDB-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 70 | SECT inspection at tubes internal (10% - 59 tubes) |  | 8 | 16 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 08:30 | 2026-07-29 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2060
D0258293-8FD0-4219-EDD4-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 80 | Borescope (videoscope) inspection at tubes internal (10% - 59 tubes) |  | 8 | 16 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-30 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2070
2F15017B-DE9F-40DE-EDD2-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 90 | DPI/MPI at Heat Exchanger Header Box and Nozzles |  | 2 | 4 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-31 14:30 | 2026-07-31 17:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2080
9D65CD69-AA1F-419E-EDDD-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 100 | Reinstate Header Plugs and Perform Torqueing |  | 8 | 80 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 08:30 | 2026-08-02 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2090
C93E9BE9-BF57-46F3-EDD3-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 110 | Perform Leak Test using N2 |  | 2 | 20 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 13:00 | 2026-08-03 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.S2100
7AEC6342-CF5F-47D5-EDD8-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 120 | Remove Physical Isolation and Reinstate Flange Connections |  | 6 | 60 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 08:30 | 2026-08-04 16:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2110
DE3CAB27-E4C2-4C6E-EDDE-08DEE9C18370 | TA00007 | E-2420A | Bokor | BOCPP-A |  | Shell & Tube Heat Exchanger | Static | Maintenance | PPM | Prelim | BSSB | Execution | 130 | Perform JIT Verification by PCSB QAQC |  | 2 | 4 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 16:30 | 2026-08-05 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.S2120
E5926E96-522A-4EED-EDBD-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 10 | TP-01 & 02: INSTALL POSITIVE ISOLATION FOR REMOVAL SCOPE (by SBD - same isolation points) |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1135
4EAE1EA1-D95A-40EC-EDBE-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 20 | TP-01 & 02: ASSIST OPS FOR DRAINING THE LINEWORK AFTER DEPRESSURIZE |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 15:00 | 2026-07-25 19:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1140
6CC541F3-DC8F-4479-EDC2-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 30 | TP-01 & 02: Perform N2 pre-purging by SBD (inclusive piping for TP01/02/03) |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 19:00 | 2026-07-25 23:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1141
B1223533-30C0-4CEF-EDD1-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 40 | TP-01 & 02: LINE UP HOSE & FILL UP THE LINEWORK WITH WATER & DEGREASER |  | 3 | 18 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 23:00 | 2026-07-26 02:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1146
166EBC6C-138F-47C7-EDD0-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 50 | TP-01 & 02: SOAK THE LINEWORK WITH DEGREASER OVERNIGHT |  | 4 | 1 |  |  | APROTH00 |  |  | 0 |  | 2026-07-26 02:00 | 2026-07-26 06:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1148
E5BE5081-2F69-489C-EDCD-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 60 | TP-01 & 02: DRAIN THE LINEWORK TO OPEN DRAIN (follow draining by SBD) |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1149
64A39BBC-1BDE-4B37-EDBC-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 70 | TP-01 & 02: PURGE THE LINEWORK UNTIL LEL ACCEPTED BY AGT - if required |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-27 08:00 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1150
26E91EC1-5EEA-49DC-EDC1-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 80 | TP-01 & 02: COLDCUT EXISTING PIPE (SECTIONAL REMOVAL) - 2 JOINTS |  | 16 | 144 |  |  | APROTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1160
678FAA21-DD39-4C83-EDC4-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 90 | TP-01 & TP-02: Set up isolation plug |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1161
59B16462-5E3A-4E8D-EDCF-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 100 | TP-01 & TP-02: WASHDOWN PRIOR TO HOTWORK |  | 1 | 2 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1165
FD28A57D-BD39-4DFA-EDC8-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 110 | TP-01 & 02: ISOLATE SUMP CAISSON |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-29 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1166
EE923A80-AAAA-46DE-EDC7-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 120 | TP-01 & 02: ENERGIZE PRESSURIZE HABITAT |  | 2 | 18 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 08:00 | 2026-07-30 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1168
DAAA44D3-0832-4E7A-EDC3-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 130 | TP-01 & 02: CONDUCT INSPECTION PRIOR HOTWORK |  | 2 | 18 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 10:30 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1169
E080A55C-73D9-45C2-EDBB-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 140 | TP-01: BUTT WELD PIPING (1 JOINTS) AT EXISTING PIPE & FABRICATED TEE SPOOL |  | 8 | 104 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-31 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1170
2177752F-A99A-49F4-EDCB-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 150 | TP-02: WELD FLANGES (1 JOINTS) AT EXISTING PIPE |  | 8 | 104 |  |  | APROTH00 |  |  | 0 |  | 2026-07-31 13:30 | 2026-08-01 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1200
EC664BD6-F9E4-4418-EDCE-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 160 | TP-01 & 02: PERFORM RT TP01/02 |  | 1 | 3 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 | 2026-08-02 01:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1210
264994F1-93C8-4895-EDC9-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 170 | TP-01 & 02: RT RESULT TP01/02 |  | 4 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 01:00 | 2026-08-02 05:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1220
AA620235-6B8C-4F2F-EDC5-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 180 | TP-01: PERFORM LOCALIZED HYDROTEST @ TP-01 & isolation plug removal |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1230
B867A7E6-B1A2-49D5-EDCA-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 190 | TP-02: PERFORM LOCALIZED HYDROTEST @ TP-02 & isolation plug removal |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-08-03 08:00 | 2026-08-03 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1240
7487BDF3-2E54-487D-EDBF-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 200 | TP-01 & 02: BOLT-UP AND INSTALL BALL VALVE (1 NOS) & BLIND OFF |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1250
BB0BB2E8-169A-4B73-EDC0-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 210 | TP-01 & 02: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 08:00 | 2026-08-05 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1260
779450C0-3E61-4B5B-EDBA-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 220 | TP-01 & 02: DE ISOLATE SUMP CAISSON |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 10:30 | 2026-08-05 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1280
35C65E7C-1E95-4E9F-EDC6-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 230 | TP-01 & 02: N2 Purging by SBD (inclusive piping for TP01/02/03) |  | 12 | 1 |  |  | APROTH00 |  |  | 0 |  | 2026-08-06 15:00 | 2026-08-07 04:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1284
2E21B75A-4605-4D6F-EDCC-08DEE9C18370 | TA00006 | 150-PW-43100-1C605@TP-01&TP-02 - TEAM 2 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 240 | TP-01 & 02: DESPADING ALL POSITIVE ISOLATION (by SBD - same isolation points) |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-07 08:00 | 2026-08-07 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1285
9769A70C-D936-47B5-EDB8-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 10 | TP-03: Isolate valve CVB05 (24") - Closed valve |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1009
AA86A603-8154-4567-EDAA-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 20 | TP-03: Unbolt end flange for 3ea drain valves (1") & 1 ea sampling ponit (1") at 24" line and install NPT flange |  | 2.5 | 15 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 15:30 | 2026-07-25 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1011
E8612575-7ACF-47C8-EDA5-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 30 | TP-03: ASSIST OPS TO DRAIN LINE INTO OPEN DRAIN - 4 points (concurrent with Vessel Purging) |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-07-25 20:00 | 2026-07-26 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1012
FED6A4C8-8FB5-40FE-EDA1-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 40 | TP-03: INSTALL POSITIVE ISOLATION FOR BO3 & BO4 (SPADING) after vessel purging |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-07-26 16:00 | 2026-07-26 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1013
BFE105B2-251A-41CC-EDB4-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 50 | TP-03: LINE UP HOSE AND FILL THE LINEWORK WITH WATER & DEGREASER (after spading 36" line by SBD) |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-07-27 08:00 | 2026-07-27 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1021
167CB711-626C-440C-EDB0-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 60 | TP-03: SOAK THE LINEWORK WITH DEGREASER OVERNIGHT |  | 8 | 1 |  |  | APROTH00 |  |  | 0 |  | 2026-07-27 18:00 | 2026-07-28 02:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1022
A95C4EFF-4FEB-4E1B-EDAC-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 70 | TP-03: DRAIN THE LINEWORK TO NEAREST POND (SBD) |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-28 08:00 | 2026-07-28 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1024
5FF896B0-C9BE-484D-EDA3-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 80 | TP-03: PURGE THE LINEWORK UNTIL LEL ACCEPTED BY AGT - if required |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-28 13:30 | 2026-07-28 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1025
BC6F7107-635F-4F57-EDAD-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 90 | TP-03: WASHDOWN PRIOR TO HOTWORK |  | 1 | 2 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1030
3D1DDCCB-831B-4186-EDA8-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 100 | TP-03: ISOLATE SUMP CAISSON |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1031
6C9F66FC-168D-4E55-EDB6-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 110 | TP-03: ENERGIZE PRESSURIZE HABITAT |  | 2 | 18 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 08:00 | 2026-07-29 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1035
C40911ED-9891-42C4-EDB7-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 120 | TP-03: CONDUCT INSPECTION PRIOR HOTWORK |  | 2 | 18 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 10:30 | 2026-07-29 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1036
A23E66BA-AF75-4F31-EDA7-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 130 | TP-03: INSTALL & WELD 6" WELDOLET FLANGE (1 JOINT) |  | 8 | 104 |  |  | APROTH00 |  |  | 0 |  | 2026-07-29 13:30 | 2026-07-30 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1040
CF9FB031-1A0D-41A8-EDA9-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 140 | TP-03: PERFORM NDT (DPI) |  | 1 | 3 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 13:30 | 2026-07-30 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1050
B549CF21-7442-4F60-EDA6-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 150 | TP03: PERFORM LOCALISED HYDROTEST TP-03 |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-07-30 14:30 | 2026-07-30 21:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1070
4BBD508E-7FA5-4BB4-EDAF-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 160 | TP-03: COLD TAPPING FOR 30" X 6" SCH 10S WELDOLET |  | 8 | 56 |  |  | APROTH00 |  |  | 0 |  | 2026-07-31 08:00 | 2026-07-31 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1080
2EB7F3FD-DBB7-405F-EDB2-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 170 | TP-03: INSTALL & WELD 45 DEG 6" ELBOW PIPE SPOOL (1 JOINT) |  | 8 | 104 |  |  | APROTH00 |  |  | 0 |  | 2026-08-01 08:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1090
D64C5204-F332-42A4-EDAB-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 180 | TP-03: PERFORM RT |  | 1 | 3 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 | 2026-08-02 01:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1100
7CD2D66F-5905-41ED-EDA2-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 190 | TP-03: ANALYZE RT RESULT |  | 4 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 01:00 | 2026-08-02 05:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1110
60DC80D8-D38B-422A-EDA0-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 200 | TP-03: PERFORM HYDROTEST 45 DEG 6" ELBOW (@ SPOOL 6 & 7) |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1111
CFD5D97B-811D-476E-EDAE-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 210 | TP-03: BOLT-UP AND INSTALL BALL VALVE (1 NOS) & BLIND OFF |  | 8 | 48 |  |  | APROTH00 |  |  | 0 |  | 2026-08-03 08:00 | 2026-08-03 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1120
B4EFF904-AB91-4CFB-EDB3-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 220 | TP-03: INSTALL & WELD PIPE SUPPORT PS-01 |  | 8 | 64 |  |  | APROTH00 |  |  | 0 |  | 2026-08-04 08:00 | 2026-08-04 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1130
D2965FEA-076D-4067-EDA4-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 230 | TP-03: PERFORM JIT VERIFICATION BY PCSB QAQC |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 08:00 | 2026-08-05 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.F1290
070D3401-4765-4633-EDB1-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 240 | TP-03: DE ISOLATE SUMP CAISSON |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 10:30 | 2026-08-05 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1310
9C7FC790-6B1B-4D8B-EDB9-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 250 | TP-03: Reinstate back end flange for 3ea drain valves (1") & 1 ea sampling ponit (1") at 24" line |  | 2 | 12 |  |  | APROTH00 |  |  | 0 |  | 2026-08-05 16:00 | 2026-08-05 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1311
487BAD16-F8C8-49DC-ED9F-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 260 | TP-03: N2 Purging by SBD (inclusive pipings for TP01/02/03) |  | 12 | 1 |  |  | APROTH00 |  |  | 0 |  | 2026-08-06 15:00 | 2026-08-07 04:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1312
DEF7C18E-DBCA-4F76-EDB5-08DEE9C18370 | TA00005 | 750-P-10010-13411-NN@TP-03 (NEAR V1010) - TEAM 1 | Bokor | BOCPP-A |  | Piping | Project | Maintenance | PPM | Prelim | DESB-F | Execution | 270 | TP-03: DESPADING ALL POSITIVE ISOLATION (CVB05, B03 & B04) |  | 4 | 24 |  |  | APROTH00 |  |  | 0 |  | 2026-08-07 08:00 | 2026-08-07 12:00 | [6 empty] | 2026-07-25 09:53 | CPP.F1315
2A260016-F470-40E1-ED7A-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 10 | Isolation incoming & outlet valves (closed valves) |  | 2 | 14 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 13:00 | 2026-07-25 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1000
A1DCFDE4-8801-464C-ED8B-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 20 | Transfer of remaining crude oil from V1010 to open drain hazardous using wilden pump |  | 4 | 52 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 15:00 | 2026-07-25 19:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1010
A1D048EF-9EFD-499E-ED93-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 30 | Perform N2 pre-purging (cover DESB scope for TP01/02/03) |  | 4 | 36 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 19:00 | 2026-07-25 23:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1020
7907EBDE-CCD0-42B7-ED80-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 40 | Fill up water and pump in degreaser (including preparation) |  | 3 | 45 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-25 23:00 | 2026-07-26 02:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1030
E6549DB1-DFB4-4458-ED9E-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 50 | Soaking |  | 4 | 1 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 02:00 | 2026-07-26 06:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1040
FFFA09A6-7880-4A22-ED7F-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 60 | Drain out the waste water with degreaser |  | 4 | 60 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 08:00 | 2026-07-26 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1050
B8133C30-3961-4C07-ED9C-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 70 | Gas test < 10% LEL |  | 0.5 | 2.5 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 13:30 | 2026-07-26 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1060
FB87651C-A21C-4522-ED98-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 80 | Spading installation, swing/install blind, drop spool - Team A: 1) 36" - 1jt, 2) 8" - 2jts, 3)6"-7jts |  | 10 | 120 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 14:00 | 2026-07-27 04:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1070
443A86C3-27A3-41D6-ED9A-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 90 | Spading installation, swing/install blind, drop spool - Team B: 1) 30" - 1jt, 2) 20" - 1jt, 3)12"-2jts, 4)6"-2jts |  | 10 | 110 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 14:00 | 2026-07-27 04:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1071
5992F001-7D62-43D0-ED83-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 100 | Spading installation, swing/install blind, drop spool - Team C: 1) 3" - 41jts, 2) 2" - 2jts, 3)4"-10jts |  | 10 | 60 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-26 14:00 | 2026-07-27 04:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1072
BB0939E1-96C8-4A1B-ED95-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 110 | Opening of vessel manhole V1010 3 NOS (24" x 3jts) |  | 4 | 76 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 08:00 | 2026-07-27 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1080
9C5D0B77-DFB9-41CE-ED81-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 120 | Ventilation installation and initial ventilation |  | 4 | 60 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 13:30 | 2026-07-27 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1090
4A47C3E2-A22D-43EA-ED89-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 130 | Initial non-intrusive vessel cleaning and ventilation (from external vessel) |  | 16 | 272 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-27 20:00 | 2026-07-28 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1100
058C69EF-9736-424B-ED91-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 140 | Gas free before entry |  | 0.5 | 3 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 20:00 | 2026-07-28 20:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1110
24D4CF2A-AD83-4DF0-ED9D-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 150 | Internal vessel cleaning -water jetting and sludge draining |  | 60 | 780 |  |  | ASEOTH00 |  |  | 0 |  | 2026-07-28 20:30 | 2026-08-01 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1120
BFAD394A-9882-4947-ED8E-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 160 | Break flange at piping from V1010 to pump P-4210 A/B/C and flush the pipe (14" x 2jts & 8" x 6jts) |  | 8 | 56 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 02:00 | 2026-08-01 14:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1130
992BF6AF-E5C4-49C0-ED8A-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 170 | Internal vessel inspection and internal photo taking (MCI) |  | 4 | 32 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 14:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1140
FBEDEDFE-925E-4E23-ED87-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 180 | Transferring remaining sludge from temporary storage to drums using wilden pumps (3 temp. storages) |  | 4 | 64 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 14:00 | 2026-08-01 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1150
CB1C3F2C-1224-4AB3-ED9B-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 190 | Dismantle the temporary storage (pool below vessel) |  | 8 | 120 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-01 20:00 | 2026-08-02 06:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1151
D1FBE833-F9CA-462E-ED7C-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 200 | Gas test < 0% LEL |  | 1 | 6 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 08:00 | 2026-08-02 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1160
43AEEE00-0E51-465A-ED97-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 210 | Surface preparation for sand weir - excavate to carbon steel layer before fit up - 426mm x 2 jts (fillet groove weld) |  | 4 | 40 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 09:30 | 2026-08-02 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1170
4F1960C4-4D7D-421C-ED8F-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 220 | Peform DPI and PMI on the surface preparation |  | 1 | 10 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 14:30 | 2026-08-02 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1171
09C1B7A4-2336-45B5-ED7D-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 230 | Fit up of 10mm extend sand weir plate - 3 jts |  | 2 | 20 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-02 16:00 | 2026-08-02 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1172
89E041E0-548C-4EA0-ED86-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 240 | Welding of extend sand weir plate - 3jts |  | 6 | 60 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 08:00 | 2026-08-03 16:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1173
279B7748-6D65-4905-ED99-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 250 | Fit up and weld 5pcs 10mm stiffener plate (fillet weld both side) - 460mm x4jts + 910mm x 2jts + 315mm x 2jts = 4920mm |  | 5 | 50 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-03 16:00 | 2026-08-04 11:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1174
7A681F2B-B4A9-4942-ED88-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 260 | Perform weld build up on pin hole for N13 - surface prep (excavate), perform DPI & PMI, and weld build up |  | 2 | 20 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 11:30 | 2026-08-04 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1180
D144AED4-CB26-4D61-ED92-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 270 | Perform weld build up on pin hole for N22 - surface prep (excavate), perform DPI & PMI, and weld build up |  | 2 | 20 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 11:30 | 2026-08-04 14:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1181
8E0064B9-D33A-43BA-ED82-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 280 | Perform visual inspection and NDT (DPI/UT) |  | 3 | 9 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 14:30 | 2026-08-04 18:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1190
7A9BE31F-5BCD-4B64-ED7B-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 290 | Remove ventilation and box up manhole V1010 |  | 12 | 132 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-04 20:00 | 2026-08-05 13:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1200
91C2A061-6703-446A-ED94-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 300 | Remove spading, blind and reinstate back the spool - Team A: 1) 36" - 1jt, 2) 8" - 2jts, 3)6"-7jts |  | 12 | 132 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 13:30 | 2026-08-06 06:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1210
D3E74FBE-DC64-4A07-ED84-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 310 | Remove spading, blind and reinstate back the spool - Team B: 1) 30" - 1jt, 2) 20" - 1jt, 3)12"-2jts, 4)6"-2jts |  | 12 | 132 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 13:30 | 2026-08-06 06:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1211
D0857C99-B54C-4A40-ED8C-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 320 | Remove spading, blind and reinstate back the spool - Team C: 1) 3" - 41jts, 2) 2" - 2jts, 3)4"-10jts |  | 12 | 84 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-05 13:30 | 2026-08-06 06:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1212
7CDBEEF5-1FEF-4EFA-ED7E-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 330 | Perform JIT Verification by PCSB QAQC |  | 3 | 18 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-06 11:00 | 2026-08-06 15:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1220
E79DDC6F-1135-438A-ED8D-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 340 | N2 purging to lower oxygen contain |  | 12 | 132 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-06 15:00 | 2026-08-07 04:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1230
B17643E8-6BD8-4E8D-ED85-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 350 | N2 leak test |  | 12 | 132 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-06 15:00 | 2026-08-07 04:00 | [6 empty] | 2026-07-25 09:53 | CPP.S1240
D7B179F6-0D15-43C8-ED90-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 360 | De-isolate incoming valve and outlet valves |  | 4 | 28 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-07 04:00 | 2026-08-07 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1250
D05B718B-1E75-4099-ED96-08DEE9C18370 | TA00004 | V-1010 | Bokor | BOCPP-A |  | Vessel | Static | Maintenance | PPM | Prelim | SBD | Execution | 370 | Hand over to Operation/PIC Normalization |  | 2 | 14 |  |  | ASEOTH00 |  |  | 0 |  | 2026-08-07 10:30 | 2026-08-07 12:30 | [6 empty] | 2026-07-25 09:53 | CPP.S1260
7CF10761-C817-46D0-ED79-08DEE9C18370 | TA00003 | SHUTDOWN SEQUENCE BAKAU | Bakau | BKP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 10 | Initiate ESD and Peform ESD Check |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 10:00 | 2026-07-25 10:30 | [6 empty] | 2026-07-25 09:53 | BKA.O1010
533453A1-3E67-47EA-ED78-08DEE9C18370 | TA00003 | SHUTDOWN SEQUENCE BAKAU | Bakau | BKP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 20 | Perform LOTO |  | 2.5 | 25 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 10:30 | 2026-07-25 13:00 | [6 empty] | 2026-07-25 09:53 | BKA.O1020
1CE10155-A4C3-4E4F-ED76-08DEE9C18370 | TA00002 | SHUTDOWN SEQUENCE BETTY | Betty | BEDP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 10 | Initiate ESD and Peform ESD Check |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 09:00 | 2026-07-25 09:30 | [6 empty] | 2026-07-25 09:53 | BPA.O1010
4E3F08EA-8483-41E3-ED77-08DEE9C18370 | TA00002 | SHUTDOWN SEQUENCE BETTY | Betty | BEDP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 20 | Perform LOTO |  | 3.5 | 35 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 09:30 | 2026-07-25 13:00 | [6 empty] | 2026-07-25 09:53 | BPA.O1020
8E12FC86-3E81-42F0-ED6F-08DEE9C18370 | TA00001 | SHUTDOWN SEQUENCE BOKOR | Bokor | BOCPP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 10 | Initiate ESD and Peform ESD Check |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 08:30 | 2026-07-25 09:00 | [6 empty] | 2026-07-25 09:53 | CPP.O1000
E567430B-08E4-42AD-ED71-08DEE9C18370 | TA00001 | SHUTDOWN SEQUENCE BOKOR | Bokor | BOCPP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 20 | Perform LOTO |  | 4 | 40 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 09:00 | 2026-07-25 13:00 | [6 empty] | 2026-07-25 09:53 | CPP.O1070
6735750C-A99B-47A9-ED73-08DEE9C18370 | TA00001 | SHUTDOWN SEQUENCE BOKOR | Bokor | BOCPP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 30 | Reset and Energize Station and Run Utilies |  | 2 | 20 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 09:00 | 2026-07-25 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.O1020
65CB0119-6B25-49B2-ED75-08DEE9C18370 | TA00001 | SHUTDOWN SEQUENCE BOKOR | Bokor | BOCPP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 40 | Online Nitrogen Package to support GLC-A |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 09:00 | 2026-07-25 09:30 | [6 empty] | 2026-07-25 09:53 | CPP.O1030
A85C03A1-2DA5-4784-ED74-08DEE9C18370 | TA00001 | SHUTDOWN SEQUENCE BOKOR | Bokor | BOCPP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 50 | Isolate LPG back up supply to Flare |  | 1 | 10 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 09:30 | 2026-07-25 10:30 | [6 empty] | 2026-07-25 09:53 | CPP.O1040
B4FEF78E-3D9D-46B0-ED70-08DEE9C18370 | TA00001 | SHUTDOWN SEQUENCE BOKOR | Bokor | BOCPP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 60 | Open 677SDV-101 and continuos supply diesel to EDG Tank |  | 0.5 | 5 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 10:30 | 2026-07-25 11:00 | [6 empty] | 2026-07-25 09:53 | CPP.O1050
7A1FE79C-8F49-462F-ED72-08DEE9C18370 | TA00001 | SHUTDOWN SEQUENCE BOKOR | Bokor | BOCPP-A |  | Shutdown | Operation/Process | Maintenance | PPM | Prelim | Operation | Shutdown | 70 | Extinguish Flare (to manually purge using N2 bottle if required) |  | 2 | 20 |  |  | AOPOTH00 |  |  | 0 |  | 2026-07-25 11:00 | 2026-07-25 13:00 | [6 empty] | 2026-07-25 09:53 | CPP.O1060
Applied filters: EventCode is BOBELATA2026 OPUCode is SKA