## Export
ID | WorklistID | EquipmentNo | Loc | SubLoc1 | SubLoc2 | EqptType | Discipline | Work Category | Job Category | Request | Worklist Reference 1 | Phase | TaskNo | Task | TaskNote | Dur (Hrs) | Weightage | Group | WCSCode | ActivityCode | SubTasklistCode | SubTasklistType | Total SubTask | For BoxUp | PlanStart | PlanFinish | BL1Start | BL1Finish | BL2Start | BL2Finish | ForecastStart | ForecastEnd | Approved Date | Reference 1 | Reference 2 | Reference 3 | Reference 4
4BF992CE-5952-44A7-3EA3-08DCBCFE539A | TA00294 | JB-7702/JB-7771 | Bokor | BODP-F |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Identify the circuit and equipment tag number | A12210 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 08:30 | 2024-08-31 11:00 | [6 empty] | 2024-08-15 15:57
8E678B92-85DB-4DAD-3EA4-08DCBCFE539A | TA00294 | JB-7702/JB-7771 | Bokor | BODP-F |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | ACP/AP to perform discharge test and prove dead | A12220 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 11:00 | 2024-08-31 14:30 | [6 empty] | 2024-08-15 15:57
C0628F2B-E854-4FEC-3EA0-08DCBCFE539A | TA00294 | JB-7702/JB-7771 | Bokor | BODP-F |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Disconnect power cable at both end of location | A12230 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 14:30 | 2024-08-31 17:00 | [6 empty] | 2024-08-15 15:57
B3B60A12-E635-4BEB-3EA2-08DCBCFE539A | TA00294 | JB-7702/JB-7771 | Bokor | BODP-F |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | To perform continuity test for the cable and insulation resistance test | A12240 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 08:00 | 2024-09-01 10:30 | [6 empty] | 2024-08-15 15:57
F812B0D8-7DC7-45A4-3EA1-08DCBCFE539A | TA00294 | JB-7702/JB-7771 | Bokor | BODP-F |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | HV cable jointing using hot shrink method | A12250 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 10:30 | 2024-09-01 14:00 | [6 empty] | 2024-08-15 15:57
DFDE8EB0-3CA4-4AE0-3E9B-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 50-PG-124-61430: INSTALL POSITIVE ISOLATION | CONS(1)_03.1000 | 3 | 6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:57
7FE2ECB6-C24C-40BB-3E9C-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 50-PG-124-61430: CUT AND REMOVE EXISTING SPOOL (FLANGE TO FLANGE REPLACEMENT) | CONS(1)_03.1020 | 11 | 77 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:57
3F73E004-9CBF-48EA-3E9F-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 50-PG-124-61430: REMOVE EXISTING PIPE SUPPORT | CONS(1)_03.1040 | 14 | 126 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:57
B429A383-3FB1-4503-3E97-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 50-PG-124-61430: INSTALL NEW SPOOL (with BONLOK) | CONS(1)_03.1060 | 6 | 66 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:57
C7A7A5AF-001D-415F-3E99-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 50 | 50-PG-124-61430: INSTALL NEW PIPE SUPPORT | CONS(1)_03.1080 | 14 | 140 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:57
291DF0DD-84A8-426E-3E9A-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 60 | 50-PG-124-61430: HYDROTEST LINEWORK | CONS(1)_03.1100 | 8 | 32 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:57
65D8B498-E562-47FE-3E98-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 70 | 50-PG-124-61430: INSTALL NEW I-ROD & U-BOLT | CONS(1)_03.1160 | 7 | 14 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:57
A5E62449-7F3F-475F-3E9E-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 80 | 50-PG-124-61430: REPLACE CORRODED BOLTINGS | CONS(1)_03.1180 | 5 | 10 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:57
1CAA093E-1AB5-4074-3E9D-08DCBCFE539A | TA00293 | 50-PG-124-61430 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 90 | 50-PG-124-61430: REMOVE POSITIVE ISOLATION | CONS(1)_03.1200 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 11:00 | [6 empty] | 2024-08-15 15:57
BE5AD5A2-7DB4-4025-3E93-08DCBCFE539A | TA00292 | BT7810 | Bokor | BOCPP-A |  | Battery Limit | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Isolate battery breaker | A11010 | 1 | 3 | 0 |  | AEESER06 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:57
59B04CAB-377D-4E68-3E96-08DCBCFE539A | TA00292 | BT7810 | Bokor | BOCPP-A |  | Battery Limit | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Dismantle existing battery bank and put at designated area and repacking inside wooden box | A11020 | 16 | 16 | 0 |  | AEESER06 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:57
2C0EB904-FAE9-4408-3E94-08DCBCFE539A | TA00292 | BT7810 | Bokor | BOCPP-A |  | Battery Limit | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform installation for new battery bank | A11030 | 16 | 48 | 0 |  | AEESER06 |  |  | 0 |  | 2024-08-27 14:00 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:57
CFABDCF5-EB25-4A36-3E92-08DCBCFE539A | TA00292 | BT7810 | Bokor | BOCPP-A |  | Battery Limit | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform link termination and connect cable interconnection cable for new battery bank | A11040 | 5 | 5 | 0 |  | AEESER06 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-30 10:00 | [6 empty] | 2024-08-15 15:57
749AE067-D0A1-4B0F-3E95-08DCBCFE539A | TA00292 | BT7810 | Bokor | BOCPP-A |  | Battery Limit | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Measure initial voltage per cell for new battery bank | A11050 | 3 | 9 | 0 |  | AEESER06 |  |  | 0 |  | 2024-08-30 10:00 | 2024-08-30 14:00 | [6 empty] | 2024-08-15 15:57
05A926F3-6BF7-4233-3E91-08DCBCFE539A | TA00292 | BT7810 | Bokor | BOCPP-A |  | Battery Limit | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform cable charging termination for new battery | A11060 | 8 | 24 | 0 |  | AEESER06 |  |  | 0 |  | 2024-08-30 14:00 | 2024-08-31 14:00 | [6 empty] | 2024-08-15 15:57
26A9AD37-A0B8-47AF-3E8D-08DCBCFE539A | TA00291 | TF-309 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12740 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 14:00 | [6 empty] | 2024-08-15 15:57
1104D01C-5897-41C4-3E8E-08DCBCFE539A | TA00291 | TF-309 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12750 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 14:00 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:57
292C866F-3F65-4E36-3E8F-08DCBCFE539A | TA00291 | TF-309 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12760 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:57
B92FD9E5-AFCB-4F65-3E90-08DCBCFE539A | TA00291 | TF-309 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12770 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:57
14D75778-300A-4712-3E8C-08DCBCFE539A | TA00290 | TF-306 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12700 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 09:00 | [6 empty] | 2024-08-15 15:57
6D332485-89A1-469F-3E8B-08DCBCFE539A | TA00290 | TF-306 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12710 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:57
E6D156C4-997E-4FF2-3E8A-08DCBCFE539A | TA00290 | TF-306 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12720 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:57
BD6B6183-B1B3-451F-3E89-08DCBCFE539A | TA00290 | TF-306 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12730 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:57
545EAEC1-CD02-4E05-3E88-08DCBCFE539A | TA00289 | TF7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12660 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:57
FA19A3F6-898C-44E2-3E87-08DCBCFE539A | TA00289 | TF7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12670 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 14:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:57
C249EC77-1CE5-4D58-3E86-08DCBCFE539A | TA00289 | TF7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12680 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-27 16:00 | [6 empty] | 2024-08-15 15:57
5B57D746-A4A3-4782-3E85-08DCBCFE539A | TA00289 | TF7503 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12690 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 16:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:57
47CA249F-1110-42BF-3E82-08DCBCFE539A | TA00288 | TF-217 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12620 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 09:00 | [6 empty] | 2024-08-15 15:57
A8E67891-AC3E-4C7C-3E84-08DCBCFE539A | TA00288 | TF-217 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12630 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 09:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:57
42C5266A-A3AB-4B60-3E81-08DCBCFE539A | TA00288 | TF-217 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12640 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:57
76468145-0AC5-4E74-3E83-08DCBCFE539A | TA00288 | TF-217 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12650 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:57
05E6D7C6-780A-402E-3E80-08DCBCFE539A | TA00287 | TF7522 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12580 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 10:00 | 2024-08-30 11:00 | [6 empty] | 2024-08-15 15:57
E2259E36-F2AB-4EF1-3E7E-08DCBCFE539A | TA00287 | TF7522 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12590 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-30 12:00 | [6 empty] | 2024-08-15 15:57
D4B61042-E63D-44A7-3E7D-08DCBCFE539A | TA00287 | TF7522 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12600 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 13:00 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:57
F29D9B25-532C-47F9-3E7F-08DCBCFE539A | TA00287 | TF7522 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12610 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-30 17:00 | [6 empty] | 2024-08-15 15:57
6643244F-4F32-44F0-3E7B-08DCBCFE539A | TA00286 | TF7521 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12540 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:57
B8957AE8-F1EA-41B9-3E7A-08DCBCFE539A | TA00286 | TF7521 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12550 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:57
F2EBAE48-2C9D-4FF3-3E79-08DCBCFE539A | TA00286 | TF7521 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12560 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:57
FC1D5E3D-C629-4958-3E7C-08DCBCFE539A | TA00286 | TF7521 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12570 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 10:00 | [6 empty] | 2024-08-15 15:57
26DC853A-1C53-49A2-3E75-08DCBCFE539A | TA00285 | TF7512 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12500 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-28 16:00 | [6 empty] | 2024-08-15 15:57
271A7CC3-0DA3-4247-3E78-08DCBCFE539A | TA00285 | TF7512 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12510 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 16:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:57
B24584A2-F412-4CBB-3E77-08DCBCFE539A | TA00285 | TF7512 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12520 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:57
7DB2D821-30E0-47BB-3E76-08DCBCFE539A | TA00285 | TF7512 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12530 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:57
621AEAEB-0927-490F-3E73-08DCBCFE539A | TA00284 | TF-7511 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform insulation resistance test (cable and transformer) | A12460 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:57
36C026D5-C2B0-497D-3E72-08DCBCFE539A | TA00284 | TF-7511 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform winding resistance test (cable and transformer) | A12470 | 1 | 3 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 10:00 | [6 empty] | 2024-08-15 15:57
1D2F7640-514E-48A3-3E74-08DCBCFE539A | TA00284 | TF-7511 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform polarization index test (cable) | A12480 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 10:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:57
02EC2957-D348-4E4A-3E71-08DCBCFE539A | TA00284 | TF-7511 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Improvement of genral contion of transformer | A12490 | 2 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:57
94590129-03C3-4099-3E6D-08DCBCFE539A | TA00283 | SB-7731 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | To perform Circuit Breaker Insulation Resistance Test | A12420 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 13:00 | 2024-09-01 14:00 | [6 empty] | 2024-08-15 15:57
C978B470-3B62-4FAA-3E70-08DCBCFE539A | TA00283 | SB-7731 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform Circuit Breaker Timing Test | A12430 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 14:00 | 2024-09-01 15:00 | [6 empty] | 2024-08-15 15:57
D82C39B2-97E0-4D20-3E6E-08DCBCFE539A | TA00283 | SB-7731 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform Vacuum Integrity Test | A12440 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 15:00 | 2024-09-01 16:00 | [6 empty] | 2024-08-15 15:57
2F6D6CF3-A5AF-4A78-3E6F-08DCBCFE539A | TA00283 | SB-7731 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | To perform Circuit Breaker Contact Resistance Test | A12450 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 16:00 | 2024-09-01 17:00 | [6 empty] | 2024-08-15 15:57
27B99025-A24F-47FC-3E69-08DCBCFE539A | TA00282 | SB-7730 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | To perform Circuit Breaker Insulation Resistance Test | A12380 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 13:00 | 2024-09-01 14:00 | [6 empty] | 2024-08-15 15:57
9F1DBE89-9E31-458A-3E6C-08DCBCFE539A | TA00282 | SB-7730 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform Circuit Breaker Timing Test | A12390 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 14:00 | 2024-09-01 15:00 | [6 empty] | 2024-08-15 15:57
9FDDD9EA-53BE-4BA6-3E6A-08DCBCFE539A | TA00282 | SB-7730 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform Vacuum Integrity Test | A12400 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 15:00 | 2024-09-01 16:00 | [6 empty] | 2024-08-15 15:57
B4FAF4C0-95C3-4E79-3E6B-08DCBCFE539A | TA00282 | SB-7730 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | To perform Circuit Breaker Contact Resistance Test | A12410 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 16:00 | 2024-09-01 17:00 | [6 empty] | 2024-08-15 15:57
B8866CAC-3E14-4988-3E68-08DCBCFE539A | TA00281 | SB-7700 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | To perform Circuit Breaker Insulation Resistance Test | A12340 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:57
0885AF0E-FBDA-4351-3E65-08DCBCFE539A | TA00281 | SB-7700 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform Circuit Breaker Timing Test | A12350 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:57
8793FAD7-80BB-40FB-3E66-08DCBCFE539A | TA00281 | SB-7700 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform Vacuum Integrity Test | A12360 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:57
E1AD2CDD-A40F-495D-3E67-08DCBCFE539A | TA00281 | SB-7700 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | To perform Circuit Breaker Contact Resistance Test | A12370 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:57
18F1AFAE-40E9-48D8-3E64-08DCBCFE539A | TA00280 | SG-7500 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | To perform Circuit Breaker Insulation Resistance Test | A12300 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:57
EB1D8314-7F1E-4F87-3E63-08DCBCFE539A | TA00280 | SG-7500 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform Circuit Breaker Timing Test | A12310 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:57
DF9ED4E0-8529-466E-3E62-08DCBCFE539A | TA00280 | SG-7500 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform Vacuum Integrity Test | A12320 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:57
CE7B6252-093A-4684-3E61-08DCBCFE539A | TA00280 | SG-7500 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | To perform Circuit Breaker Contact Resistance Test | A12330 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:57
B9E6ECE1-8C70-4ED4-3E60-08DCBCFE539A | TA00279 | SB-7710 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | To perform Circuit Breaker Insulation Resistance Test | A12260 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 09:00 | [6 empty] | 2024-08-15 15:57
24DB173C-45D8-4DDD-3E5E-08DCBCFE539A | TA00279 | SB-7710 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform Circuit Breaker Timing Test | A12270 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 09:00 | 2024-08-30 10:00 | [6 empty] | 2024-08-15 15:57
11F97508-323F-42A3-3E5F-08DCBCFE539A | TA00279 | SB-7710 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform Vacuum Integrity Test | A12280 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 10:00 | 2024-08-30 11:00 | [6 empty] | 2024-08-15 15:57
86F62951-1C82-4130-3E5D-08DCBCFE539A | TA00279 | SB-7710 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | To perform Circuit Breaker Contact Resistance Test | A12290 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-30 12:00 | [6 empty] | 2024-08-15 15:57
F2B7D9C7-5BAF-4FC1-3E5A-08DCBCFE539A | TA00278 | SB-7731 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Electrical Isolation by PCSB competence personal | A12130 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 08:00 | 2024-09-01 09:00 | [6 empty] | 2024-08-15 15:57
97706918-76DB-4502-3E5C-08DCBCFE539A | TA00278 | SB-7731 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform protection relay testing, calibration and servicing for 1 unit | A12140 | 6 | 12 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 09:00 | 2024-09-01 16:00 | [6 empty] | 2024-08-15 15:57
23667069-2EC2-40E7-3E5B-08DCBCFE539A | TA00278 | SB-7731 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Circuit normalization and de-isolation | A12150 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 16:00 | 2024-09-01 17:00 | [6 empty] | 2024-08-15 15:57
60C5FA1B-6B6D-4282-3E59-08DCBCFE539A | TA00277 | SB7730 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Electrical Isolation by PCSB competence personal | A12100 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 08:00 | 2024-09-01 09:00 | [6 empty] | 2024-08-15 15:57
45BE9207-C4FE-42C3-3E58-08DCBCFE539A | TA00277 | SB7730 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform protection relay testing, calibration and servicing for 1 unit | A12110 | 6 | 12 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 09:00 | 2024-09-01 16:00 | [6 empty] | 2024-08-15 15:57
54D07E9D-D71A-42BD-3E57-08DCBCFE539A | TA00277 | SB7730 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Circuit normalization and de-isolation | A12120 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-09-01 16:00 | 2024-09-01 17:00 | [6 empty] | 2024-08-15 15:57
0ACD8BC1-3278-431E-3E56-08DCBCFE539A | TA00276 | SB7715 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Electrical Isolation by PCSB competence personal | A12070 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:57
A5AB6A29-C2E9-4ADF-3E54-08DCBCFE539A | TA00276 | SB7715 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform protection relay testing, calibration and servicing for 1 unit | A12080 | 6 | 12 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 09:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:57
76D0EE27-04C6-48AF-3E55-08DCBCFE539A | TA00276 | SB7715 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Circuit normalization and de-isolation | A12090 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:57
9B3B3F40-044C-4C70-3E52-08DCBCFE539A | TA00275 | SB7700 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Electrical Isolation by PCSB competence personal | A12040 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:57
C8321AC4-CB02-4C5E-3E51-08DCBCFE539A | TA00275 | SB7700 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform protection relay testing, calibration and servicing for 1 unit | A12050 | 6 | 12 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 09:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:57
CB699296-EDA0-45A0-3E53-08DCBCFE539A | TA00275 | SB7700 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Circuit normalization and de-isolation | A12060 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:57
517E8C22-302A-4B32-3E50-08DCBCFE539A | TA00274 | SB7500 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Electrical Isolation by PCSB competence personal | A12010 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:57
03CF4349-FFD1-41CE-3E4F-08DCBCFE539A | TA00274 | SB7500 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform protection relay testing, calibration and servicing for 1 unit | A12020 | 6 | 12 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 09:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:57
CC210B7C-D06F-4F66-3E4E-08DCBCFE539A | TA00274 | SB7500 | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Circuit normalization and de-isolation | A12030 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:57
F2608427-BFE2-4E9B-3E4C-08DCBCFE539A | TA00273 | G-7720 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Electrical Isolation by PCSB competence personal | A11980 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 08:00 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:57
7559BCE8-9B1B-4FF5-3E4B-08DCBCFE539A | TA00273 | G-7720 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform protection relay testing, calibration and servicing for 1 unit | A11990 | 6 | 12 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 16:00 | [6 empty] | 2024-08-15 15:57
C044B457-0A23-4226-3E4D-08DCBCFE539A | TA00273 | G-7720 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Circuit normalization and de-isolation | A12000 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 16:00 | 2024-08-31 17:00 | [6 empty] | 2024-08-15 15:57
582445EA-13FF-41D4-3E48-08DCBCFE539A | TA00272 | G-7710 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Electrical Isolation by PCSB competence personal | A11950 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 09:00 | [6 empty] | 2024-08-15 15:57
6B1CDFA0-98D8-4308-3E4A-08DCBCFE539A | TA00272 | G-7710 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform protection relay testing, calibration and servicing for 1 unit | A11960 | 6 | 12 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 09:00 | 2024-08-30 16:00 | [6 empty] | 2024-08-15 15:57
AB803F74-99FE-4449-3E49-08DCBCFE539A | TA00272 | G-7710 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Circuit normalization and de-isolation | A11970 | 1 | 2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 16:00 | 2024-08-30 17:00 | [6 empty] | 2024-08-15 15:57
6CC010B1-2113-468A-3E46-08DCBCFE539A | TA00271 | JB-7500/JB-7551 | Bokor | BODP-D |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Identify the circuit and equipment tag number | A12160 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 15:30 | [6 empty] | 2024-08-15 15:57
081AA810-0EA1-4264-3E43-08DCBCFE539A | TA00271 | JB-7500/JB-7551 | Bokor | BODP-D |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | ACP/AP to perform discharge test and prove dead | A12170 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 15:30 | 2024-08-30 09:00 | [6 empty] | 2024-08-15 15:57
F421417F-28B8-44A4-3E45-08DCBCFE539A | TA00271 | JB-7500/JB-7551 | Bokor | BODP-D |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Disconnect power cable at both end of location | A12180 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 09:00 | 2024-08-30 11:30 | [6 empty] | 2024-08-15 15:57
7897A7AF-1AB4-49B3-3E44-08DCBCFE539A | TA00271 | JB-7500/JB-7551 | Bokor | BODP-D |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | To perform continuity test for the cable and insulation resistance test | A12190 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 11:30 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:57
B69F70B2-B7F0-48AA-3E47-08DCBCFE539A | TA00271 | JB-7500/JB-7551 | Bokor | BODP-D |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | HV cable jointing using hot shrink method | A12200 | 2.5 | 1.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-31 08:30 | [6 empty] | 2024-08-15 15:57
9E8801A3-03B0-4CD5-3E40-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Prove circuit dead before disconnect power cables on heater bundle and space heater prior to starting work | A11790 | 0.6 | 0.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 16:12 | 2024-08-30 16:48 | [6 empty] | 2024-08-15 15:57
B60B9162-47E2-4CB6-3E3F-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform the insulation resistance (IR) and continuity/contact resistance (CR) test for the heater element in grouping | A11800 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 16:48 | 2024-08-31 08:24 | [6 empty] | 2024-08-15 15:57
56A8905D-9B15-467D-3E3E-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform visual check and gather data | A11810 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 08:24 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:57
3F3612D4-8E31-49FB-3E3C-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform functional test for temperature transmitter/sensor heater element, flange and termination box | A11820 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 09:36 | [6 empty] | 2024-08-15 15:57
B18A5EC5-9D1C-49E2-3E42-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Perform power cables termination inside the junction box and close cover of termination box heater bundle | A11830 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 09:36 | 2024-08-31 10:12 | [6 empty] | 2024-08-15 15:57
5ABD8A24-B490-4998-3E3D-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform tightening and looseness check for the all termination heater element | A11840 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 10:12 | 2024-08-31 10:48 | [6 empty] | 2024-08-15 15:57
7FD1FBC3-6082-44B6-3E3B-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 70 | Visual check and data gathering for all electrical and mechanical equipment inside heater control panel | A11850 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 10:48 | 2024-08-31 11:24 | [6 empty] | 2024-08-15 15:57
912D5CD4-E39A-4446-3E37-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 80 | Inspect all bolted electrical connection. To perform IR testing on power cables. | A11860 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 11:24 | 2024-08-31 12:00 | [6 empty] | 2024-08-15 15:57
726EAADC-306C-48B7-3E3A-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 90 | Perform the IR and CR test for the main incoming inside heater control panel | A11870 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 13:00 | 2024-08-31 13:36 | [6 empty] | 2024-08-15 15:57
194CB151-4076-4D32-3E39-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 100 | Perform tightening and looseness check for all electrical and mechanical equipment | A11880 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 13:36 | 2024-08-31 14:12 | [6 empty] | 2024-08-15 15:57
4280EEED-366A-4EAC-3E41-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 110 | Perform general cleaning for electrical and mechanical equipment | A11890 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 14:12 | 2024-08-31 14:48 | [6 empty] | 2024-08-15 15:57
27D749A4-D326-4233-3E38-08DCBCFE539A | TA00270 | E-6050 | Laila | LADR-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 120 | Troubleshooting for heater control panel is required if the unit is not functioning well | A11900 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 14:48 | 2024-08-31 15:24 | [6 empty] | 2024-08-15 15:57
2852E685-7757-4025-3E32-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Prove circuit dead before disconnect power cables on heater bundle and space heater prior to starting work | A11670 | 0.6 | 0.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 08:36 | [6 empty] | 2024-08-15 15:57
6878543A-EFA7-44DA-3E35-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform the insulation resistance (IR) and continuity/contact resistance (CR) test for the heater element in grouping | A11680 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 08:36 | 2024-08-30 09:12 | [6 empty] | 2024-08-15 15:57
966C9DBD-11E2-4BB5-3E2B-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform visual check and gather data | A11690 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 09:12 | 2024-08-30 09:48 | [6 empty] | 2024-08-15 15:57
510CE7C1-5251-4005-3E30-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform functional test for temperature transmitter/sensor heater element, flange and termination box | A11700 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 09:48 | 2024-08-30 10:24 | [6 empty] | 2024-08-15 15:57
694354DC-B98C-483E-3E36-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Perform power cables termination inside the junction box and close cover of termination box heater bundle | A11710 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 10:24 | 2024-08-30 11:00 | [6 empty] | 2024-08-15 15:57
525CDEBB-1010-4E2E-3E2F-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform tightening and looseness check for the all termination heater element | A11720 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-30 11:36 | [6 empty] | 2024-08-15 15:57
E8B774FE-F549-4048-3E31-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 70 | Visual check and data gathering for all electrical and mechanical equipment inside heater control panel | A11730 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 11:36 | 2024-08-30 13:12 | [6 empty] | 2024-08-15 15:57
99140B15-71F2-47F3-3E2E-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 80 | Inspect all bolted electrical connection. To perform IR testing on power cables. | A11740 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 13:12 | 2024-08-30 13:48 | [6 empty] | 2024-08-15 15:57
88A6A86B-1D16-4C74-3E2C-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 90 | Perform the IR and CR test for the main incoming inside heater control panel | A11750 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 13:48 | 2024-08-30 14:24 | [6 empty] | 2024-08-15 15:57
B159A9D5-C1CE-439D-3E33-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 100 | Perform tightening and looseness check for all electrical and mechanical equipment | A11760 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 14:24 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:57
473B5EE3-9544-4475-3E2D-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 110 | Perform general cleaning for electrical and mechanical equipment | A11770 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-30 15:36 | [6 empty] | 2024-08-15 15:57
FEB38F51-3D13-425A-3E34-08DCBCFE539A | TA00269 | E-640 | Betty | BEDP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 120 | Troubleshooting for heater control panel is required if the unit is not functioning well | A11780 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 15:36 | 2024-08-30 16:12 | [6 empty] | 2024-08-15 15:57
563922DE-B4E8-4A87-3E27-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Prove circuit dead before disconnect power cables on heater bundle and space heater prior to starting work | A11550 | 0.6 | 0.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 08:48 | 2024-08-29 09:24 | [6 empty] | 2024-08-15 15:57
7B06E779-C0A8-478A-3E25-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform the insulation resistance (IR) and continuity/contact resistance (CR) test for the heater element in grouping | A11560 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 09:24 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:57
3D58AF47-B422-4927-3E24-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform visual check and gather data | A11570 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 10:36 | [6 empty] | 2024-08-15 15:57
99197300-2484-49F8-3E28-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform functional test for temperature transmitter/sensor heater element, flange and termination box | A11580 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 10:36 | 2024-08-29 11:12 | [6 empty] | 2024-08-15 15:57
B1088BC6-FB43-4303-3E21-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Perform power cables termination inside the junction box and close cover of termination box heater bundle | A11590 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 11:12 | 2024-08-29 11:48 | [6 empty] | 2024-08-15 15:57
AFCDAD74-3384-4994-3E2A-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform tightening and looseness check for the all termination heater element | A11600 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 11:48 | 2024-08-29 13:24 | [6 empty] | 2024-08-15 15:57
717B8781-335B-48B5-3E26-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 70 | Visual check and data gathering for all electrical and mechanical equipment inside heater control panel | A11610 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 13:24 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:57
0DE514AA-6F96-4334-3E29-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 80 | Inspect all bolted electrical connection. To perform IR testing on power cables. | A11620 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-29 14:36 | [6 empty] | 2024-08-15 15:57
42765FEC-DB84-4BCF-3E1F-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 90 | Perform the IR and CR test for the main incoming inside heater control panel | A11630 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 14:36 | 2024-08-29 15:12 | [6 empty] | 2024-08-15 15:57
038614BB-B4C5-4465-3E23-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 100 | Perform tightening and looseness check for all electrical and mechanical equipment | A11640 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 15:12 | 2024-08-29 15:48 | [6 empty] | 2024-08-15 15:57
05C66BD1-9A33-476C-3E22-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 110 | Perform general cleaning for electrical and mechanical equipment | A11650 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 15:48 | 2024-08-29 16:24 | [6 empty] | 2024-08-15 15:57
99DB40A2-05B3-4D58-3E20-08DCBCFE539A | TA00268 | E-2350 | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 120 | Troubleshooting for heater control panel is required if the unit is not functioning well | A11660 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 16:24 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:57
6A157258-293E-405F-3E1A-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Prove circuit dead before disconnect power cables on heater bundle and space heater prior to starting work | A11430 | 0.6 | 0.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 09:36 | 2024-08-28 10:12 | [6 empty] | 2024-08-15 15:57
D174E27A-B3E4-44B7-3E16-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform the insulation resistance (IR) and continuity/contact resistance (CR) test for the heater element in grouping | A11440 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 10:12 | 2024-08-28 10:48 | [6 empty] | 2024-08-15 15:57
894D9DA1-C3A5-4C38-3E17-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform visual check and gather data | A11450 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 10:48 | 2024-08-28 11:24 | [6 empty] | 2024-08-15 15:57
14195BF8-52D7-4CFA-3E19-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform functional test for temperature transmitter/sensor heater element, flange and termination box | A11460 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 11:24 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:57
94ED673F-919F-4B47-3E1D-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Perform power cables termination inside the junction box and close cover of termination box heater bundle | A11470 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 13:36 | [6 empty] | 2024-08-15 15:57
4B244BD3-7C8D-4538-3E13-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform tightening and looseness check for the all termination heater element | A11480 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 13:36 | 2024-08-28 14:12 | [6 empty] | 2024-08-15 15:57
9B35216D-D271-467B-3E1C-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 70 | Visual check and data gathering for all electrical and mechanical equipment inside heater control panel | A11490 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 14:12 | 2024-08-28 14:48 | [6 empty] | 2024-08-15 15:57
0EB7D20A-B83E-45E7-3E15-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 80 | Inspect all bolted electrical connection. To perform IR testing on power cables. | A11500 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 14:48 | 2024-08-28 15:24 | [6 empty] | 2024-08-15 15:57
6999DD90-08C9-44B2-3E14-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 90 | Perform the IR and CR test for the main incoming inside heater control panel | A11510 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 15:24 | 2024-08-28 16:00 | [6 empty] | 2024-08-15 15:57
CD6D9429-4FD2-429E-3E1B-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 100 | Perform tightening and looseness check for all electrical and mechanical equipment | A11520 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 16:00 | 2024-08-28 16:36 | [6 empty] | 2024-08-15 15:57
EA668F03-2834-4380-3E1E-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 110 | Perform general cleaning for electrical and mechanical equipment | A11530 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 16:36 | 2024-08-29 08:12 | [6 empty] | 2024-08-15 15:57
D0967F70-A983-4D3C-3E18-08DCBCFE539A | TA00267 | E-6020B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 120 | Troubleshooting for heater control panel is required if the unit is not functioning well | A11540 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 08:12 | 2024-08-29 08:48 | [6 empty] | 2024-08-15 15:57
4E2E5751-57B9-404B-3E0F-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Prove circuit dead before disconnect power cables on heater bundle and space heater prior to starting work | A11310 | 0.6 | 0.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 10:24 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:57
5AE8C019-295D-4788-3E0C-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform the insulation resistance (IR) and continuity/contact resistance (CR) test for the heater element in grouping | A11320 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 11:36 | [6 empty] | 2024-08-15 15:57
36038D26-1996-47C9-3E11-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform visual check and gather data | A11330 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 11:36 | 2024-08-27 13:12 | [6 empty] | 2024-08-15 15:57
65682FC8-0F84-4A20-3E10-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform functional test for temperature transmitter/sensor heater element, flange and termination box | A11340 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 13:12 | 2024-08-27 13:48 | [6 empty] | 2024-08-15 15:57
EC8596F2-D673-4983-3E0B-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Perform power cables termination inside the junction box and close cover of termination box heater bundle | A11350 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 13:48 | 2024-08-27 14:24 | [6 empty] | 2024-08-15 15:57
A14DF5EA-634B-488E-3E08-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform tightening and looseness check for the all termination heater element | A11360 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 14:24 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:57
3FA9CF26-D3C1-47EB-3E09-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 70 | Visual check and data gathering for all electrical and mechanical equipment inside heater control panel | A11370 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-27 15:36 | [6 empty] | 2024-08-15 15:57
7DF30CC5-AE33-41BF-3E12-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 80 | Inspect all bolted electrical connection. To perform IR testing on power cables. | A11380 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 15:36 | 2024-08-27 16:12 | [6 empty] | 2024-08-15 15:57
C64E9479-3963-45F5-3E0D-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 90 | Perform the IR and CR test for the main incoming inside heater control panel | A11390 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 16:12 | 2024-08-27 16:48 | [6 empty] | 2024-08-15 15:57
DC268172-4AC9-4BD5-3E07-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 100 | Perform tightening and looseness check for all electrical and mechanical equipment | A11400 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 16:48 | 2024-08-28 08:24 | [6 empty] | 2024-08-15 15:57
F50DD9A2-D6E5-43B8-3E0E-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 110 | Perform general cleaning for electrical and mechanical equipment | A11410 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 08:24 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:57
0B36DBA6-B0B5-4C86-3E0A-08DCBCFE539A | TA00266 | E-6020A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 120 | Troubleshooting for heater control panel is required if the unit is not functioning well | A11420 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 09:36 | [6 empty] | 2024-08-15 15:57
4C162C71-FFD9-4450-3E00-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Prove circuit dead before disconnect power cables on heater bundle and space heater prior to starting work | A11190 | 0.6 | 0.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 11:12 | 2024-08-26 11:48 | [6 empty] | 2024-08-15 15:57
0F3669A9-2947-4C1C-3E04-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform the insulation resistance (IR) and continuity/contact resistance (CR) test for the heater element in grouping | A11200 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 11:48 | 2024-08-26 13:24 | [6 empty] | 2024-08-15 15:57
E0A451BD-5F92-42F9-3E02-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform visual check and gather data | A11210 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 13:24 | 2024-08-26 14:00 | [6 empty] | 2024-08-15 15:57
AC2AAA64-6BB9-4234-3E01-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform functional test for temperature transmitter/sensor heater element, flange and termination box | A11220 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 14:00 | 2024-08-26 14:36 | [6 empty] | 2024-08-15 15:57
5CD8A84C-9C40-46DF-3DFC-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Perform power cables termination inside the junction box and close cover of termination box heater bundle | A11230 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 14:36 | 2024-08-26 15:12 | [6 empty] | 2024-08-15 15:57
738F3C94-A805-4BCE-3DFB-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform tightening and looseness check for the all termination heater element | A11240 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 15:12 | 2024-08-26 15:48 | [6 empty] | 2024-08-15 15:57
783E95ED-AECB-442E-3E05-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 70 | Visual check and data gathering for all electrical and mechanical equipment inside heater control panel | A11250 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 15:48 | 2024-08-26 16:24 | [6 empty] | 2024-08-15 15:57
CF58BF25-AE10-4359-3E06-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 80 | Inspect all bolted electrical connection. To perform IR testing on power cables. | A11260 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 16:24 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:57
7D805D4A-641A-42C9-3DFF-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 90 | Perform the IR and CR test for the main incoming inside heater control panel | A11270 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 08:36 | [6 empty] | 2024-08-15 15:57
AFC9A692-432F-4A76-3DFE-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 100 | Perform tightening and looseness check for all electrical and mechanical equipment | A11280 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 08:36 | 2024-08-27 09:12 | [6 empty] | 2024-08-15 15:57
B92F59A3-7FC7-4BB7-3DFD-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 110 | Perform general cleaning for electrical and mechanical equipment | A11290 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 09:12 | 2024-08-27 09:48 | [6 empty] | 2024-08-15 15:57
FE054D38-0CDE-437C-3E03-08DCBCFE539A | TA00265 | E-5920B | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 120 | Troubleshooting for heater control panel is required if the unit is not functioning well | A11300 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 09:48 | 2024-08-27 10:24 | [6 empty] | 2024-08-15 15:57
D45214D1-4673-4657-3DFA-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Prove circuit dead before disconnect power cables on heater bundle and space heater prior to starting work | A11070 | 0.6 | 0.6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:36 | [6 empty] | 2024-08-15 15:57
D2B5E6AF-CF05-4CD5-3DF8-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | Perform the insulation resistance (IR) and continuity/contact resistance (CR) test for the heater element in grouping | A11080 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 13:36 | 2024-08-25 14:12 | [6 empty] | 2024-08-15 15:57
12FBDD9D-267D-43FE-3DEF-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | Perform visual check and gather data | A11090 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 14:12 | 2024-08-25 14:48 | [6 empty] | 2024-08-15 15:57
BC876913-C06B-4FA5-3DF2-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | Perform functional test for temperature transmitter/sensor heater element, flange and termination box | A11100 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 14:48 | 2024-08-25 15:24 | [6 empty] | 2024-08-15 15:57
F25FA274-8B84-4E21-3DF5-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 50 | Perform power cables termination inside the junction box and close cover of termination box heater bundle | A11110 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 15:24 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:57
07FC67B5-0048-4B70-3DF0-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 60 | Perform tightening and looseness check for the all termination heater element | A11120 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 16:36 | [6 empty] | 2024-08-15 15:57
CDCB9DB9-5688-4F34-3DF1-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 70 | Visual check and data gathering for all electrical and mechanical equipment inside heater control panel | A11130 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 16:36 | 2024-08-26 08:12 | [6 empty] | 2024-08-15 15:57
5328C721-EAA5-4061-3DF7-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 80 | Inspect all bolted electrical connection. To perform IR testing on power cables. | A11140 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 08:12 | 2024-08-26 08:48 | [6 empty] | 2024-08-15 15:57
FE539DFF-4AC1-4960-3DF6-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 90 | Perform the IR and CR test for the main incoming inside heater control panel | A11150 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 08:48 | 2024-08-26 09:24 | [6 empty] | 2024-08-15 15:57
5A2CBFCB-F88E-408C-3DF3-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 100 | Perform tightening and looseness check for all electrical and mechanical equipment | A11160 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 09:24 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:57
0BD063C9-4E33-44D1-3DF9-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 110 | Perform general cleaning for electrical and mechanical equipment | A11170 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 10:36 | [6 empty] | 2024-08-15 15:57
FE6CFB58-72DA-4C2C-3DF4-08DCBCFE539A | TA00264 | E-5920A | Bokor | BOCPP-A |  | Heater | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 120 | Troubleshooting for heater control panel is required if the unit is not functioning well | A11180 | 0.6 | 1.2 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 10:36 | 2024-08-26 11:12 | [6 empty] | 2024-08-15 15:57
FF718DF1-FF61-4BEC-3DEE-08DCBCFE539A | TA00263 | UP110F2 | Laila | LADR-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12960 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 11:30 | [6 empty] | 2024-08-15 15:57
4C8290B3-8287-4269-3DED-08DCBCFE539A | TA00262 | UP110F1 | Laila | LADR-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12950 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 15:30 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:57
BD2E2EC0-96FF-42B7-3DEC-08DCBCFE539A | TA00261 | BC-7910B (BODP-F) | Bokor | BODP-F |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12940 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 16:30 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:57
4AF1F087-537C-4856-3DEB-08DCBCFE539A | TA00260 | BC-7910A (BODP-F) | Bokor | BODP-F |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12930 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-28 16:30 | [6 empty] | 2024-08-15 15:57
1E7B5D54-5BBF-4B5D-3DEA-08DCBCFE539A | TA00259 | BC-7910B (BODP-D) | Bokor | BODP-D |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12920 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 10:30 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:57
DD0E623D-5418-4DD6-3DE9-08DCBCFE539A | TA00258 | BC-7910A (BODP-D) | Bokor | BODP-D |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12910 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 10:30 | [6 empty] | 2024-08-15 15:57
1FA5116E-4991-405E-3DE8-08DCBCFE539A | TA00257 | UPS7880 | Bokor | BODP-C |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12900 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 14:30 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:57
A06F17E2-6F01-45E9-3DE7-08DCBCFE539A | TA00256 | UPS-7810B (BODP-A) | Bokor | BODP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12890 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 14:30 | [6 empty] | 2024-08-15 15:57
97396E91-6E18-4DB9-3DE6-08DCBCFE539A | TA00255 | UPS-7810A (BODP-A) | Bokor | BODP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12880 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 08:30 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:57
CDF0718D-0EAF-4549-3DE5-08DCBCFE539A | TA00254 | UPS-7700B | Bokor | BODP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12870 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-27 08:30 | [6 empty] | 2024-08-15 15:57
6C393939-EB45-4B74-3DE4-08DCBCFE539A | TA00253 | UPS-7700A | Bokor | BODP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12860 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 11:30 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:57
97FD597D-B8C2-4CCC-3DE3-08DCBCFE539A | TA00252 | UPS7800 | Bokor | BODP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12850 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 11:30 | [6 empty] | 2024-08-15 15:57
A97E888D-3CC8-4B36-3DE2-08DCBCFE539A | TA00251 | UPS7810A (BOCPP-A) | Bokor | BOCPP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12840 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 15:30 | 2024-08-26 09:00 | [6 empty] | 2024-08-15 15:57
E7020806-55BC-4335-3DE1-08DCBCFE539A | TA00250 | UPS-7860 | Bokor | BODP-B |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12830 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 15:30 | [6 empty] | 2024-08-15 15:57
E57E7A85-34AA-4B4B-3DE0-08DCBCFE539A | TA00249 | UPS-7810B | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12820 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 13:00 | 2024-08-30 15:30 | [6 empty] | 2024-08-15 15:57
99CEDC95-5B20-408A-3DDF-08DCBCFE539A | TA00248 | UPS-7840 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12810 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-30 09:30 | 2024-08-30 12:00 | [6 empty] | 2024-08-15 15:57
967A955B-1D02-4457-3DDE-08DCBCFE539A | TA00247 | UPS-7810A | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12800 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-30 09:30 | [6 empty] | 2024-08-15 15:57
902C1BE5-221E-4B5E-3DDD-08DCBCFE539A | TA00246 | UPS-7800A | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12790 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 13:30 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:57
4D750702-F8B2-41E2-3DDC-08DCBCFE539A | TA00245 | NCCP-7830 | Betty | BEDP-A |  | Electrical Equipment | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | Perform battery discharge test on battery bank | A12780 | 2.5 | 5 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 13:30 | [6 empty] | 2024-08-15 15:57
8CD1A9BF-2E33-4133-3DDA-08DCBCFE539A | TA00244 | IMCS | Bokor | BOCPP-A |  | IMCS | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 10 | IMCS workstation pc backup and window image backup | A11910 | 6 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:57
F4460C39-F64A-4264-3DD9-08DCBCFE539A | TA00244 | IMCS | Bokor | BOCPP-A |  | IMCS | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 20 | MACfee antivirus installation & definition updates | A11920 | 6 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:57
4CCFCEAB-315F-4BB5-3DDB-08DCBCFE539A | TA00244 | IMCS | Bokor | BOCPP-A |  | IMCS | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 30 | SEPAM relay backup & health check | A11930 | 6 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:57
F9DE499B-DA33-4C82-3DD8-08DCBCFE539A | TA00244 | IMCS | Bokor | BOCPP-A |  | IMCS | Electrical | Maintenance | PPM | Prelim | Electrical | Execution | 40 | MCU/ Tesys health check | A11940 | 6 | 6 | 0 |  | AEEITS00 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:57
9BE40AC6-9900-4714-3DD2-08DCBCFE539A | TA00243 | 060SDV002 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A5020 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 14:42 | 2024-08-29 14:57 | [6 empty] | 2024-08-15 15:57
DFF0E02C-23EE-48C4-3DD5-08DCBCFE539A | TA00243 | 060SDV002 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A5030 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 14:57 | 2024-08-29 15:12 | [6 empty] | 2024-08-15 15:57
FD3BA70A-6C9B-4B03-3DD4-08DCBCFE539A | TA00243 | 060SDV002 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A5040 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 15:12 | 2024-08-29 15:20 | [6 empty] | 2024-08-15 15:57
33B47EE2-A2B1-4C2C-3DD7-08DCBCFE539A | TA00243 | 060SDV002 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A5050 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 15:20 | 2024-08-29 15:28 | [6 empty] | 2024-08-15 15:57
3523C54C-4135-42A7-3DD3-08DCBCFE539A | TA00243 | 060SDV002 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A5060 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 15:28 | 2024-08-29 16:28 | [6 empty] | 2024-08-15 15:57
81C7D0E4-BE0F-483E-3DD6-08DCBCFE539A | TA00243 | 060SDV002 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A5070 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 16:28 | 2024-08-29 16:36 | [6 empty] | 2024-08-15 15:57
E3779E30-420D-4B26-3DD1-08DCBCFE539A | TA00242 | 290SDV061 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4960 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 11:48 | 2024-08-29 13:03 | [6 empty] | 2024-08-15 15:57
F1BE5C92-4859-4B81-3DCE-08DCBCFE539A | TA00242 | 290SDV061 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4970 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 13:03 | 2024-08-29 13:18 | [6 empty] | 2024-08-15 15:57
93C61708-F06F-40C8-3DCD-08DCBCFE539A | TA00242 | 290SDV061 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4980 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 13:18 | 2024-08-29 13:26 | [6 empty] | 2024-08-15 15:57
B2D31568-1C52-4696-3DCF-08DCBCFE539A | TA00242 | 290SDV061 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4990 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 13:26 | 2024-08-29 13:34 | [6 empty] | 2024-08-15 15:57
FFDC7923-6047-445B-3DD0-08DCBCFE539A | TA00242 | 290SDV061 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A5000 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 13:34 | 2024-08-29 14:34 | [6 empty] | 2024-08-15 15:57
01852270-611F-4C0B-3DCC-08DCBCFE539A | TA00242 | 290SDV061 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A5010 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 14:34 | 2024-08-29 14:42 | [6 empty] | 2024-08-15 15:57
20145B26-01AE-4EF3-3DC6-08DCBCFE539A | TA00241 | 135SDV050 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4900 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:54 | 2024-08-29 10:09 | [6 empty] | 2024-08-15 15:57
57A963F4-32E3-4248-3DCB-08DCBCFE539A | TA00241 | 135SDV050 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4910 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:09 | 2024-08-29 10:24 | [6 empty] | 2024-08-15 15:57
1455ADD9-CDDD-4979-3DC9-08DCBCFE539A | TA00241 | 135SDV050 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4920 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:24 | 2024-08-29 10:32 | [6 empty] | 2024-08-15 15:57
DB3F260B-94AE-4C3A-3DCA-08DCBCFE539A | TA00241 | 135SDV050 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4930 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:32 | 2024-08-29 10:40 | [6 empty] | 2024-08-15 15:57
90435CB5-B07D-408C-3DC8-08DCBCFE539A | TA00241 | 135SDV050 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4940 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:40 | 2024-08-29 11:40 | [6 empty] | 2024-08-15 15:57
D9C8E21F-4BDF-4647-3DC7-08DCBCFE539A | TA00241 | 135SDV050 | Bokor | BODP-F |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4950 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 11:40 | 2024-08-29 11:48 | [6 empty] | 2024-08-15 15:57
8B20BA37-F798-4DD1-3DC4-08DCBCFE539A | TA00240 | ABV0101 | Bokor | BODP-C |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4840 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 08:15 | [6 empty] | 2024-08-15 15:57
D22DDB32-9BC1-460D-3DC0-08DCBCFE539A | TA00240 | ABV0101 | Bokor | BODP-C |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4850 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:15 | 2024-08-29 08:30 | [6 empty] | 2024-08-15 15:57
26F120D7-DC4C-45B7-3DC5-08DCBCFE539A | TA00240 | ABV0101 | Bokor | BODP-C |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4860 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:30 | 2024-08-29 08:38 | [6 empty] | 2024-08-15 15:57
D5F7DD83-8527-4EFB-3DC2-08DCBCFE539A | TA00240 | ABV0101 | Bokor | BODP-C |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4870 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:38 | 2024-08-29 08:46 | [6 empty] | 2024-08-15 15:57
0325681E-F8C7-439E-3DC3-08DCBCFE539A | TA00240 | ABV0101 | Bokor | BODP-C |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4880 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:46 | 2024-08-29 09:46 | [6 empty] | 2024-08-15 15:57
7E10F1E2-36ED-43C8-3DC1-08DCBCFE539A | TA00240 | ABV0101 | Bokor | BODP-C |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4890 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:46 | 2024-08-29 09:54 | [6 empty] | 2024-08-15 15:57
22C57D8A-5B0C-4207-3DBB-08DCBCFE539A | TA00239 | ABV0912 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4780 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 13:42 | 2024-08-28 13:57 | [6 empty] | 2024-08-15 15:57
AAEF30B8-F45F-4EA5-3DBE-08DCBCFE539A | TA00239 | ABV0912 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4790 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 13:57 | 2024-08-28 14:12 | [6 empty] | 2024-08-15 15:57
3A07B442-0ACB-4587-3DBC-08DCBCFE539A | TA00239 | ABV0912 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4800 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 14:12 | 2024-08-28 14:20 | [6 empty] | 2024-08-15 15:57
F52F9591-52B2-49A4-3DBF-08DCBCFE539A | TA00239 | ABV0912 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4810 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 14:20 | 2024-08-28 14:28 | [6 empty] | 2024-08-15 15:57
6D79870D-D1CA-4452-3DBA-08DCBCFE539A | TA00239 | ABV0912 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4820 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 14:28 | 2024-08-28 15:28 | [6 empty] | 2024-08-15 15:57
FB6D553D-D98A-4388-3DBD-08DCBCFE539A | TA00239 | ABV0912 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4830 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 15:28 | 2024-08-28 15:36 | [6 empty] | 2024-08-15 15:57
F511CABC-408E-4A42-3DB6-08DCBCFE539A | TA00238 | ABV932 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4720 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 10:48 | 2024-08-28 11:03 | [6 empty] | 2024-08-15 15:57
77D9778F-8196-4FA9-3DB7-08DCBCFE539A | TA00238 | ABV932 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4730 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 11:03 | 2024-08-28 11:18 | [6 empty] | 2024-08-15 15:57
22429C88-D453-425A-3DB4-08DCBCFE539A | TA00238 | ABV932 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4740 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 11:18 | 2024-08-28 11:26 | [6 empty] | 2024-08-15 15:57
15241564-92BD-4039-3DB5-08DCBCFE539A | TA00238 | ABV932 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4750 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 11:26 | 2024-08-28 11:34 | [6 empty] | 2024-08-15 15:57
0A82234E-47BD-48A0-3DB9-08DCBCFE539A | TA00238 | ABV932 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4760 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 11:34 | 2024-08-28 13:34 | [6 empty] | 2024-08-15 15:57
0C6D2106-FD61-4412-3DB8-08DCBCFE539A | TA00238 | ABV932 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4770 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 13:34 | 2024-08-28 13:42 | [6 empty] | 2024-08-15 15:57
709CACFE-879D-4781-3DB0-08DCBCFE539A | TA00237 | ABV942 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4660 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 08:54 | 2024-08-28 09:09 | [6 empty] | 2024-08-15 15:57
8EF28D89-05F7-4891-3DAE-08DCBCFE539A | TA00237 | ABV942 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4670 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:09 | 2024-08-28 09:24 | [6 empty] | 2024-08-15 15:57
52F61980-4BF1-4626-3DAF-08DCBCFE539A | TA00237 | ABV942 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4680 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:24 | 2024-08-28 09:32 | [6 empty] | 2024-08-15 15:57
8A84D804-010C-4F0A-3DB3-08DCBCFE539A | TA00237 | ABV942 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4690 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:32 | 2024-08-28 09:40 | [6 empty] | 2024-08-15 15:57
F17C2F06-23F6-426A-3DB2-08DCBCFE539A | TA00237 | ABV942 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4700 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:40 | 2024-08-28 10:40 | [6 empty] | 2024-08-15 15:57
BBF73612-37DE-4453-3DB1-08DCBCFE539A | TA00237 | ABV942 | Bokor | BODP-B |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4710 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 10:40 | 2024-08-28 10:48 | [6 empty] | 2024-08-15 15:57
0278DD01-DDF8-480C-3DAD-08DCBCFE539A | TA00236 | 070SDV001 | Bokor | BODP-D |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4600 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 16:00 | 2024-08-27 16:15 | [6 empty] | 2024-08-15 15:57
75BBDCDD-9A07-43E0-3DAC-08DCBCFE539A | TA00236 | 070SDV001 | Bokor | BODP-D |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4610 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 16:15 | 2024-08-27 16:30 | [6 empty] | 2024-08-15 15:57
6D096A9B-608A-4128-3DAA-08DCBCFE539A | TA00236 | 070SDV001 | Bokor | BODP-D |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4620 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 16:30 | 2024-08-27 16:38 | [6 empty] | 2024-08-15 15:57
A01D01A1-8794-4C5E-3DAB-08DCBCFE539A | TA00236 | 070SDV001 | Bokor | BODP-D |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4630 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 16:38 | 2024-08-27 16:46 | [6 empty] | 2024-08-15 15:57
3B91DF22-EFF4-45B3-3DA9-08DCBCFE539A | TA00236 | 070SDV001 | Bokor | BODP-D |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4640 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 16:46 | 2024-08-28 08:46 | [6 empty] | 2024-08-15 15:57
9696B879-BC2E-49CC-3DA8-08DCBCFE539A | TA00236 | 070SDV001 | Bokor | BODP-D |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4650 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 08:46 | 2024-08-28 08:54 | [6 empty] | 2024-08-15 15:57
18C2A70C-6F51-480B-3DA3-08DCBCFE539A | TA00235 | 131SV101 | Bokor | BOCPP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4540 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 14:06 | 2024-08-27 14:21 | [6 empty] | 2024-08-15 15:57
3487D329-A3D6-44DD-3DA2-08DCBCFE539A | TA00235 | 131SV101 | Bokor | BOCPP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4550 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 14:21 | 2024-08-27 14:36 | [6 empty] | 2024-08-15 15:57
A6F7932C-E0B0-4940-3DA7-08DCBCFE539A | TA00235 | 131SV101 | Bokor | BOCPP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4560 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 14:36 | 2024-08-27 14:44 | [6 empty] | 2024-08-15 15:57
B6875960-D18C-4600-3DA5-08DCBCFE539A | TA00235 | 131SV101 | Bokor | BOCPP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4570 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 14:44 | 2024-08-27 14:52 | [6 empty] | 2024-08-15 15:57
E2593A91-B260-45AE-3DA6-08DCBCFE539A | TA00235 | 131SV101 | Bokor | BOCPP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4580 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 14:52 | 2024-08-27 15:52 | [6 empty] | 2024-08-15 15:57
D9D7FDC5-C71A-4E0E-3DA4-08DCBCFE539A | TA00235 | 131SV101 | Bokor | BOCPP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4590 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 15:52 | 2024-08-27 16:00 | [6 empty] | 2024-08-15 15:57
267A45F5-E009-48D3-3D9C-08DCBCFE539A | TA00234 | ABV933 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4480 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:12 | 2024-08-27 11:27 | [6 empty] | 2024-08-15 15:57
ADD1AD34-21B7-4802-3D9D-08DCBCFE539A | TA00234 | ABV933 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4490 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:27 | 2024-08-27 11:42 | [6 empty] | 2024-08-15 15:57
DB32121F-5867-46EB-3DA1-08DCBCFE539A | TA00234 | ABV933 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4500 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:42 | 2024-08-27 11:50 | [6 empty] | 2024-08-15 15:57
CBA497B4-CE5F-4588-3D9F-08DCBCFE539A | TA00234 | ABV933 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4510 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:50 | 2024-08-27 11:58 | [6 empty] | 2024-08-15 15:57
DE42FE5A-340E-49F0-3DA0-08DCBCFE539A | TA00234 | ABV933 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4520 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:58 | 2024-08-27 13:58 | [6 empty] | 2024-08-15 15:57
B1C342FB-A0FD-409B-3D9E-08DCBCFE539A | TA00234 | ABV933 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4530 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 13:58 | 2024-08-27 14:06 | [6 empty] | 2024-08-15 15:57
33E36132-AE3E-495B-3D9A-08DCBCFE539A | TA00233 | ABV921 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4420 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:18 | 2024-08-27 09:33 | [6 empty] | 2024-08-15 15:57
723F45CF-4F87-41FF-3D99-08DCBCFE539A | TA00233 | ABV921 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4430 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:33 | 2024-08-27 09:48 | [6 empty] | 2024-08-15 15:57
30CC9423-4A3E-482E-3D96-08DCBCFE539A | TA00233 | ABV921 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4440 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:48 | 2024-08-27 09:56 | [6 empty] | 2024-08-15 15:57
73277BF7-3421-4F91-3D97-08DCBCFE539A | TA00233 | ABV921 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4450 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:56 | 2024-08-27 10:04 | [6 empty] | 2024-08-15 15:57
3E699298-2CCF-4CAB-3D9B-08DCBCFE539A | TA00233 | ABV921 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4460 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:04 | 2024-08-27 11:04 | [6 empty] | 2024-08-15 15:57
E4E35193-6088-478C-3D98-08DCBCFE539A | TA00233 | ABV921 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4470 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:04 | 2024-08-27 11:12 | [6 empty] | 2024-08-15 15:57
71384F74-E754-4F3E-3D94-08DCBCFE539A | TA00232 | ABV936 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4360 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 16:24 | 2024-08-26 16:39 | [6 empty] | 2024-08-15 15:57
AE6569EB-6AAE-411B-3D91-08DCBCFE539A | TA00232 | ABV936 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4370 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 16:39 | 2024-08-26 16:54 | [6 empty] | 2024-08-15 15:57
3D24FA01-3604-49EA-3D93-08DCBCFE539A | TA00232 | ABV936 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4380 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 16:54 | 2024-08-27 08:02 | [6 empty] | 2024-08-15 15:57
297C18FB-F1B4-4028-3D92-08DCBCFE539A | TA00232 | ABV936 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4390 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:02 | 2024-08-27 08:10 | [6 empty] | 2024-08-15 15:57
A18F15CF-DFBE-4C90-3D95-08DCBCFE539A | TA00232 | ABV936 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4400 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:10 | 2024-08-27 09:10 | [6 empty] | 2024-08-15 15:57
753B08BE-DCA1-4FC0-3D90-08DCBCFE539A | TA00232 | ABV936 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4410 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:10 | 2024-08-27 09:18 | [6 empty] | 2024-08-15 15:57
EFC9999C-70AA-4DD8-3D8D-08DCBCFE539A | TA00231 | ABV9601 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4300 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 14:30 | 2024-08-26 14:45 | [6 empty] | 2024-08-15 15:57
5E6E87A1-4206-443D-3D8C-08DCBCFE539A | TA00231 | ABV9601 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4310 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 14:45 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:57
EC4191A5-C9CE-4CD1-3D8A-08DCBCFE539A | TA00231 | ABV9601 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4320 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-26 15:08 | [6 empty] | 2024-08-15 15:57
3A618668-C552-4B7B-3D8F-08DCBCFE539A | TA00231 | ABV9601 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4330 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 15:08 | 2024-08-26 15:16 | [6 empty] | 2024-08-15 15:57
ADBBCD99-1159-48EC-3D8B-08DCBCFE539A | TA00231 | ABV9601 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4340 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 15:16 | 2024-08-26 16:16 | [6 empty] | 2024-08-15 15:57
4652A5DD-26ED-43F8-3D8E-08DCBCFE539A | TA00231 | ABV9601 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4350 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 16:16 | 2024-08-26 16:24 | [6 empty] | 2024-08-15 15:57
DC310915-7D13-4A84-3D86-08DCBCFE539A | TA00230 | ABV9201 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4240 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:36 | 2024-08-26 11:51 | [6 empty] | 2024-08-15 15:57
B1A677D3-F529-4C36-3D85-08DCBCFE539A | TA00230 | ABV9201 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4250 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:51 | 2024-08-26 13:06 | [6 empty] | 2024-08-15 15:57
3ECB1AED-190C-44EA-3D84-08DCBCFE539A | TA00230 | ABV9201 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4260 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 13:06 | 2024-08-26 13:14 | [6 empty] | 2024-08-15 15:57
CA204286-F75A-4856-3D89-08DCBCFE539A | TA00230 | ABV9201 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4270 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 13:14 | 2024-08-26 13:22 | [6 empty] | 2024-08-15 15:57
5FCCF417-E1BD-4831-3D88-08DCBCFE539A | TA00230 | ABV9201 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4280 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 13:22 | 2024-08-26 14:22 | [6 empty] | 2024-08-15 15:57
B4DE2DF2-00AF-4849-3D87-08DCBCFE539A | TA00230 | ABV9201 | Bokor | BOK-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4290 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 14:22 | 2024-08-26 14:30 | [6 empty] | 2024-08-15 15:57
77C180EF-5D99-417F-3D7F-08DCBCFE539A | TA00229 | ABV911 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4180 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:42 | 2024-08-26 09:57 | [6 empty] | 2024-08-15 15:57
6739B925-2642-40CD-3D82-08DCBCFE539A | TA00229 | ABV911 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4190 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:57 | 2024-08-26 10:12 | [6 empty] | 2024-08-15 15:57
701EE898-4BFB-4C14-3D83-08DCBCFE539A | TA00229 | ABV911 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4200 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:12 | 2024-08-26 10:20 | [6 empty] | 2024-08-15 15:57
65FD6392-641E-4DE0-3D81-08DCBCFE539A | TA00229 | ABV911 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4210 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:20 | 2024-08-26 10:28 | [6 empty] | 2024-08-15 15:57
904F1314-C826-440D-3D80-08DCBCFE539A | TA00229 | ABV911 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4220 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:28 | 2024-08-26 11:28 | [6 empty] | 2024-08-15 15:57
86878FC9-D88F-4840-3D7E-08DCBCFE539A | TA00229 | ABV911 | Bokor | BODP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4230 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:28 | 2024-08-26 11:36 | [6 empty] | 2024-08-15 15:57
36240AFE-9C66-4F14-3D78-08DCBCFE539A | TA00228 | ABV971 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4120 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:48 | 2024-08-26 08:03 | [6 empty] | 2024-08-15 15:57
38132581-65D3-4B47-3D7C-08DCBCFE539A | TA00228 | ABV971 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4130 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:03 | 2024-08-26 08:18 | [6 empty] | 2024-08-15 15:57
54F0837C-FC63-4255-3D79-08DCBCFE539A | TA00228 | ABV971 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4140 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:18 | 2024-08-26 08:26 | [6 empty] | 2024-08-15 15:57
5F7D45F5-6182-429E-3D7A-08DCBCFE539A | TA00228 | ABV971 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4150 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:26 | 2024-08-26 08:34 | [6 empty] | 2024-08-15 15:57
443BB2A0-88F8-40AF-3D7D-08DCBCFE539A | TA00228 | ABV971 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4160 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:34 | 2024-08-26 09:34 | [6 empty] | 2024-08-15 15:57
2F0A0530-581F-496B-3D7B-08DCBCFE539A | TA00228 | ABV971 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4170 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:34 | 2024-08-26 09:42 | [6 empty] | 2024-08-15 15:57
3BBB6384-F177-4035-3D73-08DCBCFE539A | TA00227 | ABV1020 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4060 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:54 | 2024-08-25 15:09 | [6 empty] | 2024-08-15 15:57
752BD62D-1F54-450D-3D76-08DCBCFE539A | TA00227 | ABV1020 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4070 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:09 | 2024-08-25 15:24 | [6 empty] | 2024-08-15 15:57
1B05D138-4096-43F4-3D77-08DCBCFE539A | TA00227 | ABV1020 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4080 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:24 | 2024-08-25 15:32 | [6 empty] | 2024-08-15 15:57
5513B76D-6697-42FF-3D75-08DCBCFE539A | TA00227 | ABV1020 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4090 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:32 | 2024-08-25 15:40 | [6 empty] | 2024-08-15 15:57
4EB8FE5F-0C80-4D34-3D74-08DCBCFE539A | TA00227 | ABV1020 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4100 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:40 | 2024-08-25 16:40 | [6 empty] | 2024-08-15 15:57
D68918F6-178A-48B6-3D72-08DCBCFE539A | TA00227 | ABV1020 | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4110 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:40 | 2024-08-25 16:48 | [6 empty] | 2024-08-15 15:57
8A44CE37-E93A-4228-3D71-08DCBCFE539A | TA00226 | ABV980A | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing. | A4000 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:15 | [6 empty] | 2024-08-15 15:57
A8876551-2CB5-435D-3D6D-08DCBCFE539A | TA00226 | ABV980A | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak. | A4010 | 0.3 | 0.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:15 | 2024-08-25 13:30 | [6 empty] | 2024-08-15 15:57
207F1001-E631-4BE7-3D6E-08DCBCFE539A | TA00226 | ABV980A | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality. | A4020 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:30 | 2024-08-25 13:38 | [6 empty] | 2024-08-15 15:57
CBA2A29E-1710-40F4-3D70-08DCBCFE539A | TA00226 | ABV980A | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure. | A4030 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:38 | 2024-08-25 13:46 | [6 empty] | 2024-08-15 15:57
BFDA0137-F2B8-4118-3D6F-08DCBCFE539A | TA00226 | ABV980A | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A4040 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:46 | 2024-08-25 14:46 | [6 empty] | 2024-08-15 15:57
F0BCF082-14F5-460F-3D6C-08DCBCFE539A | TA00226 | ABV980A | Bokor | BOP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A4050 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:46 | 2024-08-25 14:54 | [6 empty] | 2024-08-15 15:57
4A9DAB8C-6AFD-4CF8-3D66-08DCBCFE539A | TA00225 | ABV-9004A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3480 | 0.4 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:22 | 2024-08-27 10:46 | [6 empty] | 2024-08-15 15:57
B0F8DF1C-C988-4A77-3D68-08DCBCFE539A | TA00225 | ABV-9004A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3490 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:46 | 2024-08-27 11:04 | [6 empty] | 2024-08-15 15:57
07C21814-5534-43C5-3D6A-08DCBCFE539A | TA00225 | ABV-9004A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3500 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:04 | 2024-08-27 11:12 | [6 empty] | 2024-08-15 15:57
544CA433-BA1A-4468-3D6B-08DCBCFE539A | TA00225 | ABV-9004A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3510 | 0.2 | 0.4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:12 | 2024-08-27 11:24 | [6 empty] | 2024-08-15 15:57
EDE36B81-F234-48A3-3D69-08DCBCFE539A | TA00225 | ABV-9004A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3520 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:24 | 2024-08-27 11:44 | [6 empty] | 2024-08-15 15:57
2FFF3FB4-56D8-4B9E-3D67-08DCBCFE539A | TA00225 | ABV-9004A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3530 | 0.1 | 0.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:44 | 2024-08-27 11:50 | [6 empty] | 2024-08-15 15:57
B0DECEF6-4B0C-44D8-3D62-08DCBCFE539A | TA00224 | ABV-9006A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3420 | 0.4 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:54 | 2024-08-27 09:18 | [6 empty] | 2024-08-15 15:57
002A6454-825A-4342-3D60-08DCBCFE539A | TA00224 | ABV-9006A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3430 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:18 | 2024-08-27 09:36 | [6 empty] | 2024-08-15 15:57
19C01A28-6E8D-444E-3D65-08DCBCFE539A | TA00224 | ABV-9006A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3440 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:36 | 2024-08-27 09:44 | [6 empty] | 2024-08-15 15:57
6705E165-C056-4B55-3D61-08DCBCFE539A | TA00224 | ABV-9006A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3450 | 0.2 | 0.4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:44 | 2024-08-27 09:56 | [6 empty] | 2024-08-15 15:57
71AF9AF6-76B9-4885-3D63-08DCBCFE539A | TA00224 | ABV-9006A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3460 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:56 | 2024-08-27 10:16 | [6 empty] | 2024-08-15 15:57
47491D73-36E0-4BBA-3D64-08DCBCFE539A | TA00224 | ABV-9006A | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3470 | 0.1 | 0.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:16 | 2024-08-27 10:22 | [6 empty] | 2024-08-15 15:57
1852FDFE-209D-427F-3D5D-08DCBCFE539A | TA00223 | ABV-9100 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3360 | 0.4 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:26 | 2024-08-26 11:50 | [6 empty] | 2024-08-15 15:57
0F95FC20-7CFD-4248-3D5A-08DCBCFE539A | TA00223 | ABV-9100 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3370 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:50 | 2024-08-27 08:08 | [6 empty] | 2024-08-15 15:57
DA0252B4-8B3C-42DB-3D5B-08DCBCFE539A | TA00223 | ABV-9100 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3380 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:08 | 2024-08-27 08:16 | [6 empty] | 2024-08-15 15:57
3F25B546-1190-403F-3D5F-08DCBCFE539A | TA00223 | ABV-9100 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3390 | 0.2 | 0.4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:16 | 2024-08-27 08:28 | [6 empty] | 2024-08-15 15:57
14462BC1-E568-46C5-3D5C-08DCBCFE539A | TA00223 | ABV-9100 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3400 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:28 | 2024-08-27 08:48 | [6 empty] | 2024-08-15 15:57
3B2F95D0-D56E-45C3-3D5E-08DCBCFE539A | TA00223 | ABV-9100 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3410 | 0.1 | 0.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:48 | 2024-08-27 08:54 | [6 empty] | 2024-08-15 15:57
E14F1B18-4113-4ED6-3D58-08DCBCFE539A | TA00222 | ABV-9101 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3300 | 0.4 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:58 | 2024-08-26 10:22 | [6 empty] | 2024-08-15 15:57
95ED26AA-1A9A-4472-3D56-08DCBCFE539A | TA00222 | ABV-9101 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3310 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:22 | 2024-08-26 10:40 | [6 empty] | 2024-08-15 15:57
B245D054-119E-4C2D-3D55-08DCBCFE539A | TA00222 | ABV-9101 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3320 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:40 | 2024-08-26 10:48 | [6 empty] | 2024-08-15 15:57
2E509B92-4CE8-436A-3D59-08DCBCFE539A | TA00222 | ABV-9101 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3330 | 0.2 | 0.4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:48 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:57
B93B3296-5B42-4436-3D54-08DCBCFE539A | TA00222 | ABV-9101 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3340 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 11:20 | [6 empty] | 2024-08-15 15:57
1CE2BBF8-6FCA-40AB-3D57-08DCBCFE539A | TA00222 | ABV-9101 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3350 | 0.1 | 0.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:20 | 2024-08-26 11:26 | [6 empty] | 2024-08-15 15:57
A677BD11-28E1-489E-3D4E-08DCBCFE539A | TA00221 | ABV-9200 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3240 | 0.4 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:30 | 2024-08-26 08:54 | [6 empty] | 2024-08-15 15:57
F067EC48-7689-4276-3D53-08DCBCFE539A | TA00221 | ABV-9200 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3250 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:54 | 2024-08-26 09:12 | [6 empty] | 2024-08-15 15:57
911E3872-5D43-43F4-3D50-08DCBCFE539A | TA00221 | ABV-9200 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3260 | 0.1 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:12 | 2024-08-26 09:20 | [6 empty] | 2024-08-15 15:57
8DA4E61E-329A-4C48-3D52-08DCBCFE539A | TA00221 | ABV-9200 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3270 | 0.2 | 0.4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:20 | 2024-08-26 09:32 | [6 empty] | 2024-08-15 15:57
FF5A3B8F-6B76-4255-3D4F-08DCBCFE539A | TA00221 | ABV-9200 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3280 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:32 | 2024-08-26 09:52 | [6 empty] | 2024-08-15 15:57
D2AED472-3DEE-4FD9-3D51-08DCBCFE539A | TA00221 | ABV-9200 | Bakau | BKP-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3290 | 0.1 | 0.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:52 | 2024-08-26 09:58 | [6 empty] | 2024-08-15 15:57
D4202ECF-FC2A-4ED3-3D48-08DCBCFE539A | TA00220 | UZV-004 | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3180 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 16:20 | [6 empty] | 2024-08-15 15:57
14CBECFE-C8D9-49C4-3D4D-08DCBCFE539A | TA00220 | UZV-004 | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3190 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:20 | 2024-08-25 16:40 | [6 empty] | 2024-08-15 15:57
8E53FDB5-5DF4-49FA-3D4A-08DCBCFE539A | TA00220 | UZV-004 | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3200 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:40 | 2024-08-25 16:50 | [6 empty] | 2024-08-15 15:57
F51E079F-DA7D-4B0E-3D4B-08DCBCFE539A | TA00220 | UZV-004 | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3210 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:50 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:57
9005040E-ADA1-4D3D-3D49-08DCBCFE539A | TA00220 | UZV-004 | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3220 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 08:20 | [6 empty] | 2024-08-15 15:57
F3921383-0D0F-400D-3D4C-08DCBCFE539A | TA00220 | UZV-004 | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3230 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:20 | 2024-08-26 08:30 | [6 empty] | 2024-08-15 15:57
504FDF9F-8891-4680-3D44-08DCBCFE539A | TA00219 | UZV-001B | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3120 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:30 | 2024-08-25 14:50 | [6 empty] | 2024-08-15 15:57
6DBF9E53-E95F-4016-3D43-08DCBCFE539A | TA00219 | UZV-001B | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3130 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:50 | 2024-08-25 15:10 | [6 empty] | 2024-08-15 15:57
F6135235-B3FC-4271-3D46-08DCBCFE539A | TA00219 | UZV-001B | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3140 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:10 | 2024-08-25 15:20 | [6 empty] | 2024-08-15 15:57
F5BB60D5-E8D9-4998-3D42-08DCBCFE539A | TA00219 | UZV-001B | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3150 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:20 | 2024-08-25 15:30 | [6 empty] | 2024-08-15 15:57
6F5E125A-C6B3-4522-3D45-08DCBCFE539A | TA00219 | UZV-001B | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3160 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:30 | 2024-08-25 15:50 | [6 empty] | 2024-08-15 15:57
EC72E781-2E0F-4FC6-3D47-08DCBCFE539A | TA00219 | UZV-001B | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3170 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:50 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:57
6D099F64-FB56-435D-3D3F-08DCBCFE539A | TA00218 | UZV-001A | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 10 | To locate all valves on site with valve list & drawing | A3060 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:20 | [6 empty] | 2024-08-15 15:57
F03A0F63-0C61-44CD-3D3E-08DCBCFE539A | TA00218 | UZV-001A | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 20 | To access general valve/actuator condition, look for sign of corrosion, cracks, external leak | A3070 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:20 | 2024-08-25 13:40 | [6 empty] | 2024-08-15 15:57
860E7283-FF6F-4D3D-3D40-08DCBCFE539A | TA00218 | UZV-001A | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 30 | To check for flow direction, valve indicator functionality | A3080 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:40 | 2024-08-25 13:50 | [6 empty] | 2024-08-15 15:57
5303618E-186F-42AD-3D3D-08DCBCFE539A | TA00218 | UZV-001A | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 40 | To verify all valves is in fully closed position & to record upstream/downstream pressure | A3090 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:50 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:57
5D8D7C4F-3A54-45A0-3D3C-08DCBCFE539A | TA00218 | UZV-001A | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 50 | To place sensor on valve upstream & downstream area | A3100 | 0.3 | 0.7 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-25 14:20 | [6 empty] | 2024-08-15 15:57
6B04E3CC-1AD2-4BE0-3D41-08DCBCFE539A | TA00218 | UZV-001A | Laila | LADR-A |  | Control Valve | Construction | Maintenance | PPM | Prelim | CBM | Execution | 60 | Photo taking | A3110 | 0.2 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:20 | 2024-08-25 14:30 | [6 empty] | 2024-08-15 15:57
B830465A-FD85-4023-3D37-08DCBCFE539A | TA00217 | SI Line Replacement - 50-SI-68011-13411X | Bokor | BODP-F |  | Piping | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Fit-up FW joint - 3 Joint for line no. 50-SI-68011-13411X | A2990 | 8 | 104 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:57
97CDE8A8-6A72-4531-3D35-08DCBCFE539A | TA00217 | SI Line Replacement - 50-SI-68011-13411X | Bokor | BODP-F |  | Piping | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Welding FW joint - 3 joint for line no. 50-SI-68011-13411X | A3000 | 8 | 112 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:57
6913BDC2-3D31-47BD-3D3A-08DCBCFE539A | TA00217 | SI Line Replacement - 50-SI-68011-13411X | Bokor | BODP-F |  | Piping | Project | Maintenance | PPM | Prelim | Project | Execution | 30 | Perform RT on welding joint for line no. 50-SI-68011-13411X | A3010 | 3 | 42 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 11:00 | [6 empty] | 2024-08-15 15:57
6581DE28-AB50-463C-3D39-08DCBCFE539A | TA00217 | SI Line Replacement - 50-SI-68011-13411X | Bokor | BODP-F |  | Piping | Project | Maintenance | PPM | Prelim | Project | Execution | 40 | Perform ferrite testing for line no. 50-SI-68011-13411X | A3020 | 3 | 42 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-28 11:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:57
33C115E1-2E82-4133-3D3B-08DCBCFE539A | TA00217 | SI Line Replacement - 50-SI-68011-13411X | Bokor | BODP-F |  | Piping | Project | Maintenance | PPM | Prelim | Project | Execution | 50 | Perform Hydrotest for line no. 50-SI-68011-13411X | A3030 | 8 | 112 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:57
ABC60680-F7F8-4DC3-3D36-08DCBCFE539A | TA00217 | SI Line Replacement - 50-SI-68011-13411X | Bokor | BODP-F |  | Piping | Project | Maintenance | PPM | Prelim | Project | Execution | 60 | Re-instate piping line no. for line no. 50-SI-68011-13411X | A3040 | 8 | 104 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:57
FB07A4B4-2074-4C75-3D38-08DCBCFE539A | TA00217 | SI Line Replacement - 50-SI-68011-13411X | Bokor | BODP-F |  | Piping | Project | Maintenance | PPM | Prelim | Project | Execution | 70 | To perform service test for line no. 50-SI-68011-13411X | A3050 | 8 | 104 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-31 15:00 | [6 empty] | 2024-08-15 15:57
B9239EE0-BFB5-40B9-3D2F-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Team A identify patch panel fiber optic at electrical room and telecon room BOCPP-A to BODP-F | A2870 | 1 | 4 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:57
661C107E-F244-4887-3D2A-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Team A Perform continuity test (lesser) for every single core from BOCPP-A to BODP-F (A to B) | A2880 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:57
F0E201B3-6556-4320-3D34-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 30 | Team B location at BODP-F to identify laser every panel to confirm the fiber optic location as per drawing | A2890 | 1 | 4 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:57
D6DCD7E3-5A1C-49B4-3D30-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 40 | Continuity test (laser) form (A to B ) and ( B to A ) in a same time to identify fiber optic core at subsea JB at BODP-E | A2900 | 1 | 4 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 09:00 | [6 empty] | 2024-08-15 15:57
AB3315E2-95A6-4397-3D2B-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 50 | Perform re-splicing fiber optic core inside subsea jb to the right cable location panel. | A2910 | 1 | 4 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:57
10444FE7-55A3-4F89-3D32-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 60 | Team A Perform continuity test (laser) for every single core from BOCPP-A to BODP-F (A to B) again | A2920 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:57
93E1B9E4-D115-4A79-3D2D-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 70 | Perform re-splicing fiber optic core inside subsea jb to the right cable location panel | A2930 | 1 | 4 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 14:00 | [6 empty] | 2024-08-15 15:57
B535DE8A-4C82-4E16-3D29-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 80 | Perform splicing fiber optic cable every panel at BODP-F | A2940 | 1 | 4 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 14:00 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:57
4671CE83-8501-4EF9-3D2C-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 90 | Team A Perform continuity test (laser) for every single core from CPP to BODP-F( A to B ) check | A2950 | 1 | 4 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:57
1F99D210-533D-4262-3D2E-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 100 | Team A Perform OTDR test from CPP to BODP-F ( A to B ) | A2960 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-27 09:00 | [6 empty] | 2024-08-15 15:57
122B7604-1BC0-4B5E-3D33-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 110 | Team A Perform OTDR test from BODP-F to CPP ( B to A ) | A2970 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-27 09:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:57
F72675A2-56DB-4C15-3D31-08DCBCFE539A | TA00216 | Fibre Optic revalidation - CIS-9201-1 | Bokor | BODP-F |  | Safe Guarding System | Project | Maintenance | PPM | Prelim | Project | Execution | 120 | Re-terminate fibre optic cable at CPP and terminate fibre optic cable every panel at BODP-F | A2980 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:57
6DED2072-EFDC-42E5-3D28-08DCBCFE539A | TA00215 | FCV Replacement - 060FCV-060 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Remove exisiting FCV | A2840 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:57
2D8BB0E7-AB41-47B7-3D27-08DCBCFE539A | TA00215 | FCV Replacement - 060FCV-060 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Install new FCV at WH Gaslift lines | A2850 | 3 | 18 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-30 09:00 | [6 empty] | 2024-08-15 15:57
D3607AA7-99F1-496F-3D26-08DCBCFE539A | TA00215 | FCV Replacement - 060FCV-060 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 30 | Testing/Stroke test with BOCPP-A DCS | A2860 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-30 09:00 | 2024-08-30 12:00 | [6 empty] | 2024-08-15 15:57
7747ACDD-1A6B-4B25-3D24-08DCBCFE539A | TA00214 | FCV Replacement - 060FCV-050 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Remove exisiting FCV | A2810 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:57
D7F20356-525D-4AE2-3D25-08DCBCFE539A | TA00214 | FCV Replacement - 060FCV-050 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Install new FCV at WH Gaslift lines | A2820 | 3 | 18 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:57
BDDBF5FE-372B-42A9-3D23-08DCBCFE539A | TA00214 | FCV Replacement - 060FCV-050 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 30 | Testing/Stroke test with BOCPP-A DCS | A2830 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-29 09:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:57
B9BAAF39-11F4-44D1-3D20-08DCBCFE539A | TA00213 | FCV Replacement - 060FCV-020 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Remove exisiting FCV | A2780 | 2 | 8 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:57
2C1A911D-460A-4519-3D22-08DCBCFE539A | TA00213 | FCV Replacement - 060FCV-020 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Install new FCV at WH Gaslift lines | A2790 | 3 | 18 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:57
4F602C5E-D7AC-40B7-3D21-08DCBCFE539A | TA00213 | FCV Replacement - 060FCV-020 | Bokor | BODP-F |  | Control Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 30 | Testing/Stroke test with BOCPP-A DCS | A2800 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:57
E8A73018-DB7D-4739-3D1E-08DCBCFE539A | TA00212 | SDV Limit Switch Replacement - 646SDV-060 | Bokor | BODP-F |  | Shutdown Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Replacement of SDV limit switches | A2760 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:57
54606888-4A2B-43D3-3D1F-08DCBCFE539A | TA00212 | SDV Limit Switch Replacement - 646SDV-060 | Bokor | BODP-F |  | Shutdown Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Testing/Stroke test with BOCPP-A DCS | A2770 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:57
2C00958A-A37A-47FB-3D1D-08DCBCFE539A | TA00211 | SDV Limit Switch Replacement - 290SDV-061 | Bokor | BODP-F |  | Shutdown Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Replacement of SDV limit switches | A2740 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 14:00 | [6 empty] | 2024-08-15 15:57
E37270C9-AC71-44C8-3D1C-08DCBCFE539A | TA00211 | SDV Limit Switch Replacement - 290SDV-061 | Bokor | BODP-F |  | Shutdown Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Testing/Stroke test with BOCPP-A DCS | A2750 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-26 14:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:57
51B2FD39-A59D-49C8-3D1A-08DCBCFE539A | TA00210 | SDV Limit Switch Replacement - 135SDV-050 | Bokor | BODP-F |  | Shutdown Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 10 | Replacement of SDV limit switches | A2720 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:57
AC2BD70C-138A-4B1B-3D1B-08DCBCFE539A | TA00210 | SDV Limit Switch Replacement - 135SDV-050 | Bokor | BODP-F |  | Shutdown Valve | Project | Maintenance | PPM | Prelim | Project | Execution | 20 | Testing/Stroke test with BOCPP-A DCS | A2730 | 3 | 12 | 0 |  | APROTH00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:57
4FE44321-E8FF-430F-3D19-08DCBCFE539A | TA00209 | 120 MOV-104 | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Remove MOV and valve (120MOV-104) | A2700 | 8 | 48 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:57
1E996EC3-FF33-4277-3D18-08DCBCFE539A | TA00209 | 120 MOV-104 | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 20 | Perform installation of new valve and reinstate MOV (120MOV-104) | A2710 | 8 | 48 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:57
4A3B7E0D-D5C8-4574-3D17-08DCBCFE539A | TA00208 | 120 MOV-103 | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Remove MOV and valve (120MOV-103) | A2680 | 8 | 48 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:57
BE6F85E3-D446-433D-3D16-08DCBCFE539A | TA00208 | 120 MOV-103 | Bokor | BOCPP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 20 | Perform installation of new valve and reinstate MOV (120MOV-103) | A2690 | 8 | 48 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:57
BA9B9B33-9D78-4BAA-3D15-08DCBCFE539A | TA00207 | FE-211 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2670 | 4 | 12 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:57
93A0877E-800B-4483-3D14-08DCBCFE539A | TA00206 | FE-114 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2660 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:57
5FD3FB4F-6BB2-4F96-3D13-08DCBCFE539A | TA00205 | FE-110 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2650 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:57
CE342C0C-552D-4FEA-3D12-08DCBCFE539A | TA00204 | FE-2701 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2640 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:57
15DEAB64-2CAA-4AF3-3D11-08DCBCFE539A | TA00203 | FE-2702 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2630 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:57
C5795F45-443A-455B-3D10-08DCBCFE539A | TA00202 | FE-501 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2620 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:57
F847E323-C1C2-4CD5-3D0F-08DCBCFE539A | TA00201 | FE-503 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2610 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:57
F56CF6C9-DB66-41C8-3D0E-08DCBCFE539A | TA00200 | FE-510 | Betty | BEP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2600 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:57
F3A85D42-2440-4324-3D0D-08DCBCFE539A | TA00199 | FE-505 | Betty | BEDP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2590 | 2 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:57
E7ACFC96-3B1E-4E0E-3D0C-08DCBCFE539A | TA00198 | 602FIA-101B | Bokor | BOCPP-A |  | Flow Switch | Instrument & Control | Maintenance | PPM | Prelim | Metering | Execution | 10 | Perform Orifice plate inspection and replacement | A2580 | 4 | 12 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:57
AFF5BCC1-D974-42BE-3D0B-08DCBCFE539A | TA00197 | 600-PSVA-001 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10960 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 10:48 | 2024-08-31 10:57 | [6 empty] | 2024-08-15 15:57
A18290BB-AFA9-4619-3D08-08DCBCFE539A | TA00197 | 600-PSVA-001 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10970 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 10:57 | 2024-08-31 11:03 | [6 empty] | 2024-08-15 15:57
C2D12A04-18CE-4119-3D09-08DCBCFE539A | TA00197 | 600-PSVA-001 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10980 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 11:03 | 2024-08-31 11:12 | [6 empty] | 2024-08-15 15:57
B093D17A-FFC3-4D3F-3D0A-08DCBCFE539A | TA00197 | 600-PSVA-001 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10990 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 11:12 | 2024-08-31 11:21 | [6 empty] | 2024-08-15 15:57
A3138C49-B591-4FAD-3D05-08DCBCFE539A | TA00196 | 600-PSV-002 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10920 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 10:15 | 2024-08-31 10:24 | [6 empty] | 2024-08-15 15:57
2D968304-E188-475C-3D07-08DCBCFE539A | TA00196 | 600-PSV-002 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10930 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 10:24 | 2024-08-31 10:30 | [6 empty] | 2024-08-15 15:57
F78DDEA7-6E03-45DC-3D04-08DCBCFE539A | TA00196 | 600-PSV-002 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10940 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 10:30 | 2024-08-31 10:39 | [6 empty] | 2024-08-15 15:57
5EBD1B3C-C534-4C08-3D06-08DCBCFE539A | TA00196 | 600-PSV-002 | Laila | LADR-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10950 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 10:39 | 2024-08-31 10:48 | [6 empty] | 2024-08-15 15:57
F9FFAC4F-E581-4269-3D01-08DCBCFE539A | TA00195 | RV942 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10880 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:27 | 2024-08-26 15:36 | [6 empty] | 2024-08-15 15:57
0EB3CE4B-812F-499A-3D02-08DCBCFE539A | TA00195 | RV942 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10890 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:36 | 2024-08-26 15:42 | [6 empty] | 2024-08-15 15:57
F61FE613-15F8-41A9-3D03-08DCBCFE539A | TA00195 | RV942 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10900 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:42 | 2024-08-26 15:51 | [6 empty] | 2024-08-15 15:57
DDBE4627-7517-4291-3D00-08DCBCFE539A | TA00195 | RV942 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10910 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:51 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:57
398C1B0C-C12C-4F0D-3CFD-08DCBCFE539A | TA00194 | RV0601 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10840 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:54 | 2024-08-26 15:03 | [6 empty] | 2024-08-15 15:57
11FA9CFF-A218-475E-3CFF-08DCBCFE539A | TA00194 | RV0601 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10850 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:03 | 2024-08-26 15:09 | [6 empty] | 2024-08-15 15:57
33A17753-1E41-402F-3CFE-08DCBCFE539A | TA00194 | RV0601 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10860 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:09 | 2024-08-26 15:18 | [6 empty] | 2024-08-15 15:57
D9638B89-552A-4C64-3CFC-08DCBCFE539A | TA00194 | RV0601 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10870 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:18 | 2024-08-26 15:27 | [6 empty] | 2024-08-15 15:57
EC1EFD8C-82DC-4B5B-3CFB-08DCBCFE539A | TA00193 | RV1604 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10800 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:21 | 2024-08-26 14:30 | [6 empty] | 2024-08-15 15:57
EC41A83C-8E2F-4390-3CF9-08DCBCFE539A | TA00193 | RV1604 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10810 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:30 | 2024-08-26 14:36 | [6 empty] | 2024-08-15 15:57
E4DAF165-29F3-49F0-3CFA-08DCBCFE539A | TA00193 | RV1604 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10820 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:36 | 2024-08-26 14:45 | [6 empty] | 2024-08-15 15:57
A7DAC0D5-F484-4FDB-3CF8-08DCBCFE539A | TA00193 | RV1604 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10830 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:45 | 2024-08-26 14:54 | [6 empty] | 2024-08-15 15:57
8CCA5F60-5AB3-41E9-3CF7-08DCBCFE539A | TA00192 | RV9111B | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10760 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:48 | 2024-08-26 13:57 | [6 empty] | 2024-08-15 15:57
CCD741F0-089F-4BCD-3CF6-08DCBCFE539A | TA00192 | RV9111B | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10770 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:57 | 2024-08-26 14:03 | [6 empty] | 2024-08-15 15:57
EC84435C-1058-4197-3CF4-08DCBCFE539A | TA00192 | RV9111B | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10780 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:03 | 2024-08-26 14:12 | [6 empty] | 2024-08-15 15:57
C860CAC0-9DBE-4EB2-3CF5-08DCBCFE539A | TA00192 | RV9111B | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10790 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:12 | 2024-08-26 14:21 | [6 empty] | 2024-08-15 15:57
73BBE401-AC60-477F-3CF1-08DCBCFE539A | TA00191 | RV9111A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10720 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:15 | 2024-08-26 13:24 | [6 empty] | 2024-08-15 15:57
6F3483E4-2435-4C51-3CF2-08DCBCFE539A | TA00191 | RV9111A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10730 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:24 | 2024-08-26 13:30 | [6 empty] | 2024-08-15 15:57
E45CB223-4B23-434C-3CF0-08DCBCFE539A | TA00191 | RV9111A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10740 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:30 | 2024-08-26 13:39 | [6 empty] | 2024-08-15 15:57
614EF11E-782C-4CA0-3CF3-08DCBCFE539A | TA00191 | RV9111A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10750 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:39 | 2024-08-26 13:48 | [6 empty] | 2024-08-15 15:57
56BBA4D2-5D55-411A-3CEC-08DCBCFE539A | TA00190 | RV9121A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10680 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:42 | 2024-08-26 11:51 | [6 empty] | 2024-08-15 15:57
CFCCC145-AD1B-43E6-3CED-08DCBCFE539A | TA00190 | RV9121A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10690 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:51 | 2024-08-26 11:57 | [6 empty] | 2024-08-15 15:57
9DEB69B8-94ED-44E0-3CEE-08DCBCFE539A | TA00190 | RV9121A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10700 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:57 | 2024-08-26 13:06 | [6 empty] | 2024-08-15 15:57
8C04D164-1552-4D6B-3CEF-08DCBCFE539A | TA00190 | RV9121A | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10710 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:06 | 2024-08-26 13:15 | [6 empty] | 2024-08-15 15:57
FB5C53C5-6278-47A0-3CEA-08DCBCFE539A | TA00189 | RV0611 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10640 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:09 | 2024-08-26 11:18 | [6 empty] | 2024-08-15 15:57
DAE3B22B-CFA0-41F2-3CE9-08DCBCFE539A | TA00189 | RV0611 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10650 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:18 | 2024-08-26 11:24 | [6 empty] | 2024-08-15 15:57
1DEB08AD-CBFD-4C0C-3CE8-08DCBCFE539A | TA00189 | RV0611 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10660 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:24 | 2024-08-26 11:33 | [6 empty] | 2024-08-15 15:57
D492C1AC-CB70-410E-3CEB-08DCBCFE539A | TA00189 | RV0611 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10670 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:33 | 2024-08-26 11:42 | [6 empty] | 2024-08-15 15:57
ABAD7B7D-EF94-4537-3CE7-08DCBCFE539A | TA00188 | RV941 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10600 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:36 | 2024-08-26 10:45 | [6 empty] | 2024-08-15 15:57
6F2973F7-CB5B-4615-3CE4-08DCBCFE539A | TA00188 | RV941 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10610 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:45 | 2024-08-26 10:51 | [6 empty] | 2024-08-15 15:57
3252523D-2251-43DA-3CE5-08DCBCFE539A | TA00188 | RV941 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10620 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:51 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:57
D8C2D71B-3E31-412A-3CE6-08DCBCFE539A | TA00188 | RV941 | Betty | BEP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10630 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 11:09 | [6 empty] | 2024-08-15 15:57
58F4BA49-3213-451D-3CE1-08DCBCFE539A | TA00187 | RV 27 LB | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10560 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:03 | 2024-08-26 10:12 | [6 empty] | 2024-08-15 15:57
26CED75F-5DA3-46A1-3CE2-08DCBCFE539A | TA00187 | RV 27 LB | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10570 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:12 | 2024-08-26 10:18 | [6 empty] | 2024-08-15 15:57
9571801C-91AE-46AB-3CE3-08DCBCFE539A | TA00187 | RV 27 LB | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10580 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:18 | 2024-08-26 10:27 | [6 empty] | 2024-08-15 15:57
682E61D8-EA09-4060-3CE0-08DCBCFE539A | TA00187 | RV 27 LB | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10590 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:27 | 2024-08-26 10:36 | [6 empty] | 2024-08-15 15:57
F49D0853-09A2-4C70-3CDC-08DCBCFE539A | TA00186 | RV SP 1C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10520 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:30 | 2024-08-26 09:39 | [6 empty] | 2024-08-15 15:57
C5D2E094-C770-4593-3CDD-08DCBCFE539A | TA00186 | RV SP 1C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10530 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:39 | 2024-08-26 09:45 | [6 empty] | 2024-08-15 15:57
1F5ADEC3-D1B6-4F6B-3CDF-08DCBCFE539A | TA00186 | RV SP 1C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10540 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:45 | 2024-08-26 09:54 | [6 empty] | 2024-08-15 15:57
D7BBE7B9-7D4A-4068-3CDE-08DCBCFE539A | TA00186 | RV SP 1C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10550 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:54 | 2024-08-26 10:03 | [6 empty] | 2024-08-15 15:57
013B9E5F-2A9C-48F5-3CDA-08DCBCFE539A | TA00185 | RV 18L C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10480 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:57 | 2024-08-26 09:06 | [6 empty] | 2024-08-15 15:57
7A20DBD7-A186-4EDB-3CD8-08DCBCFE539A | TA00185 | RV 18L C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10490 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:06 | 2024-08-26 09:12 | [6 empty] | 2024-08-15 15:57
2AD79730-1ECB-4EC6-3CD9-08DCBCFE539A | TA00185 | RV 18L C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10500 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:12 | 2024-08-26 09:21 | [6 empty] | 2024-08-15 15:57
EBD8023F-282F-4AB6-3CDB-08DCBCFE539A | TA00185 | RV 18L C | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10510 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:21 | 2024-08-26 09:30 | [6 empty] | 2024-08-15 15:57
9862E4BC-B738-4864-3CD4-08DCBCFE539A | TA00184 | PSV AN-1 WHCM SPARE #2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10440 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:24 | 2024-08-26 08:33 | [6 empty] | 2024-08-15 15:57
864E4209-6ECA-488A-3CD6-08DCBCFE539A | TA00184 | PSV AN-1 WHCM SPARE #2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10450 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:33 | 2024-08-26 08:39 | [6 empty] | 2024-08-15 15:57
C95BB96B-BA57-4A1B-3CD7-08DCBCFE539A | TA00184 | PSV AN-1 WHCM SPARE #2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10460 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:39 | 2024-08-26 08:48 | [6 empty] | 2024-08-15 15:57
C68CCC45-1BED-4B80-3CD5-08DCBCFE539A | TA00184 | PSV AN-1 WHCM SPARE #2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10470 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:48 | 2024-08-26 08:57 | [6 empty] | 2024-08-15 15:57
2AE09F6B-081C-4226-3CD0-08DCBCFE539A | TA00183 | PSV AN-1 WHCM SPARE #1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10400 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:51 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:57
CA3883A0-303D-4269-3CD2-08DCBCFE539A | TA00183 | PSV AN-1 WHCM SPARE #1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10410 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 08:06 | [6 empty] | 2024-08-15 15:57
83F84E6D-5F2D-41D5-3CD3-08DCBCFE539A | TA00183 | PSV AN-1 WHCM SPARE #1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10420 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:06 | 2024-08-26 08:15 | [6 empty] | 2024-08-15 15:57
2CA4FD96-0C61-47B8-3CD1-08DCBCFE539A | TA00183 | PSV AN-1 WHCM SPARE #1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10430 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:15 | 2024-08-26 08:24 | [6 empty] | 2024-08-15 15:57
29895B46-EED7-4DD7-3CCF-08DCBCFE539A | TA00182 | PSV AK-2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10360 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:18 | 2024-08-25 16:27 | [6 empty] | 2024-08-15 15:57
F38EBE96-5FE0-4AB6-3CCC-08DCBCFE539A | TA00182 | PSV AK-2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10370 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:27 | 2024-08-25 16:33 | [6 empty] | 2024-08-15 15:57
3EB41EBA-1A12-4F27-3CCD-08DCBCFE539A | TA00182 | PSV AK-2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10380 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:33 | 2024-08-25 16:42 | [6 empty] | 2024-08-15 15:57
3469F254-1BB9-4EE0-3CCE-08DCBCFE539A | TA00182 | PSV AK-2 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10390 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:42 | 2024-08-25 16:51 | [6 empty] | 2024-08-15 15:57
24D755E8-E074-4D33-3CCA-08DCBCFE539A | TA00181 | RV 12S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10320 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:45 | 2024-08-25 15:54 | [6 empty] | 2024-08-15 15:57
E46CAC44-737B-4AA9-3CC8-08DCBCFE539A | TA00181 | RV 12S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10330 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:54 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:57
FE31831F-556A-4205-3CC9-08DCBCFE539A | TA00181 | RV 12S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10340 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 16:09 | [6 empty] | 2024-08-15 15:57
78CC84E1-AA70-4082-3CCB-08DCBCFE539A | TA00181 | RV 12S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10350 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:09 | 2024-08-25 16:18 | [6 empty] | 2024-08-15 15:57
71D12307-FC48-4C9F-3CC4-08DCBCFE539A | TA00180 | PSV AK-1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10280 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:12 | 2024-08-25 15:21 | [6 empty] | 2024-08-15 15:57
7B3BA189-A323-42AB-3CC7-08DCBCFE539A | TA00180 | PSV AK-1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10290 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:21 | 2024-08-25 15:27 | [6 empty] | 2024-08-15 15:57
67AB0AC8-767A-460D-3CC5-08DCBCFE539A | TA00180 | PSV AK-1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10300 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:27 | 2024-08-25 15:36 | [6 empty] | 2024-08-15 15:57
09ECC8B8-8F6E-48B3-3CC6-08DCBCFE539A | TA00180 | PSV AK-1 | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10310 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:36 | 2024-08-25 15:45 | [6 empty] | 2024-08-15 15:57
97AC897C-CBA7-4414-3CC3-08DCBCFE539A | TA00179 | RV 21L A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10240 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:39 | 2024-08-25 14:48 | [6 empty] | 2024-08-15 15:57
72B1779F-85E6-4EFF-3CC0-08DCBCFE539A | TA00179 | RV 21L A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10250 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:48 | 2024-08-25 14:54 | [6 empty] | 2024-08-15 15:57
E1C26FA6-D2BC-4953-3CC1-08DCBCFE539A | TA00179 | RV 21L A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10260 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:54 | 2024-08-25 15:03 | [6 empty] | 2024-08-15 15:57
21B2C971-0C97-43AC-3CC2-08DCBCFE539A | TA00179 | RV 21L A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10270 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:03 | 2024-08-25 15:12 | [6 empty] | 2024-08-15 15:57
2941ECAF-98EA-4F22-3CBE-08DCBCFE539A | TA00178 | RV 18S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10200 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:06 | 2024-08-25 14:15 | [6 empty] | 2024-08-15 15:57
4C0BF38C-00AB-4295-3CBD-08DCBCFE539A | TA00178 | RV 18S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10210 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:15 | 2024-08-25 14:21 | [6 empty] | 2024-08-15 15:57
31D00630-3426-4A03-3CBC-08DCBCFE539A | TA00178 | RV 18S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10220 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:21 | 2024-08-25 14:30 | [6 empty] | 2024-08-15 15:57
5C5E8C35-1471-4216-3CBF-08DCBCFE539A | TA00178 | RV 18S A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10230 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:30 | 2024-08-25 14:39 | [6 empty] | 2024-08-15 15:57
866ADFDB-49C5-4D43-3CB9-08DCBCFE539A | TA00177 | RV1202B | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10160 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:33 | 2024-08-25 13:42 | [6 empty] | 2024-08-15 15:57
8403F791-73D8-46FD-3CB8-08DCBCFE539A | TA00177 | RV1202B | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10170 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:42 | 2024-08-25 13:48 | [6 empty] | 2024-08-15 15:57
A66D65AD-ADD1-4394-3CBB-08DCBCFE539A | TA00177 | RV1202B | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10180 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:48 | 2024-08-25 13:57 | [6 empty] | 2024-08-15 15:57
6DD38C7D-5B1B-41B8-3CBA-08DCBCFE539A | TA00177 | RV1202B | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10190 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:57 | 2024-08-25 14:06 | [6 empty] | 2024-08-15 15:57
99E079BA-FD26-432D-3CB6-08DCBCFE539A | TA00176 | RV1202A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10120 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:09 | [6 empty] | 2024-08-15 15:57
7D254057-F6DC-4377-3CB7-08DCBCFE539A | TA00176 | RV1202A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10130 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:09 | 2024-08-25 13:15 | [6 empty] | 2024-08-15 15:57
54BC8215-3C95-4081-3CB4-08DCBCFE539A | TA00176 | RV1202A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10140 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:15 | 2024-08-25 13:24 | [6 empty] | 2024-08-15 15:57
953E9BC4-8DFA-40C8-3CB5-08DCBCFE539A | TA00176 | RV1202A | Betty | BEDP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10150 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:24 | 2024-08-25 13:33 | [6 empty] | 2024-08-15 15:57
72448822-B25E-419A-3CB2-08DCBCFE539A | TA00175 | RV6520 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10080 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:51 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:57
C189FD82-54AD-45BE-3CB1-08DCBCFE539A | TA00175 | RV6520 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10090 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:00 | 2024-08-30 13:06 | [6 empty] | 2024-08-15 15:57
7AA1E4CF-D375-4BB7-3CB3-08DCBCFE539A | TA00175 | RV6520 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10100 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:06 | 2024-08-30 13:15 | [6 empty] | 2024-08-15 15:57
0898D342-FD81-41E9-3CB0-08DCBCFE539A | TA00175 | RV6520 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10110 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:15 | 2024-08-30 13:24 | [6 empty] | 2024-08-15 15:57
D4042D15-B3F7-4657-3CAC-08DCBCFE539A | TA00174 | RV0502 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10040 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:18 | 2024-08-29 11:27 | [6 empty] | 2024-08-15 15:57
0C9B8BF3-62E6-4F27-3CAD-08DCBCFE539A | TA00174 | RV0502 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10050 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:27 | 2024-08-29 11:33 | [6 empty] | 2024-08-15 15:57
92B049A2-D0AC-4E11-3CAF-08DCBCFE539A | TA00174 | RV0502 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10060 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:33 | 2024-08-29 11:42 | [6 empty] | 2024-08-15 15:57
AEB7B9D2-D51F-47F6-3CAE-08DCBCFE539A | TA00174 | RV0502 | Bokor | BOP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10070 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:42 | 2024-08-29 11:51 | [6 empty] | 2024-08-15 15:57
D3096E26-8F10-4A5F-3CAA-08DCBCFE539A | TA00173 | PSV1202-E | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A10000 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:45 | 2024-08-29 10:54 | [6 empty] | 2024-08-15 15:57
FFB77697-C60E-44D8-3CA9-08DCBCFE539A | TA00173 | PSV1202-E | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A10010 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:54 | 2024-08-29 11:00 | [6 empty] | 2024-08-15 15:57
F1E82597-03AC-46B4-3CAB-08DCBCFE539A | TA00173 | PSV1202-E | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A10020 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:00 | 2024-08-29 11:09 | [6 empty] | 2024-08-15 15:57
ED9AAABA-AC81-4B7E-3CA8-08DCBCFE539A | TA00173 | PSV1202-E | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A10030 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:09 | 2024-08-29 11:18 | [6 empty] | 2024-08-15 15:57
18496DE7-FBE0-43CE-3CA5-08DCBCFE539A | TA00172 | RV8161 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9960 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:12 | 2024-08-29 10:21 | [6 empty] | 2024-08-15 15:57
D00D6168-C567-4100-3CA6-08DCBCFE539A | TA00172 | RV8161 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9970 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:21 | 2024-08-29 10:27 | [6 empty] | 2024-08-15 15:57
9513762D-2ACD-469B-3CA7-08DCBCFE539A | TA00172 | RV8161 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9980 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:27 | 2024-08-29 10:36 | [6 empty] | 2024-08-15 15:57
B0F0293F-AA3C-469D-3CA4-08DCBCFE539A | TA00172 | RV8161 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9990 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:36 | 2024-08-29 10:45 | [6 empty] | 2024-08-15 15:57
F0CB04BD-3533-4B70-3CA0-08DCBCFE539A | TA00171 | PSV1202-D | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9920 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:39 | 2024-08-29 09:48 | [6 empty] | 2024-08-15 15:57
D1023A41-661D-4CDE-3CA2-08DCBCFE539A | TA00171 | PSV1202-D | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9930 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:48 | 2024-08-29 09:54 | [6 empty] | 2024-08-15 15:57
786FC482-7702-42C1-3CA3-08DCBCFE539A | TA00171 | PSV1202-D | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9940 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:54 | 2024-08-29 10:03 | [6 empty] | 2024-08-15 15:57
DED88D0B-B919-4853-3CA1-08DCBCFE539A | TA00171 | PSV1202-D | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9950 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:03 | 2024-08-29 10:12 | [6 empty] | 2024-08-15 15:57
CF8FDC2E-B6C6-4E2F-3C9F-08DCBCFE539A | TA00170 | RV6812 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9880 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:06 | 2024-08-29 09:15 | [6 empty] | 2024-08-15 15:57
48326BDC-AA24-4B54-3C9E-08DCBCFE539A | TA00170 | RV6812 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9890 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:15 | 2024-08-29 09:21 | [6 empty] | 2024-08-15 15:57
9B5428B4-D40F-4FF7-3C9C-08DCBCFE539A | TA00170 | RV6812 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9900 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:21 | 2024-08-29 09:30 | [6 empty] | 2024-08-15 15:57
EFADE1E1-E97A-42FC-3C9D-08DCBCFE539A | TA00170 | RV6812 | Bokor | BOK-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9910 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:30 | 2024-08-29 09:39 | [6 empty] | 2024-08-15 15:57
4EF8C3BB-8DCD-4D7B-3C98-08DCBCFE539A | TA00169 | 646SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9840 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:09 | 2024-08-31 09:18 | [6 empty] | 2024-08-15 15:57
0A50E769-7680-4C35-3C9A-08DCBCFE539A | TA00169 | 646SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9850 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:18 | 2024-08-31 09:24 | [6 empty] | 2024-08-15 15:57
C2C7A66B-D047-481E-3C99-08DCBCFE539A | TA00169 | 646SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9860 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:24 | 2024-08-31 09:33 | [6 empty] | 2024-08-15 15:57
57481B2E-CA6B-4D93-3C9B-08DCBCFE539A | TA00169 | 646SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9870 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:33 | 2024-08-31 09:42 | [6 empty] | 2024-08-15 15:57
86F851EC-3C50-45AF-3C95-08DCBCFE539A | TA00168 | 060SDV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9800 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 08:36 | 2024-08-31 08:45 | [6 empty] | 2024-08-15 15:57
5978AD56-D38B-493B-3C96-08DCBCFE539A | TA00168 | 060SDV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9810 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 08:45 | 2024-08-31 08:51 | [6 empty] | 2024-08-15 15:57
5981A097-49A7-4200-3C97-08DCBCFE539A | TA00168 | 060SDV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9820 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 08:51 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:57
40F12346-18C1-4EE1-3C94-08DCBCFE539A | TA00168 | 060SDV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9830 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 09:09 | [6 empty] | 2024-08-15 15:57
CC365F30-FEF9-4AA4-3C92-08DCBCFE539A | TA00167 | 060FCV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9760 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 08:03 | 2024-08-31 08:12 | [6 empty] | 2024-08-15 15:57
8C341981-FCE7-42EA-3C90-08DCBCFE539A | TA00167 | 060FCV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9770 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 08:12 | 2024-08-31 08:18 | [6 empty] | 2024-08-15 15:57
CCDACC17-F85A-4C2A-3C93-08DCBCFE539A | TA00167 | 060FCV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9780 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 08:18 | 2024-08-31 08:27 | [6 empty] | 2024-08-15 15:57
03DB8507-E30C-4CBA-3C91-08DCBCFE539A | TA00167 | 060FCV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9790 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 08:27 | 2024-08-31 08:36 | [6 empty] | 2024-08-15 15:57
1B261141-E350-4D57-3C8D-08DCBCFE539A | TA00166 | 060FCV-050 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9720 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 16:30 | 2024-08-30 16:39 | [6 empty] | 2024-08-15 15:57
7E6A7AC4-5A62-46ED-3C8E-08DCBCFE539A | TA00166 | 060FCV-050 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9730 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 16:39 | 2024-08-30 16:45 | [6 empty] | 2024-08-15 15:57
6DF5D019-1021-4D78-3C8C-08DCBCFE539A | TA00166 | 060FCV-050 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9740 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 16:45 | 2024-08-30 16:54 | [6 empty] | 2024-08-15 15:57
498E000F-E8BD-48C6-3C8F-08DCBCFE539A | TA00166 | 060FCV-050 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9750 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 16:54 | 2024-08-31 08:03 | [6 empty] | 2024-08-15 15:57
EE4BFD11-87E2-4699-3C89-08DCBCFE539A | TA00165 | 060FCV-020 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9680 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:57 | 2024-08-30 16:06 | [6 empty] | 2024-08-15 15:57
EEDFC6F6-B120-433D-3C8B-08DCBCFE539A | TA00165 | 060FCV-020 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9690 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 16:06 | 2024-08-30 16:12 | [6 empty] | 2024-08-15 15:57
BD3F5059-B797-40AF-3C88-08DCBCFE539A | TA00165 | 060FCV-020 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9700 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 16:12 | 2024-08-30 16:21 | [6 empty] | 2024-08-15 15:57
D52A3909-531E-4095-3C8A-08DCBCFE539A | TA00165 | 060FCV-020 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9710 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 16:21 | 2024-08-30 16:30 | [6 empty] | 2024-08-15 15:57
1985B1A1-8993-499A-3C86-08DCBCFE539A | TA00164 | 060FCV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9640 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:24 | 2024-08-30 15:33 | [6 empty] | 2024-08-15 15:57
0E37CD5E-58F0-46C4-3C85-08DCBCFE539A | TA00164 | 060FCV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9650 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:33 | 2024-08-30 15:39 | [6 empty] | 2024-08-15 15:57
A4DE3D19-8DE2-415A-3C87-08DCBCFE539A | TA00164 | 060FCV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9660 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:39 | 2024-08-30 15:48 | [6 empty] | 2024-08-15 15:57
E6705D96-7DCB-4976-3C84-08DCBCFE539A | TA00164 | 060FCV-002 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9670 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:48 | 2024-08-30 15:57 | [6 empty] | 2024-08-15 15:57
C71FF799-C5FF-41DE-3C80-08DCBCFE539A | TA00163 | M3 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9600 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 14:51 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:57
9CC7568C-31BD-4AB2-3C81-08DCBCFE539A | TA00163 | M3 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9610 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-30 15:06 | [6 empty] | 2024-08-15 15:57
C7882819-2C2A-4F7A-3C82-08DCBCFE539A | TA00163 | M3 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9620 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:06 | 2024-08-30 15:15 | [6 empty] | 2024-08-15 15:57
3636CE21-0219-4F25-3C83-08DCBCFE539A | TA00163 | M3 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9630 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 15:15 | 2024-08-30 15:24 | [6 empty] | 2024-08-15 15:57
D640E040-1851-4E65-3C7D-08DCBCFE539A | TA00162 | M2 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9560 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 14:18 | 2024-08-30 14:27 | [6 empty] | 2024-08-15 15:57
AC286AC9-52F5-4553-3C7F-08DCBCFE539A | TA00162 | M2 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9570 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 14:27 | 2024-08-30 14:33 | [6 empty] | 2024-08-15 15:57
DFF621A5-5FE9-4A64-3C7C-08DCBCFE539A | TA00162 | M2 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9580 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 14:33 | 2024-08-30 14:42 | [6 empty] | 2024-08-15 15:57
8792AD8E-3666-44FE-3C7E-08DCBCFE539A | TA00162 | M2 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9590 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 14:42 | 2024-08-30 14:51 | [6 empty] | 2024-08-15 15:57
435B2BDF-052C-42A7-3C7B-08DCBCFE539A | TA00161 | M1 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9520 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:45 | 2024-08-30 13:54 | [6 empty] | 2024-08-15 15:57
27AA2304-1756-492B-3C78-08DCBCFE539A | TA00161 | M1 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9530 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:54 | 2024-08-30 14:00 | [6 empty] | 2024-08-15 15:57
F4CA2C8D-7EE1-4B7B-3C79-08DCBCFE539A | TA00161 | M1 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9540 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 14:00 | 2024-08-30 14:09 | [6 empty] | 2024-08-15 15:57
B0CC9C1A-996D-42B2-3C7A-08DCBCFE539A | TA00161 | M1 MP LOGIC | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9550 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 14:09 | 2024-08-30 14:18 | [6 empty] | 2024-08-15 15:57
A7A610D5-EE8A-44DF-3C76-08DCBCFE539A | TA00160 | M5 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9480 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:12 | 2024-08-30 13:21 | [6 empty] | 2024-08-15 15:57
3AEA4504-7AAB-4971-3C74-08DCBCFE539A | TA00160 | M5 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9490 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:21 | 2024-08-30 13:27 | [6 empty] | 2024-08-15 15:57
29586FD0-869D-46D7-3C75-08DCBCFE539A | TA00160 | M5 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9500 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:27 | 2024-08-30 13:36 | [6 empty] | 2024-08-15 15:57
1F98A4C9-4B3E-4C1B-3C77-08DCBCFE539A | TA00160 | M5 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9510 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:36 | 2024-08-30 13:45 | [6 empty] | 2024-08-15 15:57
7828353A-9BDE-4609-3C72-08DCBCFE539A | TA00159 | M4 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9440 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 11:39 | 2024-08-30 11:48 | [6 empty] | 2024-08-15 15:57
CC6B7CEA-6C9C-4AD7-3C73-08DCBCFE539A | TA00159 | M4 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9450 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 11:48 | 2024-08-30 11:54 | [6 empty] | 2024-08-15 15:57
85875551-EB4F-40A9-3C70-08DCBCFE539A | TA00159 | M4 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9460 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 11:54 | 2024-08-30 13:03 | [6 empty] | 2024-08-15 15:57
9F84D20A-9C3D-4176-3C71-08DCBCFE539A | TA00159 | M4 SDV/BDV MOTOR | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9470 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 13:03 | 2024-08-30 13:12 | [6 empty] | 2024-08-15 15:57
5C5B6D5D-C4BC-4671-3C6C-08DCBCFE539A | TA00158 | M3 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9400 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 11:06 | 2024-08-30 11:15 | [6 empty] | 2024-08-15 15:57
126A298B-34AB-49E7-3C6D-08DCBCFE539A | TA00158 | M3 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9410 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 11:15 | 2024-08-30 11:21 | [6 empty] | 2024-08-15 15:57
9D7CAC1E-28CB-4078-3C6F-08DCBCFE539A | TA00158 | M3 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9420 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 11:21 | 2024-08-30 11:30 | [6 empty] | 2024-08-15 15:57
7D921C75-A929-4F22-3C6E-08DCBCFE539A | TA00158 | M3 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9430 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 11:30 | 2024-08-30 11:39 | [6 empty] | 2024-08-15 15:57
E5C53FB1-24D0-47BA-3C68-08DCBCFE539A | TA00157 | M2 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9360 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:33 | 2024-08-30 10:42 | [6 empty] | 2024-08-15 15:57
FE5F9334-B929-4835-3C6A-08DCBCFE539A | TA00157 | M2 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9370 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:42 | 2024-08-30 10:48 | [6 empty] | 2024-08-15 15:57
BF16D4E7-7298-40DC-3C6B-08DCBCFE539A | TA00157 | M2 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9380 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:48 | 2024-08-30 10:57 | [6 empty] | 2024-08-15 15:57
1A69FB25-876D-4181-3C69-08DCBCFE539A | TA00157 | M2 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9390 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:57 | 2024-08-30 11:06 | [6 empty] | 2024-08-15 15:57
19AFA02F-C5D6-4487-3C67-08DCBCFE539A | TA00156 | M1 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9320 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:00 | 2024-08-30 10:09 | [6 empty] | 2024-08-15 15:57
0840EC34-FF16-4EE7-3C64-08DCBCFE539A | TA00156 | M1 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9330 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:09 | 2024-08-30 10:15 | [6 empty] | 2024-08-15 15:57
B36BB350-5317-44B4-3C66-08DCBCFE539A | TA00156 | M1 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9340 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:15 | 2024-08-30 10:24 | [6 empty] | 2024-08-15 15:57
823D5F87-36B0-46C5-3C65-08DCBCFE539A | TA00156 | M1 SCSSV/SSV/WV | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9350 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 10:24 | 2024-08-30 10:33 | [6 empty] | 2024-08-15 15:57
42D473E9-17DF-4B77-3C61-08DCBCFE539A | TA00155 | ML-1 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9280 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 09:27 | 2024-08-30 09:36 | [6 empty] | 2024-08-15 15:57
779E6302-3C0A-45D8-3C63-08DCBCFE539A | TA00155 | ML-1 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9290 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 09:36 | 2024-08-30 09:42 | [6 empty] | 2024-08-15 15:57
5C5B755F-DA66-4156-3C62-08DCBCFE539A | TA00155 | ML-1 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9300 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 09:42 | 2024-08-30 09:51 | [6 empty] | 2024-08-15 15:57
AB2B0F28-97DC-47C1-3C60-08DCBCFE539A | TA00155 | ML-1 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9310 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 09:51 | 2024-08-30 10:00 | [6 empty] | 2024-08-15 15:57
9230EEC2-0040-4ADA-3C5C-08DCBCFE539A | TA00154 | ML-2 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9240 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 08:54 | 2024-08-30 09:03 | [6 empty] | 2024-08-15 15:57
314CD4BE-4C7E-4985-3C5F-08DCBCFE539A | TA00154 | ML-2 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9250 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 09:03 | 2024-08-30 09:09 | [6 empty] | 2024-08-15 15:57
6CBEC907-477F-4BD8-3C5E-08DCBCFE539A | TA00154 | ML-2 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9260 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 09:09 | 2024-08-30 09:18 | [6 empty] | 2024-08-15 15:57
842BA732-3EF3-4320-3C5D-08DCBCFE539A | TA00154 | ML-2 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9270 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 09:18 | 2024-08-30 09:27 | [6 empty] | 2024-08-15 15:57
EE3D8F66-FB73-48FE-3C59-08DCBCFE539A | TA00153 | ML-3 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9200 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 08:21 | 2024-08-30 08:30 | [6 empty] | 2024-08-15 15:57
3794342B-E664-482E-3C5A-08DCBCFE539A | TA00153 | ML-3 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9210 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 08:30 | 2024-08-30 08:36 | [6 empty] | 2024-08-15 15:57
05A03A22-7E68-4E31-3C58-08DCBCFE539A | TA00153 | ML-3 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9220 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 08:36 | 2024-08-30 08:45 | [6 empty] | 2024-08-15 15:57
10E5927E-5AB3-4438-3C5B-08DCBCFE539A | TA00153 | ML-3 BO 606 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9230 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 08:45 | 2024-08-30 08:54 | [6 empty] | 2024-08-15 15:57
544A97CE-7AEA-41C4-3C57-08DCBCFE539A | TA00152 | ML-1 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9160 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 16:48 | 2024-08-29 16:57 | [6 empty] | 2024-08-15 15:57
5E1C78D7-86D9-458B-3C56-08DCBCFE539A | TA00152 | ML-1 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9170 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 16:57 | 2024-08-30 08:03 | [6 empty] | 2024-08-15 15:57
E76616AF-41E9-4329-3C54-08DCBCFE539A | TA00152 | ML-1 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9180 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 08:03 | 2024-08-30 08:12 | [6 empty] | 2024-08-15 15:57
957C4608-F57B-4D32-3C55-08DCBCFE539A | TA00152 | ML-1 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9190 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-30 08:12 | 2024-08-30 08:21 | [6 empty] | 2024-08-15 15:57
69E6B9A6-61A4-4316-3C50-08DCBCFE539A | TA00151 | ML-2 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9120 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 16:15 | 2024-08-29 16:24 | [6 empty] | 2024-08-15 15:57
7EDBC9F1-1C97-4D34-3C51-08DCBCFE539A | TA00151 | ML-2 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9130 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 16:24 | 2024-08-29 16:30 | [6 empty] | 2024-08-15 15:57
513F6501-8E9D-44CD-3C53-08DCBCFE539A | TA00151 | ML-2 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9140 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 16:30 | 2024-08-29 16:39 | [6 empty] | 2024-08-15 15:57
6D90D84A-4F96-4C7F-3C52-08DCBCFE539A | TA00151 | ML-2 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9150 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 16:39 | 2024-08-29 16:48 | [6 empty] | 2024-08-15 15:57
325F934B-F26F-47F6-3C4F-08DCBCFE539A | TA00150 | ML-3 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9080 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:42 | 2024-08-29 15:51 | [6 empty] | 2024-08-15 15:57
0BA2F4BD-7DD9-4780-3C4C-08DCBCFE539A | TA00150 | ML-3 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9090 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:51 | 2024-08-29 15:57 | [6 empty] | 2024-08-15 15:57
1ACA8E1F-8E44-4ED3-3C4E-08DCBCFE539A | TA00150 | ML-3 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9100 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:57 | 2024-08-29 16:06 | [6 empty] | 2024-08-15 15:57
3D117E6A-7706-4F2D-3C4D-08DCBCFE539A | TA00150 | ML-3 BO 605 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9110 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 16:06 | 2024-08-29 16:15 | [6 empty] | 2024-08-15 15:57
97D41E0E-5707-4EE0-3C49-08DCBCFE539A | TA00149 | ML-1 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9040 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:09 | 2024-08-29 15:18 | [6 empty] | 2024-08-15 15:57
35B8D39F-1145-47A2-3C48-08DCBCFE539A | TA00149 | ML-1 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9050 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:18 | 2024-08-29 15:24 | [6 empty] | 2024-08-15 15:57
CE106DB0-1FD3-4421-3C4B-08DCBCFE539A | TA00149 | ML-1 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9060 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:24 | 2024-08-29 15:33 | [6 empty] | 2024-08-15 15:57
E5FD7859-48CD-4276-3C4A-08DCBCFE539A | TA00149 | ML-1 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9070 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:33 | 2024-08-29 15:42 | [6 empty] | 2024-08-15 15:57
5B5B7CCA-3515-4C5D-3C45-08DCBCFE539A | TA00148 | ML-2 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A9000 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 14:36 | 2024-08-29 14:45 | [6 empty] | 2024-08-15 15:57
98DB81F1-9FB3-4008-3C44-08DCBCFE539A | TA00148 | ML-2 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A9010 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 14:45 | 2024-08-29 14:51 | [6 empty] | 2024-08-15 15:57
4EB7EE6D-1A8B-416B-3C47-08DCBCFE539A | TA00148 | ML-2 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A9020 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 14:51 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:57
2739B370-0D86-47B3-3C46-08DCBCFE539A | TA00148 | ML-2 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A9030 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-29 15:09 | [6 empty] | 2024-08-15 15:57
64FC553A-4962-4719-3C43-08DCBCFE539A | TA00147 | ML-3 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8960 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 14:03 | 2024-08-29 14:12 | [6 empty] | 2024-08-15 15:57
58AAE65D-87EA-4D73-3C41-08DCBCFE539A | TA00147 | ML-3 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8970 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 14:12 | 2024-08-29 14:18 | [6 empty] | 2024-08-15 15:57
629F4539-6C1B-4455-3C42-08DCBCFE539A | TA00147 | ML-3 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8980 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 14:18 | 2024-08-29 14:27 | [6 empty] | 2024-08-15 15:57
5C296068-C7DB-41ED-3C40-08DCBCFE539A | TA00147 | ML-3 BO 604 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8990 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 14:27 | 2024-08-29 14:36 | [6 empty] | 2024-08-15 15:57
C467C247-1EC9-4B0B-3C3C-08DCBCFE539A | TA00146 | ML-1 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8920 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 13:30 | 2024-08-29 13:39 | [6 empty] | 2024-08-15 15:57
476ECF62-7999-48D3-3C3F-08DCBCFE539A | TA00146 | ML-1 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8930 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 13:39 | 2024-08-29 13:45 | [6 empty] | 2024-08-15 15:57
4044B079-7A5A-41E3-3C3E-08DCBCFE539A | TA00146 | ML-1 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8940 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 13:45 | 2024-08-29 13:54 | [6 empty] | 2024-08-15 15:57
34E91EAF-C604-4829-3C3D-08DCBCFE539A | TA00146 | ML-1 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8950 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 13:54 | 2024-08-29 14:03 | [6 empty] | 2024-08-15 15:57
B35B1E1C-3AC5-4B1D-3C3B-08DCBCFE539A | TA00145 | ML-2 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8880 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:57 | 2024-08-29 13:06 | [6 empty] | 2024-08-15 15:57
635FCD7F-CC4D-4D11-3C38-08DCBCFE539A | TA00145 | ML-2 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8890 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 13:06 | 2024-08-29 13:12 | [6 empty] | 2024-08-15 15:57
E4C6EAD6-F31B-4716-3C3A-08DCBCFE539A | TA00145 | ML-2 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8900 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 13:12 | 2024-08-29 13:21 | [6 empty] | 2024-08-15 15:57
CAC4A155-FAC0-4E38-3C39-08DCBCFE539A | TA00145 | ML-2 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8910 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 13:21 | 2024-08-29 13:30 | [6 empty] | 2024-08-15 15:57
CF7A64CF-685D-45C0-3C36-08DCBCFE539A | TA00144 | ML-3 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8840 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:24 | 2024-08-29 11:33 | [6 empty] | 2024-08-15 15:57
9864672C-0D50-40B3-3C35-08DCBCFE539A | TA00144 | ML-3 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8850 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:33 | 2024-08-29 11:39 | [6 empty] | 2024-08-15 15:57
B7E8D7C5-F17D-455D-3C37-08DCBCFE539A | TA00144 | ML-3 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8860 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:39 | 2024-08-29 11:48 | [6 empty] | 2024-08-15 15:57
E2B9E596-0951-4F73-3C34-08DCBCFE539A | TA00144 | ML-3 BO 603 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8870 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:48 | 2024-08-29 11:57 | [6 empty] | 2024-08-15 15:57
4A15DBC1-5CD2-4616-3C32-08DCBCFE539A | TA00143 | ML-1 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8800 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:51 | 2024-08-29 11:00 | [6 empty] | 2024-08-15 15:57
B27DE4A6-93A3-4EAE-3C33-08DCBCFE539A | TA00143 | ML-1 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8810 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:00 | 2024-08-29 11:06 | [6 empty] | 2024-08-15 15:57
FBD3D74C-087F-4E8A-3C31-08DCBCFE539A | TA00143 | ML-1 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8820 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:06 | 2024-08-29 11:15 | [6 empty] | 2024-08-15 15:57
00C0288A-E9DD-4BF2-3C30-08DCBCFE539A | TA00143 | ML-1 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8830 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 11:15 | 2024-08-29 11:24 | [6 empty] | 2024-08-15 15:57
68FD847C-E480-47A6-3C2C-08DCBCFE539A | TA00142 | ML-2 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8760 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:18 | 2024-08-29 10:27 | [6 empty] | 2024-08-15 15:57
77449DE0-3298-47B2-3C2F-08DCBCFE539A | TA00142 | ML-2 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8770 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:27 | 2024-08-29 10:33 | [6 empty] | 2024-08-15 15:57
3F6CE049-731C-43E2-3C2E-08DCBCFE539A | TA00142 | ML-2 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8780 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:33 | 2024-08-29 10:42 | [6 empty] | 2024-08-15 15:57
3B160DC0-7672-46A1-3C2D-08DCBCFE539A | TA00142 | ML-2 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8790 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:42 | 2024-08-29 10:51 | [6 empty] | 2024-08-15 15:57
9E4E2F43-84C5-4E88-3C2B-08DCBCFE539A | TA00141 | ML-3 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8720 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:45 | 2024-08-29 09:54 | [6 empty] | 2024-08-15 15:57
58A7635C-782C-4231-3C29-08DCBCFE539A | TA00141 | ML-3 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8730 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:54 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:57
C8CF6B60-7A09-4D95-3C28-08DCBCFE539A | TA00141 | ML-3 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8740 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 10:09 | [6 empty] | 2024-08-15 15:57
41F84C26-3D64-4848-3C2A-08DCBCFE539A | TA00141 | ML-3 BO SPARE #4 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8750 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 10:09 | 2024-08-29 10:18 | [6 empty] | 2024-08-15 15:57
9484E73E-8FB8-4833-3C27-08DCBCFE539A | TA00140 | ML-1 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8680 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:12 | 2024-08-29 09:21 | [6 empty] | 2024-08-15 15:57
433DB962-15A3-4D11-3C26-08DCBCFE539A | TA00140 | ML-1 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8690 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:21 | 2024-08-29 09:27 | [6 empty] | 2024-08-15 15:57
053C9965-EF9A-49CD-3C24-08DCBCFE539A | TA00140 | ML-1 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8700 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:27 | 2024-08-29 09:36 | [6 empty] | 2024-08-15 15:57
1127A390-23D8-4AB3-3C25-08DCBCFE539A | TA00140 | ML-1 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8710 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:36 | 2024-08-29 09:45 | [6 empty] | 2024-08-15 15:57
07ACBABA-CD69-4E3C-3C20-08DCBCFE539A | TA00139 | ML-2 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8640 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:39 | 2024-08-29 08:48 | [6 empty] | 2024-08-15 15:57
7B6EFBAA-3656-4805-3C22-08DCBCFE539A | TA00139 | ML-2 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8650 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:48 | 2024-08-29 08:54 | [6 empty] | 2024-08-15 15:57
E3368001-7423-43E8-3C21-08DCBCFE539A | TA00139 | ML-2 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8660 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:54 | 2024-08-29 09:03 | [6 empty] | 2024-08-15 15:57
1EECBAF1-1B9F-48AF-3C23-08DCBCFE539A | TA00139 | ML-2 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8670 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 09:03 | 2024-08-29 09:12 | [6 empty] | 2024-08-15 15:57
10CD0A13-809B-4B86-3C1F-08DCBCFE539A | TA00138 | ML-3 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8600 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:06 | 2024-08-29 08:15 | [6 empty] | 2024-08-15 15:57
F92A0678-F93B-40B2-3C1D-08DCBCFE539A | TA00138 | ML-3 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8610 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:15 | 2024-08-29 08:21 | [6 empty] | 2024-08-15 15:57
8DC17EA6-6974-43E7-3C1C-08DCBCFE539A | TA00138 | ML-3 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8620 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:21 | 2024-08-29 08:30 | [6 empty] | 2024-08-15 15:57
6ABA2B5C-03B4-4EBA-3C1E-08DCBCFE539A | TA00138 | ML-3 BO SPARE #3 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8630 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:30 | 2024-08-29 08:39 | [6 empty] | 2024-08-15 15:57
885F3701-7A79-4349-3C1B-08DCBCFE539A | TA00137 | ML-1 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8560 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:33 | 2024-08-28 16:42 | [6 empty] | 2024-08-15 15:57
A98C3C9A-536D-440C-3C19-08DCBCFE539A | TA00137 | ML-1 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8570 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:42 | 2024-08-28 16:48 | [6 empty] | 2024-08-15 15:57
5D691590-8EBB-418C-3C18-08DCBCFE539A | TA00137 | ML-1 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8580 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:48 | 2024-08-28 16:57 | [6 empty] | 2024-08-15 15:57
4497B96D-A468-4AE2-3C1A-08DCBCFE539A | TA00137 | ML-1 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8590 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:57 | 2024-08-29 08:06 | [6 empty] | 2024-08-15 15:57
812FDCAF-9FA0-4D59-3C17-08DCBCFE539A | TA00136 | ML-2 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8520 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:00 | 2024-08-28 16:09 | [6 empty] | 2024-08-15 15:57
4A6FC375-6FAA-489B-3C16-08DCBCFE539A | TA00136 | ML-2 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8530 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:09 | 2024-08-28 16:15 | [6 empty] | 2024-08-15 15:57
7B6BD098-A5C8-4CDD-3C15-08DCBCFE539A | TA00136 | ML-2 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8540 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:15 | 2024-08-28 16:24 | [6 empty] | 2024-08-15 15:57
7AA95046-D10A-4676-3C14-08DCBCFE539A | TA00136 | ML-2 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8550 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 16:24 | 2024-08-28 16:33 | [6 empty] | 2024-08-15 15:57
8355C85B-0610-4D46-3C12-08DCBCFE539A | TA00135 | ML-3 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8480 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:27 | 2024-08-28 15:36 | [6 empty] | 2024-08-15 15:57
49764656-E5E0-4ABC-3C13-08DCBCFE539A | TA00135 | ML-3 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8490 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:36 | 2024-08-28 15:42 | [6 empty] | 2024-08-15 15:57
A6354664-B91F-44C4-3C10-08DCBCFE539A | TA00135 | ML-3 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8500 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:42 | 2024-08-28 15:51 | [6 empty] | 2024-08-15 15:57
0E3217F7-21B6-4523-3C11-08DCBCFE539A | TA00135 | ML-3 BO SPARE #2 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8510 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:51 | 2024-08-28 16:00 | [6 empty] | 2024-08-15 15:57
C546748E-E1C6-4BCF-3C0F-08DCBCFE539A | TA00134 | ML-1 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8440 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:54 | 2024-08-28 15:03 | [6 empty] | 2024-08-15 15:57
848FDA4B-5D1B-48EA-3C0E-08DCBCFE539A | TA00134 | ML-1 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8450 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:03 | 2024-08-28 15:09 | [6 empty] | 2024-08-15 15:57
64D1FCFF-D796-4ADA-3C0D-08DCBCFE539A | TA00134 | ML-1 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8460 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:09 | 2024-08-28 15:18 | [6 empty] | 2024-08-15 15:57
25D57538-CC8C-4E96-3C0C-08DCBCFE539A | TA00134 | ML-1 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8470 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:18 | 2024-08-28 15:27 | [6 empty] | 2024-08-15 15:57
769E242B-86DB-4C65-3C09-08DCBCFE539A | TA00133 | ML-2 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8400 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:21 | 2024-08-28 14:30 | [6 empty] | 2024-08-15 15:57
6A6DD41D-1754-4477-3C0B-08DCBCFE539A | TA00133 | ML-2 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8410 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:30 | 2024-08-28 14:36 | [6 empty] | 2024-08-15 15:57
5BA6C161-EC64-48D1-3C0A-08DCBCFE539A | TA00133 | ML-2 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8420 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:36 | 2024-08-28 14:45 | [6 empty] | 2024-08-15 15:57
ADD9BAD8-1753-461F-3C08-08DCBCFE539A | TA00133 | ML-2 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8430 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:45 | 2024-08-28 14:54 | [6 empty] | 2024-08-15 15:57
9B65BA84-83BB-41A1-3C05-08DCBCFE539A | TA00132 | ML-3 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8360 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:48 | 2024-08-28 13:57 | [6 empty] | 2024-08-15 15:57
77219365-49FB-40D5-3C04-08DCBCFE539A | TA00132 | ML-3 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8370 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:57 | 2024-08-28 14:03 | [6 empty] | 2024-08-15 15:57
89178BB0-5C20-4699-3C06-08DCBCFE539A | TA00132 | ML-3 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8380 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:03 | 2024-08-28 14:12 | [6 empty] | 2024-08-15 15:57
BF39F0AB-2A44-47F6-3C07-08DCBCFE539A | TA00132 | ML-3 BO SPARE #1 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8390 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:12 | 2024-08-28 14:21 | [6 empty] | 2024-08-15 15:57
3AA69B6A-2BF6-4F85-3C01-08DCBCFE539A | TA00131 | ML-1 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8320 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:15 | 2024-08-28 13:24 | [6 empty] | 2024-08-15 15:57
EB503000-B030-4333-3C03-08DCBCFE539A | TA00131 | ML-1 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8330 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:24 | 2024-08-28 13:30 | [6 empty] | 2024-08-15 15:57
655354C7-1A32-46E1-3C02-08DCBCFE539A | TA00131 | ML-1 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8340 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:30 | 2024-08-28 13:39 | [6 empty] | 2024-08-15 15:57
E333B05F-52C2-44CA-3C00-08DCBCFE539A | TA00131 | ML-1 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8350 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:39 | 2024-08-28 13:48 | [6 empty] | 2024-08-15 15:57
4202156E-7C87-4D37-3BFE-08DCBCFE539A | TA00130 | ML-2 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8280 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:42 | 2024-08-28 11:51 | [6 empty] | 2024-08-15 15:57
79121112-8652-4AE5-3BFD-08DCBCFE539A | TA00130 | ML-2 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8290 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:51 | 2024-08-28 11:57 | [6 empty] | 2024-08-15 15:57
707246FF-4F0B-4A7A-3BFC-08DCBCFE539A | TA00130 | ML-2 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8300 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:57 | 2024-08-28 13:06 | [6 empty] | 2024-08-15 15:57
4E47B67C-9DD3-4235-3BFF-08DCBCFE539A | TA00130 | ML-2 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8310 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:06 | 2024-08-28 13:15 | [6 empty] | 2024-08-15 15:57
094530E2-488F-4BC0-3BF9-08DCBCFE539A | TA00129 | ML-3 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8240 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:09 | 2024-08-28 11:18 | [6 empty] | 2024-08-15 15:57
D74F193F-0AE2-457E-3BFB-08DCBCFE539A | TA00129 | ML-3 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8250 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:18 | 2024-08-28 11:24 | [6 empty] | 2024-08-15 15:57
1B91D622-F88E-474B-3BFA-08DCBCFE539A | TA00129 | ML-3 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8260 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:24 | 2024-08-28 11:33 | [6 empty] | 2024-08-15 15:57
3ECA2A00-040E-4DDC-3BF8-08DCBCFE539A | TA00129 | ML-3 SPARE 4 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8270 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:33 | 2024-08-28 11:42 | [6 empty] | 2024-08-15 15:57
7C995EE6-C5DC-4542-3BF7-08DCBCFE539A | TA00128 | ML-1 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8200 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:36 | 2024-08-28 10:45 | [6 empty] | 2024-08-15 15:57
D85C1715-C3E2-4B49-3BF4-08DCBCFE539A | TA00128 | ML-1 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8210 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:45 | 2024-08-28 10:51 | [6 empty] | 2024-08-15 15:57
FFFBFA00-2537-4C03-3BF5-08DCBCFE539A | TA00128 | ML-1 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8220 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:51 | 2024-08-28 11:00 | [6 empty] | 2024-08-15 15:57
CB2958C5-3FD8-49E4-3BF6-08DCBCFE539A | TA00128 | ML-1 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8230 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:00 | 2024-08-28 11:09 | [6 empty] | 2024-08-15 15:57
2C37CA20-1AA6-4E39-3BF0-08DCBCFE539A | TA00127 | ML-2 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8160 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:03 | 2024-08-28 10:12 | [6 empty] | 2024-08-15 15:57
6D03899C-55F1-4F2A-3BF1-08DCBCFE539A | TA00127 | ML-2 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8170 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:12 | 2024-08-28 10:18 | [6 empty] | 2024-08-15 15:57
75BB3EE5-5A35-4EB8-3BF3-08DCBCFE539A | TA00127 | ML-2 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8180 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:18 | 2024-08-28 10:27 | [6 empty] | 2024-08-15 15:57
BE97F3C4-6735-4974-3BF2-08DCBCFE539A | TA00127 | ML-2 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8190 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:27 | 2024-08-28 10:36 | [6 empty] | 2024-08-15 15:57
BD3859EA-BDB9-44E4-3BEC-08DCBCFE539A | TA00126 | ML-3 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8120 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:30 | 2024-08-28 09:39 | [6 empty] | 2024-08-15 15:57
4065EE71-1763-4E15-3BEF-08DCBCFE539A | TA00126 | ML-3 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8130 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:39 | 2024-08-28 09:45 | [6 empty] | 2024-08-15 15:57
3451ACAD-ABFB-4F27-3BEE-08DCBCFE539A | TA00126 | ML-3 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8140 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:45 | 2024-08-28 09:54 | [6 empty] | 2024-08-15 15:57
5531A797-133C-4364-3BED-08DCBCFE539A | TA00126 | ML-3 SPARE 3 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8150 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:54 | 2024-08-28 10:03 | [6 empty] | 2024-08-15 15:57
A9E0418B-D27F-445E-3BE9-08DCBCFE539A | TA00125 | ML-1 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8080 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:57 | 2024-08-28 09:06 | [6 empty] | 2024-08-15 15:57
68546F58-EEF5-4014-3BEA-08DCBCFE539A | TA00125 | ML-1 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8090 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:06 | 2024-08-28 09:12 | [6 empty] | 2024-08-15 15:57
C3B3B892-83BA-40D4-3BE8-08DCBCFE539A | TA00125 | ML-1 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8100 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:12 | 2024-08-28 09:21 | [6 empty] | 2024-08-15 15:57
5D59544B-2F14-47F8-3BEB-08DCBCFE539A | TA00125 | ML-1 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8110 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:21 | 2024-08-28 09:30 | [6 empty] | 2024-08-15 15:57
F94DEE2E-834F-4F4A-3BE6-08DCBCFE539A | TA00124 | ML-2 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8040 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:24 | 2024-08-28 08:33 | [6 empty] | 2024-08-15 15:57
AB28358B-32D9-4B69-3BE5-08DCBCFE539A | TA00124 | ML-2 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8050 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:33 | 2024-08-28 08:39 | [6 empty] | 2024-08-15 15:57
0BE88FF9-DFBD-4B71-3BE7-08DCBCFE539A | TA00124 | ML-2 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8060 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:39 | 2024-08-28 08:48 | [6 empty] | 2024-08-15 15:57
39724431-759D-4EC5-3BE4-08DCBCFE539A | TA00124 | ML-2 SPARE 2 (WHCP) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8070 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:48 | 2024-08-28 08:57 | [6 empty] | 2024-08-15 15:57
4EAF1D68-2E81-4EFF-3BE1-08DCBCFE539A | TA00123 | ML-3 SPARE 2 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A8000 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:51 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:57
F7E18BA8-9BAF-40D8-3BE3-08DCBCFE539A | TA00123 | ML-3 SPARE 2 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A8010 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 08:06 | [6 empty] | 2024-08-15 15:57
4BB2932D-85FB-4CE4-3BE2-08DCBCFE539A | TA00123 | ML-3 SPARE 2 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A8020 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:06 | 2024-08-28 08:15 | [6 empty] | 2024-08-15 15:57
450B0C22-B2BA-40F6-3BE0-08DCBCFE539A | TA00123 | ML-3 SPARE 2 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A8030 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:15 | 2024-08-28 08:24 | [6 empty] | 2024-08-15 15:57
9313C815-72CD-4993-3BDE-08DCBCFE539A | TA00122 | ML-1 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7960 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:18 | 2024-08-25 16:27 | [6 empty] | 2024-08-15 15:57
0397C18A-C665-46A9-3BDF-08DCBCFE539A | TA00122 | ML-1 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7970 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:27 | 2024-08-25 16:33 | [6 empty] | 2024-08-15 15:57
64B810DE-8DF6-4A9E-3BDC-08DCBCFE539A | TA00122 | ML-1 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7980 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:33 | 2024-08-25 16:42 | [6 empty] | 2024-08-15 15:57
AE1FF1FA-6F95-4D96-3BDD-08DCBCFE539A | TA00122 | ML-1 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7990 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:42 | 2024-08-25 16:51 | [6 empty] | 2024-08-15 15:57
8C8D16D4-4A75-4BB0-3BDA-08DCBCFE539A | TA00121 | ML-2 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7920 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:45 | 2024-08-25 15:54 | [6 empty] | 2024-08-15 15:57
289BD11A-6B1C-478C-3BD9-08DCBCFE539A | TA00121 | ML-2 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7930 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:54 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:57
BA76254C-FA64-4452-3BDB-08DCBCFE539A | TA00121 | ML-2 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7940 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 16:09 | [6 empty] | 2024-08-15 15:57
4E73924B-BA16-4620-3BD8-08DCBCFE539A | TA00121 | ML-2 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7950 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:09 | 2024-08-25 16:18 | [6 empty] | 2024-08-15 15:57
BF8FAE12-8EA5-4614-3BD5-08DCBCFE539A | TA00120 | ML-3 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7880 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:12 | 2024-08-25 15:21 | [6 empty] | 2024-08-15 15:57
F2E19AE2-14B2-41CA-3BD4-08DCBCFE539A | TA00120 | ML-3 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7890 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:21 | 2024-08-25 15:27 | [6 empty] | 2024-08-15 15:57
342385F8-E9FA-4D0C-3BD7-08DCBCFE539A | TA00120 | ML-3 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7900 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:27 | 2024-08-25 15:36 | [6 empty] | 2024-08-15 15:57
7442974C-B4F1-48FD-3BD6-08DCBCFE539A | TA00120 | ML-3 SPARE 1 (WHCP) BODP-F | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7910 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:36 | 2024-08-25 15:45 | [6 empty] | 2024-08-15 15:57
11B1434A-6E54-4383-3BD3-08DCBCFE539A | TA00119 | 531-DLV-010 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7840 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:39 | 2024-08-25 14:48 | [6 empty] | 2024-08-15 15:57
F0A20C92-B211-4111-3BD0-08DCBCFE539A | TA00119 | 531-DLV-010 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7850 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:48 | 2024-08-25 14:54 | [6 empty] | 2024-08-15 15:57
674B4D74-3B28-4BFE-3BD2-08DCBCFE539A | TA00119 | 531-DLV-010 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7860 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:54 | 2024-08-25 15:03 | [6 empty] | 2024-08-15 15:57
6FF051D1-E5A6-4EE6-3BD1-08DCBCFE539A | TA00119 | 531-DLV-010 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7870 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:03 | 2024-08-25 15:12 | [6 empty] | 2024-08-15 15:57
E5574A3B-674C-4AC2-3BCF-08DCBCFE539A | TA00118 | 646-SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7800 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:06 | 2024-08-25 14:15 | [6 empty] | 2024-08-15 15:57
B9571C8B-D561-4DD5-3BCD-08DCBCFE539A | TA00118 | 646-SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7810 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:15 | 2024-08-25 14:21 | [6 empty] | 2024-08-15 15:57
5E40CD03-6D57-4148-3BCE-08DCBCFE539A | TA00118 | 646-SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7820 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:21 | 2024-08-25 14:30 | [6 empty] | 2024-08-15 15:57
4BC50F43-762C-448C-3BCC-08DCBCFE539A | TA00118 | 646-SDV-060 | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7830 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:30 | 2024-08-25 14:39 | [6 empty] | 2024-08-15 15:57
C7860C96-7755-466B-3BC8-08DCBCFE539A | TA00117 | 656PSV060 (P-6560) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7760 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:33 | 2024-08-25 13:42 | [6 empty] | 2024-08-15 15:57
6036D59D-A2CA-4BAB-3BCA-08DCBCFE539A | TA00117 | 656PSV060 (P-6560) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7770 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:42 | 2024-08-25 13:48 | [6 empty] | 2024-08-15 15:57
28BE5AE3-9902-48AD-3BC9-08DCBCFE539A | TA00117 | 656PSV060 (P-6560) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7780 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:48 | 2024-08-25 13:57 | [6 empty] | 2024-08-15 15:57
B2D6D8D7-A5A8-4AB2-3BCB-08DCBCFE539A | TA00117 | 656PSV060 (P-6560) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7790 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:57 | 2024-08-25 14:06 | [6 empty] | 2024-08-15 15:57
CDC89769-1B6C-4B56-3BC4-08DCBCFE539A | TA00116 | 646PSV060 (V-6450) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7720 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:09 | [6 empty] | 2024-08-15 15:57
8EEC63D5-5B1A-48C5-3BC5-08DCBCFE539A | TA00116 | 646PSV060 (V-6450) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7730 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:09 | 2024-08-25 13:15 | [6 empty] | 2024-08-15 15:57
4F23CDC1-66D8-4793-3BC7-08DCBCFE539A | TA00116 | 646PSV060 (V-6450) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7740 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:15 | 2024-08-25 13:24 | [6 empty] | 2024-08-15 15:57
795B4447-12CB-424B-3BC6-08DCBCFE539A | TA00116 | 646PSV060 (V-6450) | Bokor | BODP-F |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7750 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:24 | 2024-08-25 13:33 | [6 empty] | 2024-08-15 15:57
6ADC590E-7F8A-4D1E-3BC0-08DCBCFE539A | TA00115 | 090XV-030 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7680 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:24 | 2024-08-28 15:33 | [6 empty] | 2024-08-15 15:57
E19B68F2-2A2C-4539-3BC1-08DCBCFE539A | TA00115 | 090XV-030 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7690 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:33 | 2024-08-28 15:39 | [6 empty] | 2024-08-15 15:57
45C2FAA2-77E0-413B-3BC3-08DCBCFE539A | TA00115 | 090XV-030 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7700 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:39 | 2024-08-28 15:48 | [6 empty] | 2024-08-15 15:57
BD3CBD07-067B-4B57-3BC2-08DCBCFE539A | TA00115 | 090XV-030 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7710 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:48 | 2024-08-28 15:57 | [6 empty] | 2024-08-15 15:57
E6B2D032-0053-47ED-3BBD-08DCBCFE539A | TA00114 | 090XV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7640 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:51 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:57
10398145-D5C8-4E46-3BBE-08DCBCFE539A | TA00114 | 090XV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7650 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-28 15:06 | [6 empty] | 2024-08-15 15:57
16DB41AE-1775-453D-3BBF-08DCBCFE539A | TA00114 | 090XV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7660 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:06 | 2024-08-28 15:15 | [6 empty] | 2024-08-15 15:57
C69F8199-3E3A-47F5-3BBC-08DCBCFE539A | TA00114 | 090XV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7670 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 15:15 | 2024-08-28 15:24 | [6 empty] | 2024-08-15 15:57
082E6236-77E6-4EBC-3BB8-08DCBCFE539A | TA00113 | 090XV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7600 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:18 | 2024-08-28 14:27 | [6 empty] | 2024-08-15 15:57
7BBDE1A7-5F65-40CE-3BBB-08DCBCFE539A | TA00113 | 090XV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7610 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:27 | 2024-08-28 14:33 | [6 empty] | 2024-08-15 15:57
20D20F50-76B4-4E75-3BB9-08DCBCFE539A | TA00113 | 090XV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7620 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:33 | 2024-08-28 14:42 | [6 empty] | 2024-08-15 15:57
6CCAAA24-79CC-4B65-3BBA-08DCBCFE539A | TA00113 | 090XV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7630 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:42 | 2024-08-28 14:51 | [6 empty] | 2024-08-15 15:57
5C3827E6-82D0-449C-3BB7-08DCBCFE539A | TA00112 | 090FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7560 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:45 | 2024-08-28 13:54 | [6 empty] | 2024-08-15 15:57
4776D6D6-0A4D-4630-3BB6-08DCBCFE539A | TA00112 | 090FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7570 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:54 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:57
E7B89CC3-583F-4E7B-3BB4-08DCBCFE539A | TA00112 | 090FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7580 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-28 14:09 | [6 empty] | 2024-08-15 15:57
8A8B73FA-A7AC-4BDB-3BB5-08DCBCFE539A | TA00112 | 090FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7590 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 14:09 | 2024-08-28 14:18 | [6 empty] | 2024-08-15 15:57
E098FB07-7F3B-4BEA-3BB0-08DCBCFE539A | TA00111 | 090FCV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7520 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:12 | 2024-08-28 13:21 | [6 empty] | 2024-08-15 15:57
D9DCD5EC-7EBC-47BF-3BB1-08DCBCFE539A | TA00111 | 090FCV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7530 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:21 | 2024-08-28 13:27 | [6 empty] | 2024-08-15 15:57
1B579185-FE22-4C55-3BB2-08DCBCFE539A | TA00111 | 090FCV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7540 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:27 | 2024-08-28 13:36 | [6 empty] | 2024-08-15 15:57
66D5BB6F-3B89-47BB-3BB3-08DCBCFE539A | TA00111 | 090FCV-020 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7550 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:36 | 2024-08-28 13:45 | [6 empty] | 2024-08-15 15:57
5D2E811E-DB4E-4491-3BAD-08DCBCFE539A | TA00110 | 090FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7480 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:39 | 2024-08-28 11:48 | [6 empty] | 2024-08-15 15:57
A9C98998-CCFB-43A3-3BAE-08DCBCFE539A | TA00110 | 090FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7490 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:48 | 2024-08-28 11:54 | [6 empty] | 2024-08-15 15:57
C5983D1C-941E-48E1-3BAF-08DCBCFE539A | TA00110 | 090FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7500 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:54 | 2024-08-28 13:03 | [6 empty] | 2024-08-15 15:57
905124EF-BBB1-4139-3BAC-08DCBCFE539A | TA00110 | 090FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7510 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 13:03 | 2024-08-28 13:12 | [6 empty] | 2024-08-15 15:57
FB7FFD97-D8A6-4BD0-3BAA-08DCBCFE539A | TA00109 | 071FCV-001 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7440 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:06 | 2024-08-28 11:15 | [6 empty] | 2024-08-15 15:57
26BD26D3-D74F-4175-3BAB-08DCBCFE539A | TA00109 | 071FCV-001 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7450 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:15 | 2024-08-28 11:21 | [6 empty] | 2024-08-15 15:57
78F9C59E-0F01-40A7-3BA9-08DCBCFE539A | TA00109 | 071FCV-001 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7460 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:21 | 2024-08-28 11:30 | [6 empty] | 2024-08-15 15:57
5A89B262-E83C-4FD1-3BA8-08DCBCFE539A | TA00109 | 071FCV-001 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7470 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 11:30 | 2024-08-28 11:39 | [6 empty] | 2024-08-15 15:57
FC0FDB40-859A-4BC9-3BA4-08DCBCFE539A | TA00108 | 070FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7400 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:33 | 2024-08-28 10:42 | [6 empty] | 2024-08-15 15:57
E471E49C-0B66-4D10-3BA5-08DCBCFE539A | TA00108 | 070FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7410 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:42 | 2024-08-28 10:48 | [6 empty] | 2024-08-15 15:57
2ABAE6C6-770B-423F-3BA7-08DCBCFE539A | TA00108 | 070FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7420 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:48 | 2024-08-28 10:57 | [6 empty] | 2024-08-15 15:57
D5008F22-8111-428D-3BA6-08DCBCFE539A | TA00108 | 070FCV-040 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7430 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:57 | 2024-08-28 11:06 | [6 empty] | 2024-08-15 15:57
373123CE-95CB-494D-3BA3-08DCBCFE539A | TA00107 | 070FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7360 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:00 | 2024-08-28 10:09 | [6 empty] | 2024-08-15 15:57
CF16E2BA-E5FC-4627-3BA0-08DCBCFE539A | TA00107 | 070FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7370 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:09 | 2024-08-28 10:15 | [6 empty] | 2024-08-15 15:57
F5B24DAD-08F1-4A6F-3BA1-08DCBCFE539A | TA00107 | 070FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7380 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:15 | 2024-08-28 10:24 | [6 empty] | 2024-08-15 15:57
D25E29EE-2AD0-4A51-3BA2-08DCBCFE539A | TA00107 | 070FCV-010 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7390 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 10:24 | 2024-08-28 10:33 | [6 empty] | 2024-08-15 15:57
D813C9D4-E699-4510-3B9E-08DCBCFE539A | TA00106 | M-3 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7320 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:27 | 2024-08-28 09:36 | [6 empty] | 2024-08-15 15:57
3BEDA199-2462-40F1-3B9F-08DCBCFE539A | TA00106 | M-3 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7330 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:36 | 2024-08-28 09:42 | [6 empty] | 2024-08-15 15:57
A9ECF3CE-9599-4660-3B9D-08DCBCFE539A | TA00106 | M-3 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7340 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:42 | 2024-08-28 09:51 | [6 empty] | 2024-08-15 15:57
F9D44C8C-BF63-4337-3B9C-08DCBCFE539A | TA00106 | M-3 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7350 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:51 | 2024-08-28 10:00 | [6 empty] | 2024-08-15 15:57
C2CC6D54-6D04-4CA8-3B98-08DCBCFE539A | TA00105 | M-2 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7280 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:54 | 2024-08-28 09:03 | [6 empty] | 2024-08-15 15:57
78D163BD-0E47-4F47-3B9B-08DCBCFE539A | TA00105 | M-2 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7290 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:03 | 2024-08-28 09:09 | [6 empty] | 2024-08-15 15:57
EAE1748B-1E85-4F0D-3B9A-08DCBCFE539A | TA00105 | M-2 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7300 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:09 | 2024-08-28 09:18 | [6 empty] | 2024-08-15 15:57
4C195785-010E-4272-3B99-08DCBCFE539A | TA00105 | M-2 P-0210A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7310 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 09:18 | 2024-08-28 09:27 | [6 empty] | 2024-08-15 15:57
031652FE-A9DB-4737-3B95-08DCBCFE539A | TA00104 | M-1 P-0210B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7240 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:21 | 2024-08-28 08:30 | [6 empty] | 2024-08-15 15:57
C288E1C8-076C-43BE-3B96-08DCBCFE539A | TA00104 | M-1 P-0210B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7250 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:30 | 2024-08-28 08:36 | [6 empty] | 2024-08-15 15:57
49C81464-5401-4807-3B94-08DCBCFE539A | TA00104 | M-1 P-0210B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7260 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:36 | 2024-08-28 08:45 | [6 empty] | 2024-08-15 15:57
1CA9A159-482A-4F36-3B97-08DCBCFE539A | TA00104 | M-1 P-0210B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7270 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:45 | 2024-08-28 08:54 | [6 empty] | 2024-08-15 15:57
65C6E75C-EFDF-4963-3B91-08DCBCFE539A | TA00103 | M-8 P-0130A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7200 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 16:48 | 2024-08-27 16:57 | [6 empty] | 2024-08-15 15:57
7997CE3B-3F13-4A0E-3B92-08DCBCFE539A | TA00103 | M-8 P-0130A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7210 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 16:57 | 2024-08-28 08:03 | [6 empty] | 2024-08-15 15:57
8A049451-F670-431D-3B90-08DCBCFE539A | TA00103 | M-8 P-0130A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7220 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:03 | 2024-08-28 08:12 | [6 empty] | 2024-08-15 15:57
0A3864FF-B2E3-47D9-3B93-08DCBCFE539A | TA00103 | M-8 P-0130A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7230 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-28 08:12 | 2024-08-28 08:21 | [6 empty] | 2024-08-15 15:57
473F5780-2295-4ABC-3B8E-08DCBCFE539A | TA00102 | M-4 P-0130B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7160 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 16:15 | 2024-08-27 16:24 | [6 empty] | 2024-08-15 15:56
896B0DF1-49C1-4089-3B8F-08DCBCFE539A | TA00102 | M-4 P-0130B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7170 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 16:24 | 2024-08-27 16:30 | [6 empty] | 2024-08-15 15:56
81E89BBE-B497-48E6-3B8D-08DCBCFE539A | TA00102 | M-4 P-0130B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7180 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 16:30 | 2024-08-27 16:39 | [6 empty] | 2024-08-15 15:56
C2E66568-EF82-4F4B-3B8C-08DCBCFE539A | TA00102 | M-4 P-0130B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7190 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 16:39 | 2024-08-27 16:48 | [6 empty] | 2024-08-15 15:56
D2FC114C-B77B-4EC5-3B8B-08DCBCFE539A | TA00101 | M-3 P-0110B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7120 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:42 | 2024-08-27 15:51 | [6 empty] | 2024-08-15 15:56
361C6376-EE51-46B6-3B88-08DCBCFE539A | TA00101 | M-3 P-0110B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7130 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:51 | 2024-08-27 15:57 | [6 empty] | 2024-08-15 15:56
DC3ABF3E-9DC1-4CDE-3B8A-08DCBCFE539A | TA00101 | M-3 P-0110B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7140 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:57 | 2024-08-27 16:06 | [6 empty] | 2024-08-15 15:56
EF385868-9FC8-4A8C-3B89-08DCBCFE539A | TA00101 | M-3 P-0110B | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7150 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 16:06 | 2024-08-27 16:15 | [6 empty] | 2024-08-15 15:56
5C327EDB-99E2-4FBE-3B86-08DCBCFE539A | TA00100 | M-2 P-0110C | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7080 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:09 | 2024-08-27 15:18 | [6 empty] | 2024-08-15 15:56
42F27976-F0E8-41E5-3B87-08DCBCFE539A | TA00100 | M-2 P-0110C | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7090 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:18 | 2024-08-27 15:24 | [6 empty] | 2024-08-15 15:56
8E850028-83F8-47D8-3B84-08DCBCFE539A | TA00100 | M-2 P-0110C | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7100 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:24 | 2024-08-27 15:33 | [6 empty] | 2024-08-15 15:56
DC63014D-F7AA-4978-3B85-08DCBCFE539A | TA00100 | M-2 P-0110C | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7110 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:33 | 2024-08-27 15:42 | [6 empty] | 2024-08-15 15:56
AF351BF9-7D6D-4190-3B82-08DCBCFE539A | TA00099 | M-1 P-0110A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7040 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 14:36 | 2024-08-27 14:45 | [6 empty] | 2024-08-15 15:56
36A70E6A-1678-43B4-3B81-08DCBCFE539A | TA00099 | M-1 P-0110A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7050 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 14:45 | 2024-08-27 14:51 | [6 empty] | 2024-08-15 15:56
9388B3EA-31D4-4658-3B83-08DCBCFE539A | TA00099 | M-1 P-0110A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7060 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 14:51 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:56
127B8038-C87A-4E9D-3B80-08DCBCFE539A | TA00099 | M-1 P-0110A | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7070 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-27 15:09 | [6 empty] | 2024-08-15 15:56
91EAF156-23B4-4833-3B7E-08DCBCFE539A | TA00098 | ML-1 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A7000 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 14:03 | 2024-08-27 14:12 | [6 empty] | 2024-08-15 15:56
C955D13E-F013-4590-3B7F-08DCBCFE539A | TA00098 | ML-1 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A7010 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 14:12 | 2024-08-27 14:18 | [6 empty] | 2024-08-15 15:56
F379CC62-432F-4B8C-3B7C-08DCBCFE539A | TA00098 | ML-1 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A7020 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 14:18 | 2024-08-27 14:27 | [6 empty] | 2024-08-15 15:56
D070339E-0FC2-4436-3B7D-08DCBCFE539A | TA00098 | ML-1 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A7030 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 14:27 | 2024-08-27 14:36 | [6 empty] | 2024-08-15 15:56
9A364F37-392D-4401-3B7B-08DCBCFE539A | TA00097 | ML-2 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6960 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 13:30 | 2024-08-27 13:39 | [6 empty] | 2024-08-15 15:56
DA36A414-B42A-4CEB-3B79-08DCBCFE539A | TA00097 | ML-2 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6970 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 13:39 | 2024-08-27 13:45 | [6 empty] | 2024-08-15 15:56
4C69A416-41D6-4935-3B7A-08DCBCFE539A | TA00097 | ML-2 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6980 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 13:45 | 2024-08-27 13:54 | [6 empty] | 2024-08-15 15:56
3C1DECC6-3D0F-4414-3B78-08DCBCFE539A | TA00097 | ML-2 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6990 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 13:54 | 2024-08-27 14:03 | [6 empty] | 2024-08-15 15:56
E7EA5265-B55B-4AC9-3B74-08DCBCFE539A | TA00096 | ML-3 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6920 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:57 | 2024-08-27 13:06 | [6 empty] | 2024-08-15 15:56
DFCE1149-669C-4490-3B76-08DCBCFE539A | TA00096 | ML-3 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6930 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 13:06 | 2024-08-27 13:12 | [6 empty] | 2024-08-15 15:56
79817398-D007-41C6-3B77-08DCBCFE539A | TA00096 | ML-3 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6940 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 13:12 | 2024-08-27 13:21 | [6 empty] | 2024-08-15 15:56
E50F213D-C9CF-4492-3B75-08DCBCFE539A | TA00096 | ML-3 BO 404 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6950 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 13:21 | 2024-08-27 13:30 | [6 empty] | 2024-08-15 15:56
8B9F1B5E-8B04-4FB1-3B71-08DCBCFE539A | TA00095 | ML-1 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6880 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:24 | 2024-08-27 11:33 | [6 empty] | 2024-08-15 15:56
34E28C04-7089-44F0-3B73-08DCBCFE539A | TA00095 | ML-1 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6890 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:33 | 2024-08-27 11:39 | [6 empty] | 2024-08-15 15:56
A5E2DD0B-2002-4324-3B72-08DCBCFE539A | TA00095 | ML-1 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6900 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:39 | 2024-08-27 11:48 | [6 empty] | 2024-08-15 15:56
1D90FB22-5E22-433D-3B70-08DCBCFE539A | TA00095 | ML-1 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6910 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:48 | 2024-08-27 11:57 | [6 empty] | 2024-08-15 15:56
39C62238-881C-42EF-3B6E-08DCBCFE539A | TA00094 | ML-2 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6840 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 10:51 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
C68B1268-6FEC-4915-3B6C-08DCBCFE539A | TA00094 | ML-2 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6850 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 11:06 | [6 empty] | 2024-08-15 15:56
4A46EA7E-E2F2-4A9A-3B6D-08DCBCFE539A | TA00094 | ML-2 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6860 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:06 | 2024-08-27 11:15 | [6 empty] | 2024-08-15 15:56
1096EEE4-0DEC-484B-3B6F-08DCBCFE539A | TA00094 | ML-2 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6870 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 11:15 | 2024-08-27 11:24 | [6 empty] | 2024-08-15 15:56
0D0237BD-0AE3-4C7C-3B68-08DCBCFE539A | TA00093 | ML-3 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6800 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 10:18 | 2024-08-27 10:27 | [6 empty] | 2024-08-15 15:56
E5C947C1-AD0E-488F-3B6B-08DCBCFE539A | TA00093 | ML-3 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6810 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 10:27 | 2024-08-27 10:33 | [6 empty] | 2024-08-15 15:56
D4BE72EC-E24D-471C-3B69-08DCBCFE539A | TA00093 | ML-3 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6820 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 10:33 | 2024-08-27 10:42 | [6 empty] | 2024-08-15 15:56
E7493C13-4DDA-4F1B-3B6A-08DCBCFE539A | TA00093 | ML-3 BO 403 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6830 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 10:42 | 2024-08-27 10:51 | [6 empty] | 2024-08-15 15:56
EB766558-6BB4-4F53-3B67-08DCBCFE539A | TA00092 | ML-1 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6760 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 09:45 | 2024-08-27 09:54 | [6 empty] | 2024-08-15 15:56
9D22D887-C49D-454E-3B66-08DCBCFE539A | TA00092 | ML-1 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6770 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 09:54 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
C29DBECB-D8DB-47EC-3B64-08DCBCFE539A | TA00092 | ML-1 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6780 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 10:09 | [6 empty] | 2024-08-15 15:56
5B40E075-1B1A-4827-3B65-08DCBCFE539A | TA00092 | ML-1 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6790 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 10:09 | 2024-08-27 10:18 | [6 empty] | 2024-08-15 15:56
347C5C3F-F9A9-4DD8-3B63-08DCBCFE539A | TA00091 | ML-2 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6720 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 09:12 | 2024-08-27 09:21 | [6 empty] | 2024-08-15 15:56
0F354DCF-2D6A-4035-3B62-08DCBCFE539A | TA00091 | ML-2 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6730 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 09:21 | 2024-08-27 09:27 | [6 empty] | 2024-08-15 15:56
C293E0DE-EC37-4C58-3B60-08DCBCFE539A | TA00091 | ML-2 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6740 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 09:27 | 2024-08-27 09:36 | [6 empty] | 2024-08-15 15:56
EE03F6FD-6797-4118-3B61-08DCBCFE539A | TA00091 | ML-2 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6750 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 09:36 | 2024-08-27 09:45 | [6 empty] | 2024-08-15 15:56
8842CB6D-7781-465A-3B5E-08DCBCFE539A | TA00090 | ML-3 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6680 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 08:39 | 2024-08-27 08:48 | [6 empty] | 2024-08-15 15:56
6269DB40-1F91-49C3-3B5D-08DCBCFE539A | TA00090 | ML-3 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6690 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 08:48 | 2024-08-27 08:54 | [6 empty] | 2024-08-15 15:56
0662617B-D601-42C7-3B5F-08DCBCFE539A | TA00090 | ML-3 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6700 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 08:54 | 2024-08-27 09:03 | [6 empty] | 2024-08-15 15:56
2717117F-571E-4297-3B5C-08DCBCFE539A | TA00090 | ML-3 BO 402 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6710 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 09:03 | 2024-08-27 09:12 | [6 empty] | 2024-08-15 15:56
6A2DA0EF-8948-4424-3B59-08DCBCFE539A | TA00089 | ML-1 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6640 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 08:06 | 2024-08-27 08:15 | [6 empty] | 2024-08-15 15:56
D10EE8E5-6353-4C0D-3B5A-08DCBCFE539A | TA00089 | ML-1 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6650 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 08:15 | 2024-08-27 08:21 | [6 empty] | 2024-08-15 15:56
A43622E1-7EBB-4A06-3B58-08DCBCFE539A | TA00089 | ML-1 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6660 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 08:21 | 2024-08-27 08:30 | [6 empty] | 2024-08-15 15:56
B8B4BB4F-728C-4AE6-3B5B-08DCBCFE539A | TA00089 | ML-1 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6670 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-27 08:30 | 2024-08-27 08:39 | [6 empty] | 2024-08-15 15:56
ACC84D54-2C38-4FCF-3B57-08DCBCFE539A | TA00088 | ML-2 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6600 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:33 | 2024-08-26 16:42 | [6 empty] | 2024-08-15 15:56
164BA82D-D02E-45B1-3B54-08DCBCFE539A | TA00088 | ML-2 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6610 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:42 | 2024-08-26 16:48 | [6 empty] | 2024-08-15 15:56
85471D9E-E4B7-4A13-3B55-08DCBCFE539A | TA00088 | ML-2 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6620 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:48 | 2024-08-26 16:57 | [6 empty] | 2024-08-15 15:56
8B8FF298-DC96-4380-3B56-08DCBCFE539A | TA00088 | ML-2 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6630 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:57 | 2024-08-27 08:06 | [6 empty] | 2024-08-15 15:56
F924907F-4511-4C9E-3B51-08DCBCFE539A | TA00087 | ML-3 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6560 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-26 16:09 | [6 empty] | 2024-08-15 15:56
5E08E8AA-648F-42B9-3B52-08DCBCFE539A | TA00087 | ML-3 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6570 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:09 | 2024-08-26 16:15 | [6 empty] | 2024-08-15 15:56
262DBFB8-8CF9-4A66-3B50-08DCBCFE539A | TA00087 | ML-3 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6580 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:15 | 2024-08-26 16:24 | [6 empty] | 2024-08-15 15:56
07B9A2ED-B698-4C7F-3B53-08DCBCFE539A | TA00087 | ML-3 BO 401 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6590 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 16:24 | 2024-08-26 16:33 | [6 empty] | 2024-08-15 15:56
A6669535-A885-461D-3B4E-08DCBCFE539A | TA00086 | ML-1 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6520 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:27 | 2024-08-26 15:36 | [6 empty] | 2024-08-15 15:56
8B63D24B-1595-4561-3B4F-08DCBCFE539A | TA00086 | ML-1 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6530 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:36 | 2024-08-26 15:42 | [6 empty] | 2024-08-15 15:56
16F4FECA-31C5-458A-3B4D-08DCBCFE539A | TA00086 | ML-1 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6540 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:42 | 2024-08-26 15:51 | [6 empty] | 2024-08-15 15:56
D5C4BE13-0D6A-4F9D-3B4C-08DCBCFE539A | TA00086 | ML-1 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6550 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:51 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:56
E099A335-72D0-4528-3B48-08DCBCFE539A | TA00085 | ML-2 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6480 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:54 | 2024-08-26 15:03 | [6 empty] | 2024-08-15 15:56
DAE1B14F-E2C0-4B32-3B4B-08DCBCFE539A | TA00085 | ML-2 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6490 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:03 | 2024-08-26 15:09 | [6 empty] | 2024-08-15 15:56
0E6A6445-29B9-4DCB-3B49-08DCBCFE539A | TA00085 | ML-2 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6500 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:09 | 2024-08-26 15:18 | [6 empty] | 2024-08-15 15:56
A36D309F-BB1A-40C5-3B4A-08DCBCFE539A | TA00085 | ML-2 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6510 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 15:18 | 2024-08-26 15:27 | [6 empty] | 2024-08-15 15:56
1F87964B-4953-402D-3B44-08DCBCFE539A | TA00084 | ML-3 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6440 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:21 | 2024-08-26 14:30 | [6 empty] | 2024-08-15 15:56
A938CC36-3BE0-4AAC-3B46-08DCBCFE539A | TA00084 | ML-3 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6450 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:30 | 2024-08-26 14:36 | [6 empty] | 2024-08-15 15:56
2BBC12A3-81CF-4E91-3B47-08DCBCFE539A | TA00084 | ML-3 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6460 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:36 | 2024-08-26 14:45 | [6 empty] | 2024-08-15 15:56
CE3382CB-202B-4AF1-3B45-08DCBCFE539A | TA00084 | ML-3 SPARE 1 (WHCP) | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6470 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:45 | 2024-08-26 14:54 | [6 empty] | 2024-08-15 15:56
327BFD72-3CE3-47B8-3B43-08DCBCFE539A | TA00083 | 656PSV060 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6400 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:48 | 2024-08-26 13:57 | [6 empty] | 2024-08-15 15:56
40A6DA2B-F64C-4B47-3B40-08DCBCFE539A | TA00083 | 656PSV060 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6410 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:57 | 2024-08-26 14:03 | [6 empty] | 2024-08-15 15:56
5F8C5EDF-7DAA-4344-3B42-08DCBCFE539A | TA00083 | 656PSV060 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6420 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:03 | 2024-08-26 14:12 | [6 empty] | 2024-08-15 15:56
A1708CAA-9EE9-45B8-3B41-08DCBCFE539A | TA00083 | 656PSV060 | Bokor | BODP-D |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6430 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 14:12 | 2024-08-26 14:21 | [6 empty] | 2024-08-15 15:56
53B4405E-2160-4482-3B3F-08DCBCFE539A | TA00082 | RV0102 Spare | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6360 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:33 | 2024-08-29 08:42 | [6 empty] | 2024-08-15 15:56
A241148D-7666-4FB0-3B3D-08DCBCFE539A | TA00082 | RV0102 Spare | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6370 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:42 | 2024-08-29 08:48 | [6 empty] | 2024-08-15 15:56
7495A5F2-6D7B-4235-3B3C-08DCBCFE539A | TA00082 | RV0102 Spare | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6380 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:48 | 2024-08-29 08:57 | [6 empty] | 2024-08-15 15:56
A06AF581-4661-4A98-3B3E-08DCBCFE539A | TA00082 | RV0102 Spare | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6390 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:57 | 2024-08-29 09:06 | [6 empty] | 2024-08-15 15:56
A2C22C02-B7A5-4524-3B3A-08DCBCFE539A | TA00081 | RV 0101 | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6320 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 08:09 | [6 empty] | 2024-08-15 15:56
19D6E75E-2619-4BCA-3B3B-08DCBCFE539A | TA00081 | RV 0101 | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6330 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:09 | 2024-08-29 08:15 | [6 empty] | 2024-08-15 15:56
94B22B34-76D2-4C15-3B38-08DCBCFE539A | TA00081 | RV 0101 | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6340 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:15 | 2024-08-29 08:24 | [6 empty] | 2024-08-15 15:56
A3E8373B-88F9-44C0-3B39-08DCBCFE539A | TA00081 | RV 0101 | Bokor | BODP-C |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6350 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-29 08:24 | 2024-08-29 08:33 | [6 empty] | 2024-08-15 15:56
B1D0B711-64E9-41F5-3B36-08DCBCFE539A | TA00080 | RV0702 | Bokor | BODP-B |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A6280 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:42 | 2024-08-31 09:51 | [6 empty] | 2024-08-15 15:56
7469C52A-6961-4012-3B37-08DCBCFE539A | TA00080 | RV0702 | Bokor | BODP-B |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A6290 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:51 | 2024-08-31 09:57 | [6 empty] | 2024-08-15 15:56
B50C7C0B-F5FF-435C-3B35-08DCBCFE539A | TA00080 | RV0702 | Bokor | BODP-B |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A6300 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 09:57 | 2024-08-31 10:06 | [6 empty] | 2024-08-15 15:56
6C7AEB0A-4106-4C58-3B34-08DCBCFE539A | TA00080 | RV0702 | Bokor | BODP-B |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A6310 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-31 10:06 | 2024-08-31 10:15 | [6 empty] | 2024-08-15 15:56
D1B2DFDF-AE35-4898-3B33-08DCBCFE539A | TA00079 | 407RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2540 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:15 | 2024-08-26 13:24 | [6 empty] | 2024-08-15 15:56
4F33503B-9A34-4C52-3B32-08DCBCFE539A | TA00079 | 407RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2550 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:24 | 2024-08-26 13:30 | [6 empty] | 2024-08-15 15:56
2A03E4B6-1B7E-4702-3B30-08DCBCFE539A | TA00079 | 407RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2560 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:30 | 2024-08-26 13:39 | [6 empty] | 2024-08-15 15:56
16FB76D8-D840-46C6-3B31-08DCBCFE539A | TA00079 | 407RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2570 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:39 | 2024-08-26 13:48 | [6 empty] | 2024-08-15 15:56
B30BBD5D-4D07-4B48-3B2F-08DCBCFE539A | TA00078 | 251RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2500 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:42 | 2024-08-26 11:51 | [6 empty] | 2024-08-15 15:56
CF699B4D-58A1-4638-3B2E-08DCBCFE539A | TA00078 | 251RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2510 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:51 | 2024-08-26 11:57 | [6 empty] | 2024-08-15 15:56
05EAD346-EAB3-459F-3B2C-08DCBCFE539A | TA00078 | 251RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2520 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:57 | 2024-08-26 13:06 | [6 empty] | 2024-08-15 15:56
370787A8-DD58-4E2F-3B2D-08DCBCFE539A | TA00078 | 251RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2530 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 13:06 | 2024-08-26 13:15 | [6 empty] | 2024-08-15 15:56
91DD264C-E342-403E-3B2A-08DCBCFE539A | TA00077 | 642RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2460 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:09 | 2024-08-26 11:18 | [6 empty] | 2024-08-15 15:56
3B2C3F0A-2C37-4240-3B29-08DCBCFE539A | TA00077 | 642RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2470 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:18 | 2024-08-26 11:24 | [6 empty] | 2024-08-15 15:56
A279299D-8452-4B36-3B28-08DCBCFE539A | TA00077 | 642RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2480 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:24 | 2024-08-26 11:33 | [6 empty] | 2024-08-15 15:56
0581E433-236E-4464-3B2B-08DCBCFE539A | TA00077 | 642RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2490 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:33 | 2024-08-26 11:42 | [6 empty] | 2024-08-15 15:56
489CE32C-04A9-4FC8-3B26-08DCBCFE539A | TA00076 | 641RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2420 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:36 | 2024-08-26 10:45 | [6 empty] | 2024-08-15 15:56
D3BA6C9A-81D8-4786-3B25-08DCBCFE539A | TA00076 | 641RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2430 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:45 | 2024-08-26 10:51 | [6 empty] | 2024-08-15 15:56
E118BDCD-A103-42BC-3B24-08DCBCFE539A | TA00076 | 641RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2440 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:51 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
8F5BC55C-279D-43E5-3B27-08DCBCFE539A | TA00076 | 641RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2450 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 11:09 | [6 empty] | 2024-08-15 15:56
7AED9231-06A3-4EE9-3B21-08DCBCFE539A | TA00075 | 624RV-001 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2380 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:03 | 2024-08-26 10:12 | [6 empty] | 2024-08-15 15:56
0FC15FBC-3003-4E60-3B20-08DCBCFE539A | TA00075 | 624RV-001 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2390 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:12 | 2024-08-26 10:18 | [6 empty] | 2024-08-15 15:56
7A04395B-7E92-4495-3B23-08DCBCFE539A | TA00075 | 624RV-001 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2400 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:18 | 2024-08-26 10:27 | [6 empty] | 2024-08-15 15:56
EA66FF62-7884-4F3B-3B22-08DCBCFE539A | TA00075 | 624RV-001 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2410 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 10:27 | 2024-08-26 10:36 | [6 empty] | 2024-08-15 15:56
3C763BDD-8A38-40F4-3B1E-08DCBCFE539A | TA00074 | 687RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2340 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:30 | 2024-08-26 09:39 | [6 empty] | 2024-08-15 15:56
FB6D7608-150D-4374-3B1C-08DCBCFE539A | TA00074 | 687RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2350 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:39 | 2024-08-26 09:45 | [6 empty] | 2024-08-15 15:56
E48117C3-13B2-49EA-3B1F-08DCBCFE539A | TA00074 | 687RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2360 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:45 | 2024-08-26 09:54 | [6 empty] | 2024-08-15 15:56
2C4D825F-77B0-4E1E-3B1D-08DCBCFE539A | TA00074 | 687RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2370 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:54 | 2024-08-26 10:03 | [6 empty] | 2024-08-15 15:56
A8D5975D-76BF-434C-3B19-08DCBCFE539A | TA00073 | 687RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2300 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:57 | 2024-08-26 09:06 | [6 empty] | 2024-08-15 15:56
8E804F79-5847-40FC-3B1B-08DCBCFE539A | TA00073 | 687RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2310 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:06 | 2024-08-26 09:12 | [6 empty] | 2024-08-15 15:56
F0AD209E-3734-41EC-3B18-08DCBCFE539A | TA00073 | 687RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2320 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:12 | 2024-08-26 09:21 | [6 empty] | 2024-08-15 15:56
3D7BA3FA-45EC-4B0F-3B1A-08DCBCFE539A | TA00073 | 687RV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2330 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 09:21 | 2024-08-26 09:30 | [6 empty] | 2024-08-15 15:56
1C838C0C-4E31-442B-3B16-08DCBCFE539A | TA00072 | 232RV-104 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2260 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:24 | 2024-08-26 08:33 | [6 empty] | 2024-08-15 15:56
2EC80D45-4932-4D84-3B15-08DCBCFE539A | TA00072 | 232RV-104 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2270 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:33 | 2024-08-26 08:39 | [6 empty] | 2024-08-15 15:56
7EFFAD78-8FDF-495B-3B17-08DCBCFE539A | TA00072 | 232RV-104 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2280 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:39 | 2024-08-26 08:48 | [6 empty] | 2024-08-15 15:56
DE81C0BC-77F4-4E92-3B14-08DCBCFE539A | TA00072 | 232RV-104 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2290 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:48 | 2024-08-26 08:57 | [6 empty] | 2024-08-15 15:56
C1F44443-6D32-40E8-3B12-08DCBCFE539A | TA00071 | 232-PVRV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2220 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:51 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
8F2809B4-0F98-47C0-3B13-08DCBCFE539A | TA00071 | 232-PVRV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2230 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 08:06 | [6 empty] | 2024-08-15 15:56
2950BEE0-8CE4-46A0-3B10-08DCBCFE539A | TA00071 | 232-PVRV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2240 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:06 | 2024-08-26 08:15 | [6 empty] | 2024-08-15 15:56
B98765E3-001A-4EF2-3B11-08DCBCFE539A | TA00071 | 232-PVRV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2250 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-26 08:15 | 2024-08-26 08:24 | [6 empty] | 2024-08-15 15:56
8BBB43ED-B397-4D42-3B0F-08DCBCFE539A | TA00070 | 402RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2180 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:18 | 2024-08-25 16:27 | [6 empty] | 2024-08-15 15:56
01FC6B75-9850-4FFE-3B0C-08DCBCFE539A | TA00070 | 402RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2190 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:27 | 2024-08-25 16:33 | [6 empty] | 2024-08-15 15:56
48752A5A-5134-41B4-3B0D-08DCBCFE539A | TA00070 | 402RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2200 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:33 | 2024-08-25 16:42 | [6 empty] | 2024-08-15 15:56
21D2932C-F538-4BA4-3B0E-08DCBCFE539A | TA00070 | 402RV-102 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2210 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:42 | 2024-08-25 16:51 | [6 empty] | 2024-08-15 15:56
FB660AD7-2277-489F-3B08-08DCBCFE539A | TA00069 | 402RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2140 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:45 | 2024-08-25 15:54 | [6 empty] | 2024-08-15 15:56
5B1CE43D-7E77-4B2B-3B09-08DCBCFE539A | TA00069 | 402RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2150 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:54 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:56
4A95D912-120A-4D49-3B0A-08DCBCFE539A | TA00069 | 402RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2160 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 16:09 | [6 empty] | 2024-08-15 15:56
47437BBF-9A14-4361-3B0B-08DCBCFE539A | TA00069 | 402RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2170 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 16:09 | 2024-08-25 16:18 | [6 empty] | 2024-08-15 15:56
958C2531-0C74-4E92-3B07-08DCBCFE539A | TA00068 | 673RV-112 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2100 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:12 | 2024-08-25 15:21 | [6 empty] | 2024-08-15 15:56
F823D469-D70E-428A-3B06-08DCBCFE539A | TA00068 | 673RV-112 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2110 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:21 | 2024-08-25 15:27 | [6 empty] | 2024-08-15 15:56
230C7B54-7ACF-436E-3B05-08DCBCFE539A | TA00068 | 673RV-112 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2120 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:27 | 2024-08-25 15:36 | [6 empty] | 2024-08-15 15:56
CCC44F44-63D7-4DDF-3B04-08DCBCFE539A | TA00068 | 673RV-112 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2130 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:36 | 2024-08-25 15:45 | [6 empty] | 2024-08-15 15:56
E97358E0-00D9-460F-3B02-08DCBCFE539A | TA00067 | 673RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2060 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:39 | 2024-08-25 14:48 | [6 empty] | 2024-08-15 15:56
048681AB-07C2-414E-3B00-08DCBCFE539A | TA00067 | 673RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2070 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:48 | 2024-08-25 14:54 | [6 empty] | 2024-08-15 15:56
826AE3FF-EDFE-429A-3B01-08DCBCFE539A | TA00067 | 673RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2080 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:54 | 2024-08-25 15:03 | [6 empty] | 2024-08-15 15:56
37F757F3-5FA7-4ACF-3B03-08DCBCFE539A | TA00067 | 673RV-111 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2090 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 15:03 | 2024-08-25 15:12 | [6 empty] | 2024-08-15 15:56
FF3F8AB9-AA2D-48DA-3AFF-08DCBCFE539A | TA00066 | 673RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A2020 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:06 | 2024-08-25 14:15 | [6 empty] | 2024-08-15 15:56
13270C44-888D-4BD1-3AFE-08DCBCFE539A | TA00066 | 673RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A2030 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:15 | 2024-08-25 14:21 | [6 empty] | 2024-08-15 15:56
A7DA7F45-E7A6-4390-3AFC-08DCBCFE539A | TA00066 | 673RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2040 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:21 | 2024-08-25 14:30 | [6 empty] | 2024-08-15 15:56
F324A133-9A4A-4BF8-3AFD-08DCBCFE539A | TA00066 | 673RV-103 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2050 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 14:30 | 2024-08-25 14:39 | [6 empty] | 2024-08-15 15:56
0EDA2FBB-FDBC-4168-3AF9-08DCBCFE539A | TA00065 | 686-PVSV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A1980 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:33 | 2024-08-25 13:42 | [6 empty] | 2024-08-15 15:56
BB01C285-A0A5-43B8-3AFA-08DCBCFE539A | TA00065 | 686-PVSV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A1990 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:42 | 2024-08-25 13:48 | [6 empty] | 2024-08-15 15:56
7E18F3EF-F33E-4975-3AF8-08DCBCFE539A | TA00065 | 686-PVSV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A2000 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:48 | 2024-08-25 13:57 | [6 empty] | 2024-08-15 15:56
8122AA93-6C4D-4613-3AFB-08DCBCFE539A | TA00065 | 686-PVSV-101 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A2010 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:57 | 2024-08-25 14:06 | [6 empty] | 2024-08-15 15:56
4B8C6D74-DD35-4DBC-3AF4-08DCBCFE539A | TA00064 | 683RV-119 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Removal of relief valve | A1940 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:09 | [6 empty] | 2024-08-15 15:56
3638C94B-FB75-45C0-3AF5-08DCBCFE539A | TA00064 | 683RV-119 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Isolation of valve inlet and outlet | A1950 | 0.1 | 0.2 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:09 | 2024-08-25 13:15 | [6 empty] | 2024-08-15 15:56
9FB900CC-9057-4700-3AF6-08DCBCFE539A | TA00064 | 683RV-119 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Servicing/recertification of relief valve | A1960 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:15 | 2024-08-25 13:24 | [6 empty] | 2024-08-15 15:56
66F7D886-931D-43A8-3AF7-08DCBCFE539A | TA00064 | 683RV-119 | Bokor | BOCPP-A |  | Pressure Control Valve (PCV) | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | Reinstall of relief valve | A1970 | 0.2 | 0.3 | 0 |  | ASEREV03 |  |  | 0 |  | 2024-08-25 13:24 | 2024-08-25 13:33 | [6 empty] | 2024-08-15 15:56
11ABA867-A57A-442F-3AF1-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Isolate & depressurize the unit & drain out remaining fluids | A1810 | 8 | 72 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:56
C9C5FC68-1712-474D-3AEC-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Drain out remaining liquid | A1820 | 4 | 36 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
C1D8BBE0-EA1C-4336-3AEE-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Soaking the unit | A1830 | 8 | 72 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:56
189E10E7-44F2-4BC2-3AF0-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | OPEN MANHOLE | A1840 | 4 | 36 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:56
327AD72E-F172-4E1D-3AEB-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 50 | Peform gas test, by AGT (by Others) | A1850 | 2 | 18 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:56
99A81899-36E2-48E2-3AF3-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 60 | Set up and run ventilation | A1860 | 2 | 18 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:56
EDFD233E-EED2-4920-3AEA-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 70 | Perform CSE cleaning using HPWJ method & visual inspection (by Others) | A1870 | 4 | 36 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:56
8F24BFA9-358A-44A1-3AED-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 80 | Transfer sludge from inside the unit into SW drums | A1880 | 8 | 72 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-29 10:24 | 2024-08-30 10:24 | [6 empty] | 2024-08-15 15:56
FAF944A3-60F0-415F-3AEF-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 90 | Conduct leak test using N2 and perform inspection | A1890 | 8 | 72 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-30 10:24 | 2024-08-31 10:24 | [6 empty] | 2024-08-15 15:56
E52A532B-143E-4B98-3AF2-08DCBCFE539A | TA00063 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 100 | Remove spades, change-out gasket & bolts/nuts & perform bolt tightening | A1900 | 8 | 72 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-31 10:24 | 2024-09-01 10:24 | [6 empty] | 2024-08-15 15:56
E0C3BB89-E8B5-4B2A-3AE1-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 10 | Isolate & depressurize the unit & drain out remaining fluids | A1700 | 8 | 56 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:56
13134707-6E2E-4CE7-3AE2-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 20 | Drain out remaining liquid | A1710 | 4 | 28 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
9075395E-1030-4B66-3AE6-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 30 | Soaking the unit | A1720 | 8 | 56 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:56
32E62E08-D183-4CC6-3AE5-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 40 | OPEN MANHOLE | A1730 | 4 | 28 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:56
1E4A2C0C-6A80-4E6A-3AE8-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 50 | Peform gas test, by AGT (by Others) | A1740 | 2 | 14 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:56
86B2874E-4A2C-4F05-3AE4-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 60 | Set up and run ventilation | A1750 | 2 | 14 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:56
296423D5-8E50-4DD3-3AE0-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 70 | Perform maintenance cleaning using HPWJ method & visual inspection (by Others) | A1760 | 4 | 28 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:56
F5D7E0EB-08C2-4DC4-3AE7-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 80 | Transfer sludge from inside the unit into SW drums | A1770 | 8 | 56 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-29 10:24 | 2024-08-30 10:24 | [6 empty] | 2024-08-15 15:56
A0F48E84-BA4A-4A04-3AE3-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 90 | Conduct leak test using N2 and perform inspection | A1780 | 8 | 56 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-30 10:24 | 2024-08-31 10:24 | [6 empty] | 2024-08-15 15:56
51B5F38B-C7CE-4008-3AE9-08DCBCFE539A | TA00062 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Static | Maintenance | PPM | Prelim | STATIC | Execution | 100 | Remove spades, change-out gasket & bolts/nuts & perform bolt tightening | A1790 | 8 | 56 | 0 |  | ASECLN00 |  |  | 0 |  | 2024-08-31 10:24 | 2024-09-01 10:24 | [6 empty] | 2024-08-15 15:56
91007C1C-3297-4851-3ADF-08DCBCFE539A | TA00061 | LP A-6250 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 10 | Worksite and Equipment Set Up and Preparation | A1660 | 0.3 | 1.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:12 | 2024-08-27 09:30 | [6 empty] | 2024-08-15 15:56
94CD455E-F718-4D69-3ADC-08DCBCFE539A | TA00061 | LP A-6250 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 20 | External Visual Inspection at flare tip | A1670 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:30 | 2024-08-27 09:48 | [6 empty] | 2024-08-15 15:56
15ABBD6C-AFF6-41CD-3ADD-08DCBCFE539A | TA00061 | LP A-6250 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 30 | Perform DPI on flare tip | A1680 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:48 | 2024-08-27 10:06 | [6 empty] | 2024-08-15 15:56
1E28DA3E-22B6-4704-3ADE-08DCBCFE539A | TA00061 | LP A-6250 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 40 | Photo Taking on Concern Area (Internal) | A1690 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:06 | 2024-08-27 10:24 | [6 empty] | 2024-08-15 15:56
24FEEBFB-D4CD-4FD7-3AD9-08DCBCFE539A | TA00060 | HP A-6220 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 10 | Worksite and Equipment Set Up and Preparation | A1620 | 0.3 | 1.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 08:18 | [6 empty] | 2024-08-15 15:56
00EA2AB1-27C3-49D0-3ADB-08DCBCFE539A | TA00060 | HP A-6220 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 20 | External Visual Inspection at flare tip | A1630 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:18 | 2024-08-27 08:36 | [6 empty] | 2024-08-15 15:56
FCF5E26A-E1B3-4C37-3ADA-08DCBCFE539A | TA00060 | HP A-6220 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 30 | Perform DPI on flare tip | A1640 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:36 | 2024-08-27 08:54 | [6 empty] | 2024-08-15 15:56
712343FC-F208-449F-3AD8-08DCBCFE539A | TA00060 | HP A-6220 | Betty | BEP-A |  | Flare Ignition | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 40 | Photo Taking on Concern Area (Internal) | A1650 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:54 | 2024-08-27 09:12 | [6 empty] | 2024-08-15 15:56
5DADA43D-DA6C-457B-3AD4-08DCBCFE539A | TA00059 | E-6010 | Laila | LADR-A |  | Lube Oil Cooler | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 10 | Worksite and Equipment Set Up and Preparation | A1580 | 0.3 | 1.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:18 | [6 empty] | 2024-08-15 15:56
F9CAFB29-7893-41E1-3AD7-08DCBCFE539A | TA00059 | E-6010 | Laila | LADR-A |  | Lube Oil Cooler | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 20 | External Visual Inspection at HEX | A1590 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:18 | 2024-08-25 13:36 | [6 empty] | 2024-08-15 15:56
B4E437B5-AA55-4580-3AD6-08DCBCFE539A | TA00059 | E-6010 | Laila | LADR-A |  | Lube Oil Cooler | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 30 | Perform DPI on HEX | A1600 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:36 | 2024-08-25 13:54 | [6 empty] | 2024-08-15 15:56
8C81DCFA-DB4C-4EC3-3AD5-08DCBCFE539A | TA00059 | E-6010 | Laila | LADR-A |  | Lube Oil Cooler | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 40 | Photo Taking on Concern Area (Internal) | A1610 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:54 | 2024-08-25 14:12 | [6 empty] | 2024-08-15 15:56
9EFDD0B0-5DF4-4496-3ACE-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 10 | Worksite and Equipment Set Up and Preparation | A1500 | 0.3 | 1.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 08:18 | [6 empty] | 2024-08-15 15:56
57B431DF-E572-4BB6-3ACD-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 20 | External Visual Inspection at Vessel | A1510 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:18 | 2024-08-29 08:36 | [6 empty] | 2024-08-15 15:56
ECB24C03-5FC8-4D96-3ACC-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 30 | Measurement of Corroded / Metal Loss Section (External, if found) | A1520 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:36 | 2024-08-29 08:54 | [6 empty] | 2024-08-15 15:56
8EEC05C8-9E19-4796-3AD1-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 40 | Photo Taking on Concern Area (External) | A1530 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:54 | 2024-08-29 09:12 | [6 empty] | 2024-08-15 15:56
A6095F9E-B5C7-450E-3AD2-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 50 | UTTG Measurement at Vessel | A1540 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:12 | 2024-08-29 09:30 | [6 empty] | 2024-08-15 15:56
BEE780A9-1783-4F37-3AD3-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 60 | Internal Visual Inspection at Vessel | A1550 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:30 | 2024-08-29 09:48 | [6 empty] | 2024-08-15 15:56
341838B1-0578-4117-3ACF-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 70 | Photo Taking on Concern Area (Internal) | A1560 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:48 | 2024-08-29 10:06 | [6 empty] | 2024-08-15 15:56
5327D857-F489-4172-3AD0-08DCBCFE539A | TA00058 | V-6400 Vent Knock Out Drum | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 80 | Measurement of Corroded / Metal Loss Section (Internal, if found) | A1570 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:06 | 2024-08-29 10:24 | [6 empty] | 2024-08-15 15:56
F7F0D09A-6FB3-4CA6-3AC9-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 10 | Worksite and Equipment Set Up and Preparation | A1420 | 0.3 | 1.2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 08:18 | [6 empty] | 2024-08-15 15:56
631D9554-1CF0-482F-3ACA-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 20 | External Visual Inspection at Vessel | A1430 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:18 | 2024-08-29 08:36 | [6 empty] | 2024-08-15 15:56
432A744D-4F0B-47EF-3ACB-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 30 | Measurement of Corroded / Metal Loss Section (External, if found) | A1440 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:36 | 2024-08-29 08:54 | [6 empty] | 2024-08-15 15:56
1E4D6F59-F293-4919-3AC8-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 40 | Photo Taking on Concern Area (External) | A1450 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:54 | 2024-08-29 09:12 | [6 empty] | 2024-08-15 15:56
126F1E74-26BA-4A22-3AC7-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 50 | UTTG Measurement at Vessel | A1460 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:12 | 2024-08-29 09:30 | [6 empty] | 2024-08-15 15:56
E7203964-C080-4389-3AC5-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 60 | Internal Visual Inspection at Vessel | A1470 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:30 | 2024-08-29 09:48 | [6 empty] | 2024-08-15 15:56
B12DBB6F-C3D9-48A8-3AC4-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 70 | Photo Taking on Concern Area (Internal) | A1480 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:48 | 2024-08-29 10:06 | [6 empty] | 2024-08-15 15:56
1CC4D796-EA24-4C9A-3AC6-08DCBCFE539A | TA00057 | V-6020 Fuel Gas Scrubber | Laila | LADR-A |  | Vessel | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 80 | Measurement of Corroded / Metal Loss Section (Internal, if found) | A1490 | 0.3 | 0.6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:06 | 2024-08-29 10:24 | [6 empty] | 2024-08-15 15:56
09943255-022F-4BF4-3AC1-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 10 | Site & equipment preparation i.e retrieval tool and service valve | A1090 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:15 | 2024-08-25 16:30 | [6 empty] | 2024-08-15 15:56
B9A031E0-7137-4AEC-3AC0-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 20 | Inspect the condition of the access fitting from any damage or corrosion & photo taking. | A1100 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 16:30 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
03329E55-F86C-4C07-3AC2-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 30 | Verify the line is isolated and depressurized | A1110 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 08:15 | [6 empty] | 2024-08-15 15:56
589CA7E4-7D88-4FC1-3ABB-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 40 | Mount & tighten the service valve on the access fitting. | A1120 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:15 | 2024-08-26 08:30 | [6 empty] | 2024-08-15 15:56
A23E2B87-5646-43A6-3AC3-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 50 | Mount & tighten the retrieval tool on the service valve. | A1130 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:30 | 2024-08-26 08:45 | [6 empty] | 2024-08-15 15:56
2B3428A0-1F2D-40E7-3ABE-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 60 | Retrieve & replace the corrosion coupon & ERP from the access fitting | A1140 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:45 | 2024-08-26 09:15 | [6 empty] | 2024-08-15 15:56
16F110AA-602B-4C91-3ABF-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 70 | Inspection the condition of the corrosion coupon & ERP and photo taking. | A1150 | 0.3 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:15 | 2024-08-26 09:30 | [6 empty] | 2024-08-15 15:56
5D87A2CA-C02A-426E-3ABD-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 80 | Install new corrosion coupon & ERP together with holder into the line & tighthen the solid and hollow plug | A1160 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:30 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:56
59E6B4BF-2F4A-49CC-3ABC-08DCBCFE539A | TA00056 | PL347 | Betty | BEP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 90 | Disengage the retrieval tool & service valve from the access fitting | A1170 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 10:30 | [6 empty] | 2024-08-15 15:56
37F0EBE4-5E50-47F3-3AB9-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 10 | Site & equipment preparation i.e retrieval tool and service valve | A1000 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:15 | [6 empty] | 2024-08-15 15:56
64BA2358-9D37-4CBF-3ABA-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 20 | Inspect the condition of the access fitting from any damage or corrosion & photo taking. | A1010 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:15 | 2024-08-25 13:45 | [6 empty] | 2024-08-15 15:56
A367F007-419F-4365-3AB2-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 30 | Verify the line is isolated and depressurized | A1020 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:45 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:56
761D43D7-094C-4A02-3AB7-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 40 | Mount & tighten the service valve on the access fitting. | A1030 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-25 14:15 | [6 empty] | 2024-08-15 15:56
21590030-3CBF-4C7B-3AB8-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 50 | Mount & tighten the retrieval tool on the service valve. | A1040 | 0.3 | 0.8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:15 | 2024-08-25 14:30 | [6 empty] | 2024-08-15 15:56
E84FAE2D-D539-4363-3AB5-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 60 | Retrieve & replace the corrosion coupon & ERP from the access fitting | A1050 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 14:30 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:56
C6C90206-6ED5-47D5-3AB3-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 70 | Inspection the condition of the corrosion coupon & ERP and photo taking. | A1060 | 0.3 | 0.3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-25 15:15 | [6 empty] | 2024-08-15 15:56
F98709BC-BF65-4F5D-3AB4-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 80 | Install new corrosion coupon & ERP together with holder into the line & tighthen the solid and hollow plug | A1070 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:15 | 2024-08-25 15:45 | [6 empty] | 2024-08-15 15:56
4BB5BE68-4C8C-4EA8-3AB6-08DCBCFE539A | TA00055 | PL363 | Bokor | BOP-A |  | Safe Guarding System | Construction | Maintenance | PPM | Prelim | Inspection | Execution | 90 | Disengage the retrieval tool & service valve from the access fitting | A1080 | 0.5 | 1.5 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 15:45 | 2024-08-25 16:15 | [6 empty] | 2024-08-15 15:56
0D28650A-6E59-4966-3AAE-08DCBCFE539A | TA00054 | DCS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | ESD Digitalization Function Test | A5910 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:56
266A5D67-8240-408E-3AAD-08DCBCFE539A | TA00054 | DCS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Quickfix Installation | A5920 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
C9680872-B0AB-4D25-3AAF-08DCBCFE539A | TA00054 | DCS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Antivirus Updates | A5930 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
D17B940C-71D6-4EE6-3AB1-08DCBCFE539A | TA00054 | DCS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | FCP and FBM firmware update | A5960 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
88AEB73D-8633-40D3-3AB0-08DCBCFE539A | TA00054 | DCS System | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Workstation Backup | A5970 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:56
53B0148F-6E35-439D-3AAA-08DCBCFE539A | TA00053 | 800xA COTP FGS | Betty | BEP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | PM visual inspection overall | A6090 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:56
FD9E1787-AD11-49B3-3AAC-08DCBCFE539A | TA00053 | 800xA COTP FGS | Betty | BEP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | PM software inspection - Backup/virus scan/system version defrag | A6100 | 7 | 7 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:56
1D040B98-80F6-4E8D-3AA8-08DCBCFE539A | TA00053 | 800xA COTP FGS | Betty | BEP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | PM software inspection - System load/firmware system warning/fault check | A6110 | 7 | 7 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
84E0C7AE-AC09-4A5A-3AA7-08DCBCFE539A | TA00053 | 800xA COTP FGS | Betty | BEP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | PM hardware inspection - Power distribution/module inspection | A6120 | 7 | 7 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-28 10:00 | [6 empty] | 2024-08-15 15:56
C7F2542C-7219-4502-3AA9-08DCBCFE539A | TA00053 | 800xA COTP FGS | Betty | BEP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | PM hardware inspection Drawing verificaion/cabinet inspection | A6130 | 7 | 7 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 10:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:56
AF71075D-11FB-4B2C-3AAB-08DCBCFE539A | TA00053 | 800xA COTP FGS | Betty | BEP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | PM spare check - Spare available/recommendation/report | A6140 | 7 | 7 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 09:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
4CC66043-DD3D-4417-3AA5-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Backup Current Logic | A5980 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 13:30 | [6 empty] | 2024-08-15 15:56
771EE81B-768B-4C66-3A9C-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Verify Control Program Application Version | A5990 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:30 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:56
51FCDAA6-D2BB-4293-3AA6-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Verify Fault Alarm Status | A6000 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:56
38803015-A069-4E01-3AA3-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | IO Count Check | A6010 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
AB092F8A-64F7-470E-3A9F-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Verify Important Setting of MODICON PLC | A6020 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 09:00 | [6 empty] | 2024-08-15 15:56
76D56D64-B9B2-4A74-3A9E-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Perform Systems Diagnostic Health Check | A6030 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
D6D48DF2-C72E-4E67-3AA1-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 70 | Measure and Record Power Supply Voltage | A6040 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 14:00 | [6 empty] | 2024-08-15 15:56
11F2EBAD-518D-478F-3AA2-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 80 | Identify Details of Power Supply Model and Part No. | A6050 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 14:00 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:56
7FFE1C1B-4484-45CA-3AA0-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 90 | Loose Connection Check | A6060 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
5A7A9958-F1DC-497F-3AA4-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 100 | Check Controller and Cabinet Temperature | A6070 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 08:30 | [6 empty] | 2024-08-15 15:56
3AE9B5D2-6195-4B27-3A9D-08DCBCFE539A | TA00052 | MODICON M580 | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 110 | Check Physical Condition Module Availability and Health Check | A6080 | 2.5 | 2.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 08:30 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
CB76818D-8CCC-4BE3-3A97-08DCBCFE539A | TA00051 | DCS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | ESD Digitalization Function Test | A5840 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:56
408D8002-6DA7-4344-3A9B-08DCBCFE539A | TA00051 | DCS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Quickfix Installation | A5850 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:56
3C6A10FE-BBA2-4F98-3A96-08DCBCFE539A | TA00051 | DCS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Antivirus Updates | A5860 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
0E4FE639-DA16-40DB-3A9A-08DCBCFE539A | TA00051 | DCS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Windows Patching | A5870 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 09:00 | [6 empty] | 2024-08-15 15:56
C6C80154-56F4-4844-3A99-08DCBCFE539A | TA00051 | DCS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Database, Graphics Backup & Graphic Housekeeping | A5880 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:56
89F09A14-062D-4AAE-3A95-08DCBCFE539A | TA00051 | DCS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | FCP and FBM firmware update | A5890 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
82706D23-3A6A-46D2-3A98-08DCBCFE539A | TA00051 | DCS System | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 70 | Workstation Backup | A5900 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:56
613E1D5C-478F-4872-3A8D-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Run DeltaV Diagnostics Check | A5750 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:56
873072F7-24B2-4277-3A94-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Install DeltaV workstation hotfixes to all DeltaV workstations | A5760 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:56
B9C523EF-97CF-4894-3A92-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Install Microsoft Security Updates sofware to all DeltaV workstations | A5770 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
606C8176-021E-4A1C-3A91-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Updated antivirus definitions on all DeltaV workstations | A5780 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 11:00 | [6 empty] | 2024-08-15 15:56
88723D51-08F0-44BF-3A8C-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Perform Flashing and Upgrade on DeltaV Controller and IO Cards | A5790 | 6 | 6 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:56
57A2BA5F-C46C-4AE4-3A8F-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Perform cabinet lights replacement inside 450-SC-001 & 450-SC-002 System cabinet | A5800 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 12:00 | [6 empty] | 2024-08-15 15:56
5158415D-92A2-4895-3A8E-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 70 | Perform Circuit Breaker (CB13) replacement inside 450-SC-001 System cabinet | A5810 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 13:00 | 2024-08-31 16:00 | [6 empty] | 2024-08-15 15:56
12508BEA-96E5-4519-3A90-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 80 | Perform Extender cables, Coax cables and BNC terminator replacement inside 450-SC-003 System cabinet | A5820 | 5 | 5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 16:00 | 2024-09-01 12:00 | [6 empty] | 2024-08-15 15:56
6A6EAC8C-A69D-4E44-3A93-08DCBCFE539A | TA00050 | DELTAV IPS/ FGS SYSTEM | Laila | LADR-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 90 | Gather the latest DeltaV System Registration/ Perform System Backup | A5830 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-09-01 13:00 | 2024-09-01 15:00 | [6 empty] | 2024-08-15 15:56
E4AE66E0-84BB-4E25-3A87-08DCBCFE539A | TA00049 | DELTAV IPS/ FGS SYSTEM | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Run DeltaV Diagnostics Check | A5680 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:56
751CB1F2-A854-41AD-3A89-08DCBCFE539A | TA00049 | DELTAV IPS/ FGS SYSTEM | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Install DeltaV workstation hotfixes to all DeltaV workstations | A5690 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
791174C3-8DFC-4343-3A8B-08DCBCFE539A | TA00049 | DELTAV IPS/ FGS SYSTEM | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Install Microsoft Security Updates sofware to all DeltaV workstations | A5700 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:56
67E879C0-B1A6-4203-3A8A-08DCBCFE539A | TA00049 | DELTAV IPS/ FGS SYSTEM | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Updated antivirus definitions on all DeltaV workstations | A5710 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
DC84FAD2-D075-48D3-3A85-08DCBCFE539A | TA00049 | DELTAV IPS/ FGS SYSTEM | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Perform Flashing and Upgrade on DeltaV Controller and IO Cards | A5720 | 5 | 5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:56
DF419404-A5BD-45D9-3A86-08DCBCFE539A | TA00049 | DELTAV IPS/ FGS SYSTEM | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Perform DC Power cable replacement inside 450-SC-001B System cabinet | A5730 | 5 | 5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
C28FF2DE-9043-45AA-3A88-08DCBCFE539A | TA00049 | DELTAV IPS/ FGS SYSTEM | Betty | BEDP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 70 | Gather the latest DeltaV System Registration/ Perform System Backup | A5740 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:56
50837E96-83DA-46DF-3A84-08DCBCFE539A | TA00048 | ABV-502 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform physical isolation | A5620 | 1 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
28FB9519-8ABA-41B4-3A82-08DCBCFE539A | TA00048 | ABV-502 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Remove ABV & control panel accessories | A5630 | 2 | 6 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 10:00 | [6 empty] | 2024-08-15 15:56
30079566-555E-4039-3A7F-08DCBCFE539A | TA00048 | ABV-502 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Install ABV | A5640 | 3 | 27 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-30 10:00 | 2024-08-30 14:00 | [6 empty] | 2024-08-15 15:56
8B5FD8FE-B999-4E75-3A83-08DCBCFE539A | TA00048 | ABV-502 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Hydraulic torquing valve flange bolt | A5650 | 1 | 6 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-30 14:00 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:56
FA320880-4D06-4901-3A81-08DCBCFE539A | TA00048 | ABV-502 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Instrumentation work (Control panel installation, tubing tie in & cable glanding) | A5660 | 1 | 2 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-30 16:00 | [6 empty] | 2024-08-15 15:56
3443917C-693A-4562-3A80-08DCBCFE539A | TA00048 | ABV-502 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Pre-testing & testing commissioning | A5670 | 1 | 2 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-30 16:00 | 2024-08-30 17:00 | [6 empty] | 2024-08-15 15:56
B366D87E-9789-4F7A-3A79-08DCBCFE539A | TA00047 | ABV-953 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform physical isolation | A5560 | 1 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-27 14:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:56
C954DF09-FABD-47EC-3A7E-08DCBCFE539A | TA00047 | ABV-953 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Remove ABV & control panel accessories | A5570 | 3 | 9 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:56
D7B7AD7F-6715-48F2-3A7D-08DCBCFE539A | TA00047 | ABV-953 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Install ABV | A5580 | 4 | 36 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
2378FA33-ABF8-411C-3A7B-08DCBCFE539A | TA00047 | ABV-953 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Hydraulic torquing valve flange bolt | A5590 | 7 | 42 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:56
D53659BD-210A-4B32-3A7C-08DCBCFE539A | TA00047 | ABV-953 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Instrumentation work (Control panel installation, tubing tie in & cable glanding) | A5600 | 2 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:56
00D6F364-BF05-4555-3A7A-08DCBCFE539A | TA00047 | ABV-953 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Pre-testing & testing commissioning | A5610 | 1 | 2 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:56
B99A5BBE-4344-4749-3A75-08DCBCFE539A | TA00046 | ABV-943 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform physical isolation | A5500 | 1 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:56
792C9092-CA5F-4D93-3A74-08DCBCFE539A | TA00046 | ABV-943 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Remove ABV & control panel accessories | A5510 | 3 | 9 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
FF6DBEC6-7664-4B21-3A77-08DCBCFE539A | TA00046 | ABV-943 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Install ABV | A5520 | 3 | 27 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
CB3CF9CA-A836-4B00-3A73-08DCBCFE539A | TA00046 | ABV-943 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Hydraulic torquing valve flange bolt | A5530 | 7 | 42 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
948FA119-BC6E-465E-3A76-08DCBCFE539A | TA00046 | ABV-943 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Instrumentation work (Control panel installation, tubing tie in & cable glanding) | A5540 | 2 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:56
3D9DA4AF-8F83-4F65-3A78-08DCBCFE539A | TA00046 | ABV-943 | Betty | BEP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Pre-testing & testing commissioning | A5550 | 1 | 2 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:56
CBB9DE79-5E02-40CD-3A6F-08DCBCFE539A | TA00045 | BOK-A AHU | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Site inspection and system verification for RMCS ESP | A5460 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 14:00 | [6 empty] | 2024-08-15 15:56
631A769F-42AB-4F0C-3A71-08DCBCFE539A | TA00045 | BOK-A AHU | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Check system error for RMCS ESP | A5470 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:56
39CBF7F1-31EC-4745-3A72-08DCBCFE539A | TA00045 | BOK-A AHU | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Backup program for RMCS ESP | A5480 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:56
67EC8811-80C3-4811-3A70-08DCBCFE539A | TA00045 | BOK-A AHU | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform fault rectification for RMCS ESP | A5490 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
14472CAB-6753-41EC-3A6E-08DCBCFE539A | TA00044 | BODP-C WSS ESP | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Site inspection and system verification for RMCS ESP | A5420 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:56
731A1D9D-C66C-4F66-3A6D-08DCBCFE539A | TA00044 | BODP-C WSS ESP | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Check system error for RMCS ESP | A5430 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 09:00 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:56
3F0DA8F4-1158-463D-3A6B-08DCBCFE539A | TA00044 | BODP-C WSS ESP | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Backup program for RMCS ESP | A5440 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 11:00 | [6 empty] | 2024-08-15 15:56
1CEA671A-315F-40DE-3A6C-08DCBCFE539A | TA00044 | BODP-C WSS ESP | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform fault rectification for RMCS ESP | A5450 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 11:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:56
558FB24F-48EF-48C7-3A6A-08DCBCFE539A | TA00043 | BODP-C FGS LERC | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Site inspection and system verification for RMCS ESP | A5380 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
EE3428FE-B6A9-4314-3A67-08DCBCFE539A | TA00043 | BODP-C FGS LERC | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Check system error for RMCS ESP | A5390 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:56
CEB8400F-7BD7-4272-3A68-08DCBCFE539A | TA00043 | BODP-C FGS LERC | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Backup program for RMCS ESP | A5400 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-28 16:00 | [6 empty] | 2024-08-15 15:56
B03B4D2B-4BFA-49E3-3A69-08DCBCFE539A | TA00043 | BODP-C FGS LERC | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform fault rectification for RMCS ESP | A5410 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 16:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:56
A0A7E3A8-046B-45E4-3A63-08DCBCFE539A | TA00042 | BODP-B Desander | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Site inspection and system verification for RMCS ESP | A5340 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:56
618D8656-3374-4C2D-3A64-08DCBCFE539A | TA00042 | BODP-B Desander | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Check system error for RMCS ESP | A5350 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 10:00 | [6 empty] | 2024-08-15 15:56
57946392-DBEB-48D0-3A66-08DCBCFE539A | TA00042 | BODP-B Desander | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Backup program for RMCS ESP | A5360 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 10:00 | 2024-08-28 11:00 | [6 empty] | 2024-08-15 15:56
97D7836A-FEDD-4952-3A65-08DCBCFE539A | TA00042 | BODP-B Desander | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform fault rectification for RMCS ESP | A5370 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 11:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:56
23C050BC-FCAA-499C-3A60-08DCBCFE539A | TA00041 | BODP-A Purge panel | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Site inspection and system verification for RMCS ESP | A5300 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:56
B35E3E31-9EBE-481B-3A62-08DCBCFE539A | TA00041 | BODP-A Purge panel | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Check system error for RMCS ESP | A5310 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 14:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:56
2FF7B5AE-5729-4A9F-3A5F-08DCBCFE539A | TA00041 | BODP-A Purge panel | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Backup program for RMCS ESP | A5320 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-27 16:00 | [6 empty] | 2024-08-15 15:56
BA692F3F-8B87-4957-3A61-08DCBCFE539A | TA00041 | BODP-A Purge panel | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform fault rectification for RMCS ESP | A5330 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 16:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:56
7ACAD73F-6295-4D68-3A5C-08DCBCFE539A | TA00040 | BODP-A AHU | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Site inspection and system verification for RMCS ESP | A5260 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:56
C6545DD9-5F77-4FB3-3A5E-08DCBCFE539A | TA00040 | BODP-A AHU | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Check system error for RMCS ESP | A5270 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
A1301382-1BB1-4304-3A5D-08DCBCFE539A | TA00040 | BODP-A AHU | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Backup program for RMCS ESP | A5280 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
5B345E21-C461-4502-3A5B-08DCBCFE539A | TA00040 | BODP-A AHU | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform fault rectification for RMCS ESP | A5290 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:56
9F35346F-AC07-4153-3A58-08DCBCFE539A | TA00039 | BODP-A RMCS ESP | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Site inspection and system verification for RMCS ESP | A5220 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:56
575D7362-F810-4A1C-3A57-08DCBCFE539A | TA00039 | BODP-A RMCS ESP | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Check system error for RMCS ESP | A5230 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
0894F397-C53D-4FA2-3A59-08DCBCFE539A | TA00039 | BODP-A RMCS ESP | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Backup program for RMCS ESP | A5240 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:56
464252D9-760B-49E9-3A5A-08DCBCFE539A | TA00039 | BODP-A RMCS ESP | Bokor | BODP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform fault rectification for RMCS ESP | A5250 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:56
10AEEFA5-77AE-4F85-3A56-08DCBCFE539A | TA00038 | SIS-4500 (BODP-F) | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check | A3970 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 08:00 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:56
6292DAE1-9879-48F0-3A54-08DCBCFE539A | TA00038 | SIS-4500 (BODP-F) | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check | A3980 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 10:00 | [6 empty] | 2024-08-15 15:56
E4DB32BA-E07A-4D51-3A55-08DCBCFE539A | TA00038 | SIS-4500 (BODP-F) | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Cabinet Temperature & Humidity Measurement | A3990 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 10:00 | 2024-08-31 11:00 | [6 empty] | 2024-08-15 15:56
40A3DCD2-C0DA-49D6-3A51-08DCBCFE539A | TA00037 | SIS-4500 (BODP-D) | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check | A3940 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 11:00 | [6 empty] | 2024-08-15 15:56
430B3FCA-9B8A-436E-3A53-08DCBCFE539A | TA00037 | SIS-4500 (BODP-D) | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check | A3950 | 3 | 3 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-30 15:00 | [6 empty] | 2024-08-15 15:56
B7A5E084-A29E-4C13-3A52-08DCBCFE539A | TA00037 | SIS-4500 (BODP-D) | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Cabinet Temperature & Humidity Measurement | A3960 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-30 17:00 | [6 empty] | 2024-08-15 15:56
75EAD0D2-2BE4-4526-3A4F-08DCBCFE539A | TA00036 | SIS-4541 | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check | A3910 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:56
9B27E3C8-11E1-4413-3A50-08DCBCFE539A | TA00036 | SIS-4541 | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check | A3920 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:56
E31B958F-81B4-48DF-3A4E-08DCBCFE539A | TA00036 | SIS-4541 | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Cabinet Temperature & Humidity Measurement | A3930 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:56
DD6CDBE6-CD11-4485-3A4D-08DCBCFE539A | TA00035 | SIS-4531 | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check | A3880 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:56
9EE18027-99A9-4A5F-3A4B-08DCBCFE539A | TA00035 | SIS-4531 | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check | A3890 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-28 16:00 | [6 empty] | 2024-08-15 15:56
BABA4A15-4B38-48DF-3A4C-08DCBCFE539A | TA00035 | SIS-4531 | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Cabinet Temperature & Humidity Measurement | A3900 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 16:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:56
16EC1A77-B7F3-4833-3A4A-08DCBCFE539A | TA00034 | FGS-8021/8022/8023 | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check | A3850 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 10:30 | 2024-08-28 11:00 | [6 empty] | 2024-08-15 15:56
684C38A5-E095-4EFF-3A49-08DCBCFE539A | TA00034 | FGS-8021/8022/8023 | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check | A3860 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 11:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:56
5BAD5007-9979-4F4F-3A48-08DCBCFE539A | TA00034 | FGS-8021/8022/8023 | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Cabinet Temperature & Humidity Measurement | A3870 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
463763CE-305C-428D-3A47-08DCBCFE539A | TA00033 | SIS-4526 | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check | A3820 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 08:30 | [6 empty] | 2024-08-15 15:56
CBE70A31-ED8D-4419-3A46-08DCBCFE539A | TA00033 | SIS-4526 | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Hardware Inspection, Power Supply & Grounding Check | A3830 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 08:30 | 2024-08-28 09:30 | [6 empty] | 2024-08-15 15:56
C5572BC5-C394-4665-3A45-08DCBCFE539A | TA00033 | SIS-4526 | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Cabinet Temperature & Humidity Measurement | A3840 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 09:30 | 2024-08-28 10:30 | [6 empty] | 2024-08-15 15:56
F05C9256-6D89-445B-3A42-08DCBCFE539A | TA00032 | SIS/FGS (FGS-8012) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check, Hardware Inspection, Power Supply & Grounding Check at IER, BOCPP-A | A3790 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 13:30 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:56
D060E524-CA67-4974-3A44-08DCBCFE539A | TA00032 | SIS/FGS (FGS-8012) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform SCS Power Supply, Cabinet Temperature & Humidity Measurement and General Cleaning at IER, BOCPP-A | A3800 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 14:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:56
2B3216D4-93DB-4B67-3A43-08DCBCFE539A | TA00032 | SIS/FGS (FGS-8012) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Perform Spare Count Checking and Record Updates | A3810 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:56
D9C57100-8863-4928-3A41-08DCBCFE539A | TA00031 | SIS/FGS (FGS-8011) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check, Hardware Inspection, Power Supply & Grounding Check at IER, BOCPP-A | A3760 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 09:00 | 2024-08-27 09:30 | [6 empty] | 2024-08-15 15:56
65190E99-7EBA-42E1-3A40-08DCBCFE539A | TA00031 | SIS/FGS (FGS-8011) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform SCS Power Supply, Cabinet Temperature & Humidity Measurement and General Cleaning at IER, BOCPP-A | A3770 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 09:30 | 2024-08-27 10:30 | [6 empty] | 2024-08-15 15:56
FA3880F5-3588-4434-3A3F-08DCBCFE539A | TA00031 | SIS/FGS (FGS-8011) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Perform Spare Count Checking and Record Updates | A3780 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 10:30 | 2024-08-27 13:30 | [6 empty] | 2024-08-15 15:56
9C9FAE75-AD22-450A-3A3C-08DCBCFE539A | TA00030 | SIS/FGS (SIS-4512) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check, Hardware Inspection, Power Supply & Grounding Check at IER, BOCPP-A | A3730 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 15:30 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:56
601F32E2-778B-45BB-3A3D-08DCBCFE539A | TA00030 | SIS/FGS (SIS-4512) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform SCS Power Supply, Cabinet Temperature & Humidity Measurement and General Cleaning at IER, BOCPP-A | A3740 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
A2273B2E-DBD0-4BEA-3A3E-08DCBCFE539A | TA00030 | SIS/FGS (SIS-4512) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Perform Spare Count Checking and Record Updates | A3750 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 09:00 | [6 empty] | 2024-08-15 15:56
76EDEF89-C163-4228-3A3B-08DCBCFE539A | TA00029 | SIS/FGS (SIS-4511) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform SCS Health Check, Hardware Inspection, Power Supply & Grounding Check at IER, BOCPP-A | A3700 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 13:30 | [6 empty] | 2024-08-15 15:56
242C1FD8-3246-409B-3A3A-08DCBCFE539A | TA00029 | SIS/FGS (SIS-4511) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform SCS Power Supply, Cabinet Temperature & Humidity Measurement and General Cleaning at IER, BOCPP-A | A3710 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:30 | 2024-08-26 14:30 | [6 empty] | 2024-08-15 15:56
E61DFFA1-ACC7-4D43-3A39-08DCBCFE539A | TA00029 | SIS/FGS (SIS-4511) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Perform Spare Count Checking and Record Updates | A3720 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 14:30 | 2024-08-26 15:30 | [6 empty] | 2024-08-15 15:56
AA9242C2-09B4-4998-3A36-08DCBCFE539A | TA00028 | SIS/FGS (EWS-4500) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform Software Patch and Windows O/S Patch for PC at CCR | A3660 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 09:00 | [6 empty] | 2024-08-15 15:56
D732754A-80A8-436B-3A37-08DCBCFE539A | TA00028 | SIS/FGS (EWS-4500) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform backup of System Database SENG collected information | A3670 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:56
0753E1EE-32EA-4013-3A35-08DCBCFE539A | TA00028 | SIS/FGS (EWS-4500) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | SOE(Sequence of Event) Backup | A3680 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
1069D185-C7A2-4BE1-3A38-08DCBCFE539A | TA00028 | SIS/FGS (EWS-4500) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform SENG Health Check and General Cleaning at CCR | A3690 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:56
E7A56732-E6FC-4BE8-3A34-08DCBCFE539A | TA00027 | SIS/FGS (ESW-8000) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform Software Patch and Windows O/S Patch for PC at CCR | A3620 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 14:00 | [6 empty] | 2024-08-15 15:56
ED473B85-1488-4856-3A31-08DCBCFE539A | TA00027 | SIS/FGS (ESW-8000) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform backup of System Database SENG collected information | A3630 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 14:00 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:56
4FA5816F-A158-4B83-3A32-08DCBCFE539A | TA00027 | SIS/FGS (ESW-8000) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | SOE(Sequence of Event) Backup | A3640 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:56
693FD077-1CB8-445E-3A33-08DCBCFE539A | TA00027 | SIS/FGS (ESW-8000) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform SENG Health Check and General Cleaning at CCR | A3650 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
1E4D1D6A-CFA8-4808-3A30-08DCBCFE539A | TA00026 | DCS (BODP-F) | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform FCS health check, L2SW maintenance (FCS0106 and L2SW) | A6260 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 08:00 | 2024-08-31 12:00 | [6 empty] | 2024-08-15 15:56
D593E87A-72F2-4AAD-3A2F-08DCBCFE539A | TA00026 | DCS (BODP-F) | Bokor | BODP-F |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform HIS health check, updating windows O/S patch and antivirus scan (HIS0156) | A6270 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-31 13:00 | 2024-08-31 17:00 | [6 empty] | 2024-08-15 15:56
534DAE58-C68F-4CEF-3A2D-08DCBCFE539A | TA00025 | DCS (BODP-D) | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform FCS health check, L2SW maintenance (FCS0106 and L2SW) | A6240 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 12:00 | [6 empty] | 2024-08-15 15:56
A98210C6-709F-4949-3A2E-08DCBCFE539A | TA00025 | DCS (BODP-D) | Bokor | BODP-D |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform HIS health check, updating windows O/S patch and antivirus scan (HIS0156) | A6250 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-30 13:00 | 2024-08-30 17:00 | [6 empty] | 2024-08-15 15:56
0D867BFF-B916-4C8C-3A2C-08DCBCFE539A | TA00024 | DCS (BODP-C) | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform FCS health check, L2SW maintenance (FCS0106 and L2SW) | A6220 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:56
2C94D1D3-0950-4A69-3A2B-08DCBCFE539A | TA00024 | DCS (BODP-C) | Bokor | BODP-C |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform HIS health check, updating windows O/S patch and antivirus scan (HIS0156) | A6230 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
E758CBF2-0C2D-4A72-3A2A-08DCBCFE539A | TA00023 | DCS (BODP-B) | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform FCS health check, L2SW maintenance (FCS0106 and L2SW) | A6200 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:56
0C39369B-3241-47AA-3A29-08DCBCFE539A | TA00023 | DCS (BODP-B) | Bokor | BODP-B |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform HIS health check, updating windows O/S patch and antivirus scan (HIS0156) | A6210 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:56
D4C9484F-5BB1-4B23-3A28-08DCBCFE539A | TA00022 | DCS (BOK-A) | Bokor | BOK-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform FCS health check, L2SW maintenance (FCS0105) | A6190 | 5 | 5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 16:00 | [6 empty] | 2024-08-15 15:56
E544D30C-C21A-45B8-3A26-08DCBCFE539A | TA00021 | DCS (BOCPP-A) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform HIS health check, updating windows O/S patch and antivirus scan (EWS0164, HIS0161, HIS0160, HIS0159) | A5210 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:56
9A1AAE9D-D7A1-4761-3A22-08DCBCFE539A | TA00021 | DCS (BOCPP-A) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Perform HIS health check, updating windows O/S patch and antivirus scan (HIS0158, STN0154, BKRSVR01, BKRBRS01) | A5940 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
4F760BA2-7016-4DF1-3A27-08DCBCFE539A | TA00021 | DCS (BOCPP-A) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Perform HIS health check, updating windows O/S patch and antivirus scan (HIS0148, STN 0173, STN0174, STN0175) | A5950 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:56
BF3EF302-0ED7-4C63-3A25-08DCBCFE539A | TA00021 | DCS (BOCPP-A) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Perform HIS health check, updating windows O/S patch and antivirus scan (STN0149, STN0150, STN0151, STN0152) | A6150 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 12:00 | [6 empty] | 2024-08-15 15:56
6A3F4535-620E-4284-3A23-08DCBCFE539A | TA00021 | DCS (BOCPP-A) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Perform HIS health check, updating windows O/S patch and antivirus scan (STN0152, STN0170) | A6160 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 13:00 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:56
DDE7F2CE-6143-43A5-3A24-08DCBCFE539A | TA00021 | DCS (BOCPP-A) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Perform FCS health check, L2SW maintenance (FCS0101, FCS0102, FCS0103, FCS0104) | A6170 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
75296820-AF1D-48F1-3A21-08DCBCFE539A | TA00021 | DCS (BOCPP-A) | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 70 | Perform spare count checking and record updates (EWS0164) | A6180 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
9013FD53-BC84-4B13-3A20-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform logic backup before start work | A5080 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 15:00 | [6 empty] | 2024-08-15 15:56
FA1CBC93-8388-4450-3A1B-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Export IO list extracted from logic program and save a copy or print for reference | A5090 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 15:00 | 2024-08-25 16:00 | [6 empty] | 2024-08-15 15:56
A09BC4BA-1197-471C-3A1C-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Perform hardware checking and record | A5100 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-25 16:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
0381FCF4-AB36-4A9A-3A1D-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Verify any trouble triggered on the EQP Faceplate and record | A5110 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:56
48210173-339B-4CA1-3A18-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Perform physical inspection IO Status | A5120 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-27 09:00 | [6 empty] | 2024-08-15 15:56
9413476E-2577-4024-3A1A-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Bypassed critical signal connected to the system | A5130 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 09:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
92F8EA67-AD1F-44E2-3A19-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 70 | Perform Loop check by trigger any input (Upon request and approval) | A5140 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:56
59941DC7-6624-4D63-3A1E-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 80 | Verify controller status | A5150 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:56
6291D933-2868-4BB7-3A1F-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 90 | Perform redundancy test | A5160 | 1 | 1 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 14:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:56
57A23788-9E23-46F0-3A15-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 100 | Earthing measurement | A5170 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 15:00 | 2024-08-27 15:30 | [6 empty] | 2024-08-15 15:56
E67851D8-55B4-4217-3A16-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 110 | EQP panel inspection (Fans, door handle, lamp) | A5180 | 0.5 | 0.5 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 15:30 | 2024-08-27 16:00 | [6 empty] | 2024-08-15 15:56
3E61F35E-0E55-4621-3A17-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 120 | System IO Spare Check | A5190 | 2 | 2 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-27 16:00 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:56
ADCF9782-C739-403D-3A14-08DCBCFE539A | TA00020 | EQP Addressable System | Bokor | BOCPP-A |  | Safe Guarding System | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 130 | Record all the reading and findings in check sheet | A5200 | 4 | 4 | 0 |  | AICITS00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
28CCCE7F-3C28-4DCD-3A13-08DCBCFE539A | TA00019 | ABV-1210 | Bokor | BODP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 10 | Perform physical isolation | A3560 | 1 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-31 08:00 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:56
51E9B543-C7A3-41D8-3A0F-08DCBCFE539A | TA00019 | ABV-1210 | Bokor | BODP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 20 | Remove ABV & control panel accessories | A3570 | 2 | 8 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 11:00 | [6 empty] | 2024-08-15 15:56
4D14F5A8-A6EC-47A0-3A11-08DCBCFE539A | TA00019 | ABV-1210 | Bokor | BODP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 30 | Install ABV | A3580 | 2 | 8 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-31 11:00 | 2024-08-31 14:00 | [6 empty] | 2024-08-15 15:56
6C14991C-443D-4592-3A12-08DCBCFE539A | TA00019 | ABV-1210 | Bokor | BODP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 40 | Manual torquing valve flange bolt | A3590 | 1 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-31 14:00 | 2024-08-31 15:00 | [6 empty] | 2024-08-15 15:56
4BACF205-428E-4D90-3A0E-08DCBCFE539A | TA00019 | ABV-1210 | Bokor | BODP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 50 | Instrumentation work (Control panel installation, tubing tie in & cable glanding) | A3600 | 1 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-31 15:00 | 2024-08-31 16:00 | [6 empty] | 2024-08-15 15:56
4425430B-E43C-48E8-3A10-08DCBCFE539A | TA00019 | ABV-1210 | Bokor | BODP-A |  | Control Valve | Instrument & Control | Maintenance | PPM | Prelim | Instrument | Execution | 60 | Pre-testing & testing commissioning | A3610 | 1 | 4 | 0 |  | AICSER05 |  |  | 0 |  | 2024-08-31 16:00 | 2024-08-31 17:00 | [6 empty] | 2024-08-15 15:56
0F4A6A50-0E2F-4D12-3A00-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | PIPE SUPPORT (PHOTO 104): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1000 | 7 | 49 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-27 09:00 | [6 empty] | 2024-08-15 15:56
3A56FCAD-48A0-46B4-39F5-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | PIPE SUPPORT (PHOTO 104): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1020 | 6 | 36 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:00 | 2024-08-27 16:00 | [6 empty] | 2024-08-15 15:56
D078A3C0-BD4B-4A77-39EA-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | PIPE SUPPORT (PHOTO 104): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1040 | 4 | 12 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
56BDE538-574A-4C24-3A09-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | PIPE SUPPORT (PHOTO 104): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1060 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
5FCC2B28-5677-4773-3A03-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 50 | PIPE SUPPORT (PHOTO 109): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1080 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 17:00 | [6 empty] | 2024-08-15 15:56
EC0E8C08-7C27-4885-39ED-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 60 | PIPE SUPPORT (PHOTO 109): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1100 | 6 | 36 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 08:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:56
974206CE-1104-4739-3A05-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 70 | PIPE SUPPORT (PHOTO 109): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1120 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 12:00 | [6 empty] | 2024-08-15 15:56
C35FE7A1-B997-4D29-39EF-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 80 | PIPE SUPPORT (PHOTO 109): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1140 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 13:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
8DFDE0BE-82A4-4B6B-39EE-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 90 | PIPE SUPPORT (PHOTO 110): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1160 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:56
7CA47C5F-4AE2-491A-39E3-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 100 | PIPE SUPPORT (PHOTO 110): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1180 | 6 | 36 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
47832F96-4A44-435D-39E8-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 110 | PIPE SUPPORT (PHOTO 110): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1200 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 11:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:56
EBC151F4-5797-46A2-39F7-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 120 | PIPE SUPPORT (PHOTO 110): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1220 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 15:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:56
C1419656-3A96-427B-39FC-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 130 | PIPE SUPPORT (113/128): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1240 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-30 12:00 | [6 empty] | 2024-08-15 15:56
D69433E7-34DA-4DC8-39FB-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 140 | PIPE SUPPORT (113/128): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1260 | 6 | 36 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 13:00 | 2024-08-31 10:00 | [6 empty] | 2024-08-15 15:56
0AFC823D-BCEA-445F-39E7-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 150 | PIPE SUPPORT (113/128): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1280 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 14:00 | 2024-08-30 17:00 | [6 empty] | 2024-08-15 15:56
39DA4728-5A6A-4854-3A07-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 160 | PIPE SUPPORT (113/128): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1300 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 08:00 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:56
421AE0B0-C7DD-4E70-39F2-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 170 | PIPE SUPPORT (PHOTO 106): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1320 | 6 | 42 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 16:00 | [6 empty] | 2024-08-15 15:56
853CD4BF-F10B-4BE2-3A08-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 180 | PIPE SUPPORT (PHOTO 106): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1340 | 5 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 16:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:56
3FF3DC68-36C2-4BA8-39E5-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 190 | PIPE SUPPORT (PHOTO 106): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1360 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
7605D82E-8AD7-4FF6-39F1-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 200 | PIPE SUPPORT (PHOTO 106): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1380 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-27 12:00 | [6 empty] | 2024-08-15 15:56
C0C1003F-9C88-49E2-3A02-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 210 | PIPE SUPPORT (PHOTO 111): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1400 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:56
6A5F73AE-8D47-470C-3A01-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 220 | PIPE SUPPORT (PHOTO 111): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1420 | 5 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:56
AD1EE8BB-945C-4377-39E4-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 230 | PIPE SUPPORT (PHOTO 111): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1440 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 10:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
70053E7D-A5B7-41B1-39EB-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 240 | PIPE SUPPORT (PHOTO 111): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1460 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-28 15:00 | [6 empty] | 2024-08-15 15:56
B650A3B8-EDED-4134-39FF-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 250 | PIPE SUPPORT (PHOTO 107): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1480 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 15:00 | 2024-08-29 11:00 | [6 empty] | 2024-08-15 15:56
EC35D961-1B1A-41F6-39EC-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 260 | PIPE SUPPORT (PHOTO 107): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1500 | 5 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 11:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
58E28E67-39FC-47D7-39F8-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 270 | PIPE SUPPORT (PHOTO 107): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1520 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 13:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:56
5C1D90AC-74AA-4313-3A0C-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 280 | PIPE SUPPORT (PHOTO 107): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1540 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 16:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
D47239DD-9F02-4C11-39FA-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 290 | PIPE SUPPORT (PHOTO 108): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1560 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 14:00 | [6 empty] | 2024-08-15 15:56
EAB5FD1C-86F0-484B-39F0-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 300 | PIPE SUPPORT (PHOTO 108): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1580 | 5 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 14:00 | 2024-08-31 10:00 | [6 empty] | 2024-08-15 15:56
BDA4CE89-8E1D-4691-39F3-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 310 | PIPE SUPPORT (PHOTO 108): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1600 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 15:00 | 2024-08-31 09:00 | [6 empty] | 2024-08-15 15:56
C09556C3-B689-4AE7-3A04-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 320 | PIPE SUPPORT (PHOTO 108): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1620 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 10:00 | [6 empty] | 2024-08-15 15:56
2289C03D-B355-4085-3A06-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 330 | PIPE SUPPORT (PHOTO 114): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.1640 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 10:00 | 2024-08-31 16:00 | [6 empty] | 2024-08-15 15:56
85D89CDB-2865-476F-39F6-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 340 | PIPE SUPPORT (PHOTO 114): INSTALL NEW PIPE SUPPORT | CONS(1)_15.1660 | 6 | 36 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 16:00 | 2024-09-01 14:00 | [6 empty] | 2024-08-15 15:56
03E9DE6E-48BA-4D1D-3A0B-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 350 | PIPE SUPPORT (PHOTO 114): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.1680 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 08:00 | 2024-09-01 11:00 | [6 empty] | 2024-08-15 15:56
A0B885F2-2E1A-4B0E-39E6-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 360 | PIPE SUPPORT (PHOTO 114): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.1700 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 11:00 | 2024-09-01 12:00 | [6 empty] | 2024-08-15 15:56
1C4A6F69-A02F-47D5-3A0A-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 370 | PIPE SUPPORT (PHOTO 149): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.2000 | 4 | 28 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 09:00 | 2024-08-31 14:00 | [6 empty] | 2024-08-15 15:56
9121F850-3A59-47F9-39F4-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 380 | PIPE SUPPORT (PHOTO 149): INSTALL NEW PIPE SUPPORT | CONS(1)_15.2020 | 3 | 18 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 14:00 | 2024-08-31 17:00 | [6 empty] | 2024-08-15 15:56
6ED48FAC-415C-4893-39E2-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 390 | PIPE SUPPORT (PHOTO 149): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.2040 | 3 | 3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 15:00 | 2024-09-01 09:00 | [6 empty] | 2024-08-15 15:56
CC361805-4FD6-4353-39FD-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 400 | PIPE SUPPORT (PHOTO 149): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.2060 | 1 | 3 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:00 | 2024-09-01 10:00 | [6 empty] | 2024-08-15 15:56
67933F1B-CDBC-4026-39FE-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 410 | PIPE SUPPORT (PHOTO 161): REMOVE EXISTING PIPE SUPPORT | CONS(1)_15.3000 | 5 | 35 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 10:00 | 2024-09-01 16:00 | [6 empty] | 2024-08-15 15:56
24513D70-02BB-4059-39E9-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 420 | PIPE SUPPORT (PHOTO 161): INSTALL NEW PIPE SUPPORT | CONS(1)_15.3020 | 6 | 36 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 16:00 | 2024-09-02 14:00 | [6 empty] | 2024-08-15 15:56
E6A2E479-4DDE-4DB9-3A0D-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 430 | PIPE SUPPORT (PHOTO 161): MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_15.3040 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 08:00 | 2024-09-02 11:00 | [6 empty] | 2024-08-15 15:56
7622ADD1-469D-48B5-39F9-08DCBCFE539A | TA00018 | Topside Structure-PS- S Deck(2),C Deck(12) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 440 | PIPE SUPPORT (PHOTO 161): INSTALL NEW I-ROD & U-BOLT | CONS(1)_15.3060 | 1 | 1 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 11:00 | 2024-09-02 12:00 | [6 empty] | 2024-08-15 15:56
C9295D06-B9D4-4CAE-39DE-08DCBCFE539A | TA00017 | 150-PL-13002-61432-NN:Check Valve 6"x600# Rplcmnt | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | CHECK VALVE 6" X 600# (150-PL-13002-61432-NN): INSTALL POSITIVE ISOLATION | CONS(1)_12.1000 | 4 | 8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:45 | 2024-09-01 14:45 | [6 empty] | 2024-08-15 15:56
54667E49-C83E-43C3-39E1-08DCBCFE539A | TA00017 | 150-PL-13002-61432-NN:Check Valve 6"x600# Rplcmnt | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | CHECK VALVE 6" X 600# (150-PL-13002-61432-NN): REMOVE POSITIVE ISOLATION | CONS(1)_12.1080 | 3 | 6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 13:45 | 2024-09-02 16:45 | [6 empty] | 2024-08-15 15:56
1D46ECCF-60A2-44F5-39DF-08DCBCFE539A | TA00017 | 150-PL-13002-61432-NN:Check Valve 6"x600# Rplcmnt | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | CHECK VALVE 6" X 600# (150-PL-13002-61432-NN): REMOVE EXISTING VALVE | CONS(1)_12.1040 | 5 | 25 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:45 | 2024-09-01 15:45 | [6 empty] | 2024-08-15 15:56
826088C6-F764-46F0-39E0-08DCBCFE539A | TA00017 | 150-PL-13002-61432-NN:Check Valve 6"x600# Rplcmnt | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | CHECK VALVE 6" X 600# (150-PL-13002-61432-NN): INSTALL NEW VALVE | CONS(1)_12.1060 | 6 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 15:45 | 2024-09-02 13:45 | [6 empty] | 2024-08-15 15:56
8D04AE75-9CC0-43D8-39DD-08DCBCFE539A | TA00016 | 80-PG-1077-3143 | Bokor | BOK-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 80-PG-1077-3143: INSTALL POSITIVE ISOLATION | CONS(1)_13.1000 | 4 | 16 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 11:00 | 2024-09-01 16:00 | [6 empty] | 2024-08-15 15:56
828CC646-1073-4A76-39DC-08DCBCFE539A | TA00016 | 80-PG-1077-3143 | Bokor | BOK-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 80-PG-1077-3143: REPLACE CORRODED BOLTINGS | CONS(1)_13.1080 | 4 | 12 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 10:00 | 2024-09-02 15:00 | [6 empty] | 2024-08-15 15:56
AFE72C1B-F8A0-4685-39DA-08DCBCFE539A | TA00016 | 80-PG-1077-3143 | Bokor | BOK-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 80-PG-1077-3143: MECHANICAL CLEAN AND TOUCH-UP PAINTING ON THE CORRODED PIPE AND VALVE | CONS(1)_13.1020 | 6 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 16:00 | 2024-09-02 14:00 | [6 empty] | 2024-08-15 15:56
890349E2-DC44-4993-39DB-08DCBCFE539A | TA00016 | 80-PG-1077-3143 | Bokor | BOK-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 80-PG-1077-3143: REMOVE POSITIVE ISOLATION | CONS(1)_13.1060 | 4 | 8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 10:00 | 2024-09-02 15:00 | [6 empty] | 2024-08-15 15:56
81395335-B32F-48D8-39D7-08DCBCFE539A | TA00015 | 300-PL13301-61432: Ball Valve 10"x600# (2 Pcs) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | BALL VALVE 10" X 600# X 2PCS (300-PL13301-61432): INSTALL POSITIVE ISOLATION | CONS(1)_17.1000 | 8 | 24 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-30 09:00 | [6 empty] | 2024-08-15 15:56
6BF6ED2B-717E-47A9-39D8-08DCBCFE539A | TA00015 | 300-PL13301-61432: Ball Valve 10"x600# (2 Pcs) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | BALL VALVE 10" X 600# X 2PCS (300-PL13301-61432): REMOVE EXISTING VALVE | CONS(1)_17.1020 | 8 | 72 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 09:00 | 2024-09-01 09:00 | [6 empty] | 2024-08-15 15:56
364C534B-DF96-4BFD-39D6-08DCBCFE539A | TA00015 | 300-PL13301-61432: Ball Valve 10"x600# (2 Pcs) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | BALL VALVE 10" X 600# X 2PCS (300-PL13301-61432): INSTALL NEW VALVE | CONS(1)_17.1040 | 8 | 72 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:00 | 2024-09-01 17:00 | [6 empty] | 2024-08-15 15:56
26C2BF97-8267-4274-39D9-08DCBCFE539A | TA00015 | 300-PL13301-61432: Ball Valve 10"x600# (2 Pcs) | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | BALL VALVE 10" X 600# X 2PCS (300-PL13301-61432): REMOVE POSITIVE ISOLATION | CONS(1)_17.1060 | 8 | 24 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 17:00 | 2024-09-02 13:00 | [6 empty] | 2024-08-15 15:56
6C9DB72F-D9F1-4F19-39D4-08DCBCFE539A | TA00014 | FPL&TLCP TubingSupport Rectification&Installation | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | FPL & TLCP TUBING SUPPORT RECTIFICATION & INSTALLATION: INSTALL 5 NOS TUBING SUPPORT | CONS(1)_16.1000 | 7 | 84 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 13:00 | 2024-09-02 11:00 | [6 empty] | 2024-08-15 15:56
6A726472-B73D-4A32-39D5-08DCBCFE539A | TA00014 | FPL&TLCP TubingSupport Rectification&Installation | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | FPL & TLCP TUBING SUPPORT RECTIFICATION & INSTALLATION: MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW TUBING | CONS(1)_16.1020 | 5 | 20 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 11:00 | 2024-09-02 17:00 | [6 empty] | 2024-08-15 15:56
BCB25A37-C61D-432E-39CD-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 400-P-027-6101X: INSTALL POSITIVE ISOLATION | CONS(1)_14.1000 | 6 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-26 09:00 | [6 empty] | 2024-08-15 15:56
6FF0082D-C667-4A1B-39D3-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 400-P-027-6101X: FLUSHING AND SOAKING LINEWORK | CONS(1)_14.1020 | 8 | 72 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 09:00 | 2024-08-26 18:00 | [6 empty] | 2024-08-15 15:56
713ABC5A-B78F-4C7C-39D0-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 400-P-027-6101X: CUT AND REMOVE EXISTING SPOOL (FLANGE TO FLANGE REPLACEMENT) | CONS(1)_14.1040 | 46 | 1334 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-31 17:30 | [6 empty] | 2024-08-15 15:56
29DA5246-6875-425A-39D2-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 400-P-027-6101X: INSTALL NEW SPOOL (WELDING - 5 Jts, INCLUDING RT) | CONS(1)_14.1060 | 43 | 1075 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-09-01 08:30 | [6 empty] | 2024-08-15 15:56
C1EB2286-1913-42DB-39D1-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 50 | 400-P-027-6101X: HYDROTEST LINEWORK | CONS(1)_14.1080 | 10 | 80 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 08:30 | 2024-09-02 09:30 | [6 empty] | 2024-08-15 15:56
014ED8E8-1028-4DB9-39CC-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 60 | 400-P-027-6101X: REMOVE POSITIVE ISOLATION | CONS(1)_14.1300 | 10 | 50 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 09:30 | 2024-09-03 10:30 | [6 empty] | 2024-08-15 15:56
A86BB4AC-5F33-41BF-39CF-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 70 | 400-P-027-6101X: REMOVE EXISTING PIPE SUPPORT | CONS(1)_14.1140 | 16 | 176 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-28 14:30 | [6 empty] | 2024-08-15 15:56
DDBF6F3B-2E31-41DB-39CE-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 80 | 400-P-027-6101X: INSTALL NEW PIPE SUPPORT | CONS(1)_14.1160 | 17 | 204 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 13:00 | 2024-08-29 09:30 | [6 empty] | 2024-08-15 15:56
714D364B-8058-4EC5-39CA-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 90 | 400-P-027-6101X: INSTALL NEW I-ROD & U-BOLT | CONS(1)_14.1220 | 4 | 8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:30 | 2024-08-29 14:30 | [6 empty] | 2024-08-15 15:56
28BA2F13-9404-4227-39CB-08DCBCFE539A | TA00013 | 400-P-027-6101X | Bakau | BKP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 100 | 400-P-027-6101X: REPLACE CORRODED BOLTINGS | CONS(1)_14.1240 | 8 | 24 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:30 | 2024-08-30 08:30 | [6 empty] | 2024-08-15 15:56
7D5EE40D-3C74-46E4-39C9-08DCBCFE539A | TA00012 | MOV-104 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | MOV-104: INSTALL POSITIVE ISOLATION | CONS(1)_11.1000 | 4 | 4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:45 | 2024-09-01 14:45 | [6 empty] | 2024-08-15 15:56
1883B387-7EDA-4A1E-39C6-08DCBCFE539A | TA00012 | MOV-104 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | MOV-104: REMOVE EXISTING VALVE | CONS(1)_11.1020 | 5 | 20 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:45 | 2024-09-01 15:45 | [6 empty] | 2024-08-15 15:56
1D45C4AE-B820-41C6-39C8-08DCBCFE539A | TA00012 | MOV-104 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | MOV-104: INSTALL NEW VALVE | CONS(1)_11.1040 | 5.8 | 23 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 15:45 | 2024-09-02 13:30 | [6 empty] | 2024-08-15 15:56
F6196C2A-EB86-4CB8-39C7-08DCBCFE539A | TA00012 | MOV-104 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | MOV-104: REMOVE POSITIVE ISOLATION | CONS(1)_11.1060 | 3.3 | 3.25 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 13:30 | 2024-09-02 16:45 | [6 empty] | 2024-08-15 15:56
01050595-E30F-4CED-39C2-08DCBCFE539A | TA00011 | MOV-103 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | MOV-103: INSTALL POSITIVE ISOLATION | CONS(1)_10.1000 | 4 | 4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 16:00 | 2024-08-31 11:00 | [6 empty] | 2024-08-15 15:56
9275AD28-4865-497E-39C5-08DCBCFE539A | TA00011 | MOV-103 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | MOV-103: REMOVE EXISTING VALVE | CONS(1)_10.1020 | 5 | 20 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 16:00 | 2024-08-31 12:00 | [6 empty] | 2024-08-15 15:56
452A11CF-A8D7-4C3F-39C4-08DCBCFE539A | TA00011 | MOV-103 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | MOV-103: INSTALL NEW VALVE | CONS(1)_10.1040 | 5.8 | 23 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 13:00 | 2024-09-01 09:45 | [6 empty] | 2024-08-15 15:56
AAD0A206-4E49-484B-39C3-08DCBCFE539A | TA00011 | MOV-103 | Bokor | BOCPP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | MOV-103: REMOVE POSITIVE ISOLATION | CONS(1)_10.1060 | 3.3 | 3.25 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:45 | 2024-09-01 14:00 | [6 empty] | 2024-08-15 15:56
42110011-8377-4830-39C0-08DCBCFE539A | TA00010 | 50-BD-4003-11472 | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 50-BD-4003-11472: INSTALL POSITIVE ISOLATION | CONS(1)_09.1000 | 2 | 4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 11:00 | 2024-08-28 09:00 | [6 empty] | 2024-08-15 15:56
DB4AEA9C-D42C-4A58-39BF-08DCBCFE539A | TA00010 | 50-BD-4003-11472 | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 50-BD-4003-11472: REPLACE CORRODED BOLTING AND GASKET | CONS(1)_09.1040 | 6 | 12 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 09:00 | 2024-08-28 16:00 | [6 empty] | 2024-08-15 15:56
2002615F-4841-40DA-39C1-08DCBCFE539A | TA00010 | 50-BD-4003-11472 | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 50-BD-4003-11472: REMOVE POSITIVE ISOLATION | CONS(1)_09.1060 | 2 | 4 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 16:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:56
076553E8-1E7B-41B5-39BB-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 50-PL-203-1801X: INSTALL POSITIVE ISOLATION | CONS(1)_08.1000 | 4 | 8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-25 17:00 | [6 empty] | 2024-08-15 15:56
4378407B-1E8D-4EB2-39B8-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 50-PL-203-1801X: REMOVE EXISTING SPOOL AND SUMP CAISSON COVER PLATE | CONS(1)_08.1020 | 6 | 54 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 08:00 | 2024-08-26 15:00 | [6 empty] | 2024-08-15 15:56
D7B99F90-9A74-4325-39BA-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 50-PL-203-1801X: REMOVE EXISTING PIPE SUPPORT | CONS(1)_08.1040 | 4 | 20 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
D6CECF76-EFE1-4AB2-39B5-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 50-PL-203-1801X: REMOVE EXISTING TUNDISH | CONS(1)_08.1060 | 3 | 15 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-27 09:00 | [6 empty] | 2024-08-15 15:56
556B1B36-770E-45D3-39B7-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 50 | 50-PL-203-1801X: INSTALL NEW SPOOL AND SUMP CAISSON COVER PLATE (BONLOK: 1jt, HW: plate-piping) | CONS(1)_08.1080 | 7 | 56 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 15:00 | 2024-08-27 14:00 | [6 empty] | 2024-08-15 15:56
122AE90D-97EF-4BD1-39BE-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 60 | 50-PL-203-1801X: INSTALL NEW PIPE SUPPORT | CONS(1)_08.1100 | 4 | 24 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-27 15:00 | [6 empty] | 2024-08-15 15:56
82299223-304A-4256-39B9-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 70 | 50-PL-203-1801X: INSTALL NEW TUNDISH | CONS(1)_08.1120 | 2 | 12 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 09:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
3ACA1D3B-8F0D-438D-39BD-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 80 | 50-PL-203-1801X: HYDROTEST LINEWORK | CONS(1)_08.1140 | 8 | 24 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 14:00 | 2024-08-28 14:00 | [6 empty] | 2024-08-15 15:56
5630C8CE-2465-47F6-39BC-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 90 | 50-PL-203-1801X: INSTALL NEW I-ROD & U-BOLT | CONS(1)_08.1220 | 3 | 6 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 14:00 | 2024-08-28 17:00 | [6 empty] | 2024-08-15 15:56
4D972EB8-B208-4E04-39B6-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 100 | 50-PL-203-1801X: REPLACE CORRODED BLIND FLANGE | CONS(1)_08.1240 | 4 | 8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 08:00 | 2024-08-29 12:00 | [6 empty] | 2024-08-15 15:56
B4DC5A93-686A-480D-39B4-08DCBCFE539A | TA00009 | 50-PL-203-1801X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 110 | 50-PL-203-1801X: REMOVE POSITIVE ISOLATION | CONS(1)_08.1260 | 4 | 16 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 15:00 | [6 empty] | 2024-08-15 15:56
B691A8D1-233F-4571-39B2-08DCBCFE539A | TA00008 | 80/100-BD-4001-11472/1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 80/100-BD-4001-11472/1103X: INSTALL POSITIVE ISOLATION | CONS(1)_07.1000 | 4.5 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 14:00 | 2024-09-01 09:30 | [6 empty] | 2024-08-15 15:56
7C95FFF7-1416-40B7-39B0-08DCBCFE539A | TA00008 | 80/100-BD-4001-11472/1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 80/100-BD-4001-11472/1103X: REMOVE EXISTING SPOOL (FLANGE TO FLANGE REPLACEMENT) | CONS(1)_07.1020 | 5 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 09:30 | 2024-09-01 15:30 | [6 empty] | 2024-08-15 15:56
16C3CF9C-11DD-4959-39B3-08DCBCFE539A | TA00008 | 80/100-BD-4001-11472/1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 80/100-BD-4001-11472/1103X: INSTALL NEW SPOOL (FLANGE TO FLANGE REPLACEMENT) | CONS(1)_07.1040 | 5 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 15:30 | 2024-09-02 11:30 | [6 empty] | 2024-08-15 15:56
29766A51-AC93-4550-39B1-08DCBCFE539A | TA00008 | 80/100-BD-4001-11472/1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 80/100-BD-4001-11472/1103X: REMOVE POSITIVE ISOLATION | CONS(1)_07.1120 | 4.5 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-02 11:30 | 2024-09-02 17:00 | [6 empty] | 2024-08-15 15:56
A23DE981-81F8-446D-39AC-08DCBCFE539A | TA00007 | 150-PD-301-1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 150-PD-301-1103X: INSTALL POSITIVE ISOLATION | CONS(1)_06.1000 | 14 | 112 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
4B404F1E-B208-47E7-39AA-08DCBCFE539A | TA00007 | 150-PD-301-1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 150-PD-301-1103X: FLUSHING AND SOAKING LINEWORK | CONS(1)_06.1020 | 16 | 128 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 10:00 | 2024-08-29 10:00 | [6 empty] | 2024-08-15 15:56
A57E4BBC-E9CF-402D-39AB-08DCBCFE539A | TA00007 | 150-PD-301-1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 150-PD-301-1103X: CUT AND REMOVE EXISTING SPOOL | CONS(1)_06.1040 | 6 | 72 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 10:00 | 2024-08-29 17:00 | [6 empty] | 2024-08-15 15:56
F57573AE-3EA4-45DD-39AD-08DCBCFE539A | TA00007 | 150-PD-301-1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 150-PD-301-1103X: INSTALL NEW SPOOL (SECTIONAL REPLACEMENT with BONLOK) | CONS(1)_06.1060 | 7 | 70 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 08:00 | 2024-08-30 16:00 | [6 empty] | 2024-08-15 15:56
5FAF2723-4C8F-4756-39AE-08DCBCFE539A | TA00007 | 150-PD-301-1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 50 | 150-PD-301-1103X: HYDROTEST LINEWORK | CONS(1)_06.1080 | 8 | 72 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 16:00 | 2024-08-31 16:00 | [6 empty] | 2024-08-15 15:56
E45B6FB5-28F9-49F7-39AF-08DCBCFE539A | TA00007 | 150-PD-301-1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 60 | 150-PD-301-1103X: INSTALL NEW I-ROD & U-BOLT | CONS(1)_06.1140 | 1 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 16:00 | 2024-08-31 17:00 | [6 empty] | 2024-08-15 15:56
C93E84FE-72CC-4CD8-39A9-08DCBCFE539A | TA00007 | 150-PD-301-1103X | Bokor | BODP-C |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 70 | 150-PD-301-1103X: REMOVE POSITIVE ISOLATION | CONS(1)_06.1160 | 14 | 112 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 08:00 | 2024-09-02 15:00 | [6 empty] | 2024-08-15 15:56
18B4F02F-8630-4EF9-39A6-08DCBCFE539A | TA00006 | 100-BD-322-11432 | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 100-BD-322-11432: INSTALL POSITIVE ISOLATION | CONS(1)_05.1000 | 6 | 18 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 09:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:56
E1256A45-07AB-46AF-39A4-08DCBCFE539A | TA00006 | 100-BD-322-11432 | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 100-BD-322-11432: REMOVE EXISTING SPOOL (FLANGE TO FLANGE REPLACEMENT) | CONS(1)_05.1020 | 6 | 36 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 09:00 | 2024-08-30 16:00 | [6 empty] | 2024-08-15 15:56
478BAC36-8E0F-45C6-39A7-08DCBCFE539A | TA00006 | 100-BD-322-11432 | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 100-BD-322-11432: INSTALL NEW SPOOL (FLANGE TO FLANGE REPLACEMENT) | CONS(1)_05.1040 | 5 | 30 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 16:00 | 2024-08-31 12:00 | [6 empty] | 2024-08-15 15:56
1B085790-EAA9-405F-39A5-08DCBCFE539A | TA00006 | 100-BD-322-11432 | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 100-BD-322-11432: REPLACE BOLTINGS | CONS(1)_05.1120 | 6 | 12 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 13:00 | 2024-09-01 10:00 | [6 empty] | 2024-08-15 15:56
A60B6F5E-76BC-46AF-39A8-08DCBCFE539A | TA00006 | 100-BD-322-11432 | Bokor | BODP-B |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 50 | 100-BD-322-11432: REMOVE POSITIVE ISOLATION | CONS(1)_05.1140 | 8 | 24 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 13:00 | 2024-09-01 12:00 | [6 empty] | 2024-08-15 15:56
A7DC603D-A78E-4D96-39A2-08DCBCFE539A | TA00005 | 300-PG-644-61XXX(R930)-Ball Valve 12"x600#Rplcmnt | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | BALL VALVE 12" X 600# (300-PG-644-61XXX (R930)): INSTALL POSITIVE ISOLATION | CONS(1)_04.1000 | 6 | 12 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-30 11:00 | [6 empty] | 2024-08-15 15:56
0CC00325-84F0-4217-39A0-08DCBCFE539A | TA00005 | 300-PG-644-61XXX(R930)-Ball Valve 12"x600#Rplcmnt | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | BALL VALVE 12" X 600# (300-PG-644-61XXX (R930)): REMOVE EXISTING VALVE | CONS(1)_04.1020 | 8 | 40 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-31 11:00 | [6 empty] | 2024-08-15 15:56
EA5401E1-FBBB-428C-39A3-08DCBCFE539A | TA00005 | 300-PG-644-61XXX(R930)-Ball Valve 12"x600#Rplcmnt | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | BALL VALVE 12" X 600# (300-PG-644-61XXX (R930)): INSTALL NEW VALVE | CONS(1)_04.1040 | 8 | 40 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 11:00 | 2024-09-01 11:00 | [6 empty] | 2024-08-15 15:56
A07F4C02-DAE7-47DF-39A1-08DCBCFE539A | TA00005 | 300-PG-644-61XXX(R930)-Ball Valve 12"x600#Rplcmnt | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | BALL VALVE 12" X 600# (300-PG-644-61XXX (R930)): REMOVE POSITIVE ISOLATION | CONS(1)_04.1060 | 6 | 12 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 11:00 | 2024-09-02 09:00 | [6 empty] | 2024-08-15 15:56
11C50F94-AD30-4767-399E-08DCBCFE539A | TA00002 | 50-PG-131-61432 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 50-PG-131-61432: REMOVE EXISTING PIPE SUPPORT | CONS(1)_02.1000 | 6 | 54 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-26 10:00 | [6 empty] | 2024-08-15 15:56
3248F6ED-CB71-4DDF-399C-08DCBCFE539A | TA00002 | 50-PG-131-61432 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 50-PG-131-61432: INSTALL NEW PIPE SUPPORT | CONS(1)_02.1020 | 6 | 60 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 10:00 | 2024-08-26 17:00 | [6 empty] | 2024-08-15 15:56
F099405A-415F-4494-399D-08DCBCFE539A | TA00002 | 50-PG-131-61432 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 50-PG-131-61432: MECHANICAL CLEAN AND TOUCH-UP PAINTING AFTER INSTALL NEW PIPE SUPPORT | CONS(1)_02.1040 | 3 | 9 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 11:00 | [6 empty] | 2024-08-15 15:56
7FB740E3-6DDE-4237-399F-08DCBCFE539A | TA00002 | 50-PG-131-61432 | Bokor | BODP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 50-PG-131-61432: INSTALL NEW I-ROD & U-BOLT | CONS(1)_02.1060 | 2 | 2 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-27 08:00 | 2024-08-27 10:00 | [6 empty] | 2024-08-15 15:56
BA70AC3B-9474-487E-3995-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 10 | 150-PD-0300-1101X: INSTALL POSITIVE ISOLATION | CONS(1)_01.1000 | 7 | 56 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-25 13:00 | 2024-08-26 11:00 | [6 empty] | 2024-08-15 15:56
D4C176FD-D6B4-433C-3998-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 20 | 150-PD-0300-1101X: FLUSHING AND SOAKING LINEWORK | CONS(1)_01.1020 | 16 | 128 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-26 11:00 | 2024-08-28 11:00 | [6 empty] | 2024-08-15 15:56
86ADC2C0-D452-4999-3994-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 30 | 150-PD-0300-1101X: CUT AND REMOVE EXISTING SPOOL (SECTIONAL REPLACEMENT) | CONS(1)_01.1040 | 12 | 120 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 11:00 | 2024-08-29 16:00 | [6 empty] | 2024-08-15 15:56
86300114-D23B-451E-399A-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 40 | 150-PD-0300-1101X: REMOVE EXISTING PIPE SUPPORT | CONS(1)_01.1060 | 6 | 54 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-28 11:00 | 2024-08-29 09:00 | [6 empty] | 2024-08-15 15:56
5BFDBDEF-007E-40D5-399B-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 50 | 150-PD-0300-1101X: INSTALL NEW SPOOL (SECTIONAL REPLACEMENT with BONLOK) | CONS(1)_01.1080 | 11 | 99 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-31 15:00 | [6 empty] | 2024-08-15 15:56
2944A680-0A4D-47AB-3996-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 60 | 150-PD-0300-1101X: INSTALL NEW PIPE SUPPORT | CONS(1)_01.1100 | 6 | 54 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-29 14:00 | 2024-08-30 11:00 | [6 empty] | 2024-08-15 15:56
98F2C5A6-BF39-4C1E-3997-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 70 | 150-PD-0300-1101X: HYDROTEST LINEWORK | CONS(1)_01.1120 | 8 | 72 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-30 11:00 | 2024-08-31 11:00 | [6 empty] | 2024-08-15 15:56
74081789-273F-4839-3999-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 80 | 150-PD-0300-1101X: INSTALL NEW I-ROD & U-BOLT | CONS(1)_01.1180 | 4 | 8 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 11:00 | 2024-08-31 16:00 | [6 empty] | 2024-08-15 15:56
3AAC25F4-3E76-4762-3993-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 90 | 150-PD-0300-1101X: REPLACE CORRODED BOLTINGS | CONS(1)_01.1200 | 8 | 16 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-08-31 16:00 | 2024-09-01 16:00 | [6 empty] | 2024-08-15 15:56
60792382-4869-49E2-3992-08DCBCFE539A | TA00001 | 150-PD-0300-1101X | Bokor | BOP-A |  | Piping | Construction | Maintenance | PPM | Prelim | Construction | Execution | 100 | 150-PD-0300-1101X: REMOVE POSITIVE ISOLATION | CONS(1)_01.1220 | 7 | 56 | 0 |  | ACOOTH00 |  |  | 0 |  | 2024-09-01 16:00 | 2024-09-02 15:00 | [6 empty] | 2024-08-15 15:56
Applied filters: EventCode is BOBELABKTA2024 OPUCode is SKA